MCQ-5043 | RCQE-sourced question (Second-level RCQE in 2023) | SD4 Quality control | SD4-2 System of quality control in construction engineering | MAMCQ | No | 88、 下列工程施工质量保证手段和措施中，属于组织保证体系内容的有（ ）。 A 按照规范进行施工 B 建立健全各种规章制度 C 落实建筑工人实名制管理 D 建立质量信息系统 E 按照规范标准进行检查验收 | 88、 下列工程施工质量保证手段和措施中，属于组织保证体系内容的有（ ）。 A 按照规范进行施工 B 建立健全各种规章制度 C 落实建筑工人实名制管理 D 建立质量信息系统 E 按照规范标准进行检查验收 | 88. Among the following engineering construction quality assurance means and measures, which belong to the organizational assurance system, are (). A construction in accordance with the norms B establish and improve a variety of rules and regulations C implementation of construction workers real-name system management D establish quality information system E in accordance with the norms and standards for inspection and acceptance
MCQ-5044 | RCQE-sourced question (Second-level RCQE in 2023) | SD2 Cost management | SD2-2 Cost planning | MAMCQ | No | 89、 下列建筑安装工程措施项目费中，宜采用综合单价法计价的有（ ）。 A 冬雨期施工增加费 B 垂直运输工程费 C 混凝土模板工程费 D 夜间施工增加费 E 脚手架工程费 | 89、 下列建筑安装工程措施项目费中，宜采用综合单价法计价的有（ ）。 A 冬雨期施工增加费 B 垂直运输工程费 C 混凝土模板工程费 D 夜间施工增加费 E 脚手架工程费 | 89. Among the following construction and installation project measures, it is appropriate to use the comprehensive unit price method for pricing (). A winter rain period construction increase fee B vertical transportation engineering fee C concrete formwork engineering fee D night construction increase fee E scaffold engineering fee
MCQ-5045 | RCQE-sourced question (Second-level RCQE in 2023) | SD1 Organization and management | SD1-10 Construction engineering supervision | MAMCQ | No | 90、 根据《建设工程监理规范》，监理实施细则的编制依据有（ ）。 A 工程设计文件 B 工程承包合同 C 施工组织设计 D 专项施工方案 E 质量管理体系文件 | 90、 根据《建设工程监理规范》，监理实施细则的编制依据有（ ）。 A 工程设计文件 B 工程承包合同 C 施工组织设计 D 专项施工方案 E 质量管理体系文件 | 90. According to the "construction engineering supervision Code", the preparation of supervision implementation rules based on (). A engineering design document B engineering contract C construction organization design D special construction plan E quality management system document
MCQ-5046 | RCQE-sourced question (Second-level RCQE in 2023) | SD6 Contracts and contract management | SD6-2 Contract contents of construction engineering | MAMCQ | No | 91、 根据《建设工程施工专业分包合同（示范文本）》，下列工作中，属于承包人（总承包单位）责任和义务的有（ ）。 A 提供总包合同相关内容供分包人查阅 B 向分包人提供具备施工条件的施工场地 C 组织分包人参加由发包人组织的图纸会审 D 要求分包人及时提供分包工程进度统计报表 E 为分包人所分包的工作提供详细施工组织设计 | 91、 根据《建设工程施工专业分包合同（示范文本）》，下列工作中，属于承包人（总承包单位）责任和义务的有（ ）。 A 提供总包合同相关内容供分包人查阅 B 向分包人提供具备施工条件的施工场地 C 组织分包人参加由发包人组织的图纸会审 D 要求分包人及时提供分包工程进度统计报表 E 为分包人所分包的工作提供详细施工组织设计 | 91. According to the "Construction engineering construction professional Subcontract (Model text)", the following work, belonging to the contractor (general contractor) responsibilities and obligations are (). A provides the relevant contents of the general contract for the subcontractor to consult B provides the subcontractor with construction sites with construction conditions C organizes the subcontractor to participate in the joint review of drawings organized by the employer D requires the subcontractor to timely provide statistical reports of the progress of the subcontracted project E Provide detailed construction organization design for the subcontractor's subcontracted work
MCQ-5047 | RCQE-sourced question (Second-level RCQE in 2023) | SD1 Organization and management | SD1-9 Construction engineering risks | MAMCQ | No | 92、 下列工程项目施工风险中，属于组织风险的有（ ）。 A 人身安全控制计划不周 B 施工机械操作人员经验不足 C 存在火灾事故隐患 D 安全管理人员知识欠缺 E 工程施工方案不当 | 92、 下列工程项目施工风险中，属于组织风险的有（ ）。 A 人身安全控制计划不周 B 施工机械操作人员经验不足 C 存在火灾事故隐患 D 安全管理人员知识欠缺 E 工程施工方案不当 | 92. Among the construction risks of the following engineering projects, those belonging to the organization risk are (). A personal safety control plan is inadequate B construction machinery operators lack of experience C there is a potential fire accident D safety management personnel lack of knowledge E project construction plan is improper
MCQ-5048 | RCQE-sourced question (Second-level RCQE in 2023) | SD7 Information management | SD7-2 Information classification, coding, and processing of construction engineering | MAMCQ | No | 93、 下列工程文件资料中，属于工程施工技术管理资料的有（ ）。 A 施工试验记录 B 图纸会审记录文件 C 设计变更文件 D 工程开工报告相关资料 E 工程测量记录文件 | 93、 下列工程文件资料中，属于工程施工技术管理资料的有（ ）。 A 施工试验记录 B 图纸会审记录文件 C 设计变更文件 D 工程开工报告相关资料 E 工程测量记录文件 | 93. Among the following engineering documents and materials, those belonging to the engineering construction technical management materials are (). A construction test record B drawing review record C design change file D project start report related information E project survey record file
MCQ-5049 | RCQE-sourced question (Second-level RCQE in 2023) | SD3 Schedule control | SD3-3 Schedule development and adjustment of construction engineering | MAMCQ | No | 94、 实施性施工进度计划的主要作用有（ ）。 A 分析里程碑事件进度目标 B 分解施工总进度目标 C 进行施工作业具体安排 D 确定月、旬资金需求 E 确定月、旬施工机械需求 | 94、 实施性施工进度计划的主要作用有（ ）。 A 分析里程碑事件进度目标 B 分解施工总进度目标 C 进行施工作业具体安排 D 确定月、旬资金需求 E 确定月、旬施工机械需求 | 94. The main functions of the implementation construction schedule are (). A Analyze the milestone event progress target B decompose the total construction progress target C to carry out the specific arrangement of construction work D to determine the monthly and ten-day capital needs E to determine the monthly and ten-day construction machinery needs
MCQ-5050 | RCQE-sourced question (Second-level RCQE in 2023) | SD5 Occupational health, safety and environment management | SD5-4 Requirements of occupational health, safety and environment management in construction engineering | MAMCQ | No | 95、 按照文明工地标准，下列图牌中，属于施工现场“五牌一图”的有（ ）。 A 组织机构图 B 工程概况牌 C 消防保卫牌 D 安全生产牌 E 文明施工牌 | 95、 按照文明工地标准，下列图牌中，属于施工现场“五牌一图”的有（ ）。 A 组织机构图 B 工程概况牌 C 消防保卫牌 D 安全生产牌 E 文明施工牌 | 95. According to the civilized site standards, among the following cards, belong to the construction site "five cards and one map" are (). A organization chart B Project overview card C fire protection card D safety production card E civilized construction card

## Case-based questions
The CEM-QA test dataset containing 100 case-based questions
No. | Background material in Chinese | Background material in English | Question in Chinese | Question in English
CBQ-001 | 1、某新建住宅小区，单位工程分别为地下2层，地上9~12层，总建筑面积15.5万平方米。各单位为贯彻落实《建设工程质量检测管理办法》（住房和城乡建设部第57号令）要求，在工程施工质量检查管理周边做了以下工作： 建设单位委托具有相应资质的检测机构负责本次工程质量检测工作； 监理工程师对混凝土试样制作与送检进行了见证。试验员如实记录了其取样现场检测等情况，制作了见证记录； 混凝土试样送检时，试验员向检测机构填报了检测委托单； 总包项目按照建设单位要求，每月向检测机构支付当期检测费用。 地下室混凝土模板拆除后，发现混凝土墙体、楼板面存在有蜂窝、麻面、露筋、裂缝、孔洞和层间错台等质量缺陷。项目部按要求制定了质量缺陷处理专项方案，按照“凿除孔洞松散混凝土-......-剔除多余混凝土”的工艺流程进行孔洞质量缺陷治理。 | 1. A new residential community, the unit projects are respectively underground 2 floors, 9~12 floors above the ground, the total construction area of 155,000 square meters. In order to implement the "Measures for the Management of Construction Engineering Quality Inspection" (Order No. 57 of the Ministry of Housing and Urban-Rural Development), the units have done the following work around the construction quality inspection management: The construction unit entrusts the testing institution with corresponding qualifications to be responsible for the project quality inspection; The supervision engineer witnessed the production and inspection of concrete samples. The tester truthfully recorded the sampling site testing and so on, and made a witness record; When the concrete sample was submitted for inspection, the tester filled in the inspection order to the testing institution; The total contract project shall pay the current testing fee to the testing institution every month according to the requirements of the construction unit. After the removal of the basement concrete formwork, it is found that there are quality defects such as honeycomb, pockmarked surface, exposed reinforcement, cracks, holes and inter-floor fault in the concrete wall and floor surface. The project department has formulated a special quality defect treatment plan according to the requirements, which is "excavating loose concrete with holes -...... - Remove excess concrete "process flow to carry out the hole quality defect treatment. | 1、指出工程施工质量检测管理工作中的不妥之处，并写出正确做法（本问题2项不妥，多答不得分）。混凝土试样制作与取样见证记录还有哪些？ | 1. Point out the inadequacies in the construction quality inspection and management work, and write out the correct approach (2 inadequacies in this question, multiple answers do not score). What are the witness records of concrete sample making and sampling?
CBQ-002 | 2、某新建住宅小区，单位工程分别为地下2层，地上9~12层，总建筑面积15.5万平方米。各单位为贯彻落实《建设工程质量检测管理办法》（住房和城乡建设部第57号令）要求，在工程施工质量检查管理周边做了以下工作： 建设单位委托具有相应资质的检测机构负责本次工程质量检测工作； 监理工程师对混凝土试样制作与送检进行了见证。试验员如实记录了其取样现场检测等情况，制作了见证记录； 混凝土试样送检时，试验员向检测机构填报了检测委托单； 总包项目按照建设单位要求，每月向检测机构支付当期检测费用。 地下室混凝土模板拆除后，发现混凝土墙体、楼板面存在有蜂窝、麻面、露筋、裂缝、孔洞和层间错台等质量缺陷。项目部按要求制定了质量缺陷处理专项方案，按照“凿除孔洞松散混凝土-......-剔除多余混凝土”的工艺流程进行孔洞质量缺陷治理。 | 2. A new residential community, the unit projects are respectively underground 2 floors, 9~12 floors above the ground, the total construction area of 155,000 square meters. In order to implement the "Measures for the Management of Construction Engineering Quality Inspection" (Order No. 57 of the Ministry of Housing and Urban-Rural Development), the units have done the following work around the construction quality inspection management: The construction unit entrusts the testing institution with corresponding qualifications to be responsible for the project quality inspection; The supervision engineer witnessed the production and inspection of concrete samples. The tester truthfully recorded the sampling site testing and so on, and made a witness record; When the concrete sample was submitted for inspection, the tester filled in the inspection order to the testing institution; The total contract project shall pay the current testing fee to the testing institution every month according to the requirements of the construction unit. After the removal of the basement concrete formwork, it is found that there are quality defects such as honeycomb, pockmarked surface, exposed reinforcement, cracks, holes and inter-floor fault in the concrete wall and floor surface. The project department has formulated a special quality defect treatment plan according to the requirements, which is "excavating loose concrete with holes -...... - Remove excess concrete "process flow to carry out the hole quality defect treatment. | 2、补充完整混凝土表面孔洞质量缺陷治理工艺流程内容。 | 2. Supplement the complete concrete surface hole quality defects treatment process content.
CBQ-003 | 3、某施工企业中标一新建办公楼工程，地下二层，地上二十八层。钢筋混凝土灌注桩基础，上部为框架剪力墙结构，建筑面积28600平方米。 项目部在开工后编制了项目质量计划，内容包括质量目标和要求、管理组织体系及管理职责、质量控制点等，并根据工程进展实施静态管理。其中，设置质量控制点的关键部位和环节包括：影响施工质量的关键部位和环节；影响使用功能的关键部位和环节；采用新材料、新设备的部位和环节等。 桩基施工完成后，项目部采用高应变法按要求进行了工程桩桩身完整性检测，其抽检数量按照相关标准规定选取。 钢筋施工专项技术方案中规定：采用专用量规等检测工具对钢筋直螺纹加工和安装质量进行检测；纵向受力钢筋采用机械连接或焊接接头时的接头面积百分率等要求如下： 受拉接头不宜大于50%； 受压接头不宜大于75%； 直接承受动力荷载的结构件不宜采用焊接； 直接承受动力荷载的结构构件采用机械连接时，不宜超过50%。 项目部质量员在现场发现屋面卷材有流淌现象，经质量分析讨论，对产生屋面卷材流淌现象的原因分析如下： 胶结料耐热度偏低； 找平层的分格缝设置不当； 胶结料粘结层过厚； 屋面板因温度变化产生胀缩； 卷材搭接长度太小。 针对原因分析，整改方案采用钉钉子法：在卷材上部离屋脊200～350mm范围内钉一排20mm长圆钉，钉眼涂防锈漆。 监理工程师认为屋面卷材流淌现象的原因分析和钉钉子法做法存在不妥，要求修改。 | 3. A construction enterprise won the bid for a new office building project, with two underground floors and 28 above-ground floors. Reinforced concrete cast-in-place pile foundation, the upper part of the frame shear wall structure, construction area 28600 square meters. The project department prepared the project quality plan after the start of construction, including quality objectives and requirements, management organization system and management responsibilities, quality control points, etc., and implemented static management according to the progress of the project. Among them, the key parts and links to set quality control points include: the key parts and links that affect the construction quality; The key parts and links that affect the use of functions; The parts and links of new materials and new equipment, etc. After the completion of pile foundation construction, the project department used the high strain method to carry out the integrity test of the project pile body according to the requirements, and the number of random inspection was selected in accordance with the relevant standards. As stipulated in the special technical plan of reinforcement construction, the processing and installation quality of reinforcement straight thread are tested by special measuring tools such as gauges; The joint area percentage of mechanical connection or welding joint when the longitudinal stress reinforcement is as follows: the tension joint should not be greater than 50%; The compression joint should not be greater than 75%; Structural parts that directly bear the dynamic load should not be welded; When the structural members that directly bear the dynamic load are mechanically connected, it should not exceed 50%. The quality staff of the project department found the roof coil flowing phenomenon on the site. After quality analysis and discussion, the reasons for the roof coil flowing phenomenon were analyzed as follows: the heat resistance of cement material was low; The partition joint of the screed layer is not set properly; The binder bonding layer is too thick; The roof panel expands and contracts due to temperature change; The lap length of the coil is too small. According to the cause analysis, the rectification plan adopts the nail method: nail a row of 20mm long round nails in the upper part of the coil within 200 ~ 350mm from the ridge, and paint the nail eyes with anti-rust paint. The supervision engineer thinks that the cause analysis of the roof coil flowing phenomenon and the nailing method are inappropriate, and requires modification. | 3、指出工程质量计划编制和管理中的不妥之处，并写出正确做法。工程质量计划中应设置质量控制点的关键部位和环节还有哪些？ | 3. Point out the inadequacies in project quality planning and management, and write out the correct practices. What are the other key parts and links in which quality control points should be set up in the project quality plan?
CBQ-004 | 4、某施工企业中标一新建办公楼工程，地下二层，地上二十八层。钢筋混凝土灌注桩基础，上部为框架剪力墙结构，建筑面积28600平方米。 项目部在开工后编制了项目质量计划，内容包括质量目标和要求、管理组织体系及管理职责、质量控制点等，并根据工程进展实施静态管理。其中，设置质量控制点的关键部位和环节包括：影响施工质量的关键部位和环节；影响使用功能的关键部位和环节；采用新材料、新设备的部位和环节等。 桩基施工完成后，项目部采用高应变法按要求进行了工程桩桩身完整性检测，其抽检数量按照相关标准规定选取。 钢筋施工专项技术方案中规定：采用专用量规等检测工具对钢筋直螺纹加工和安装质量进行检测；纵向受力钢筋采用机械连接或焊接接头时的接头面积百分率等要求如下： 受拉接头不宜大于50%； 受压接头不宜大于75%； 直接承受动力荷载的结构件不宜采用焊接； 直接承受动力荷载的结构构件采用机械连接时，不宜超过50%。 项目部质量员在现场发现屋面卷材有流淌现象，经质量分析讨论，对产生屋面卷材流淌现象的原因分析如下： 胶结料耐热度偏低； 找平层的分格缝设置不当； 胶结料粘结层过厚； 屋面板因温度变化产生胀缩； 卷材搭接长度太小。 针对原因分析，整改方案采用钉钉子法：在卷材上部离屋脊200～350mm范围内钉一排20mm长圆钉，钉眼涂防锈漆。 监理工程师认为屋面卷材流淌现象的原因分析和钉钉子法做法存在不妥，要求修改。 | 4. A construction enterprise won the bid for a new office building project, with two underground floors and 28 above-ground floors. Reinforced concrete cast-in-place pile foundation, the upper part of the frame shear wall structure, construction area 28600 square meters. The project department prepared the project quality plan after the start of construction, including quality objectives and requirements, management organization system and management responsibilities, quality control points, etc., and implemented static management according to the progress of the project. Among them, the key parts and links to set quality control points include: the key parts and links that affect the construction quality; The key parts and links that affect the use of functions; The parts and links of new materials and new equipment, etc. After the completion of pile foundation construction, the project department used the high strain method to carry out the integrity test of the project pile body according to the requirements, and the number of random inspection was selected in accordance with the relevant standards. As stipulated in the special technical plan of reinforcement construction, the processing and installation quality of reinforcement straight thread are tested by special measuring tools such as gauges; The joint area percentage of mechanical connection or welding joint when the longitudinal stress reinforcement is as follows: the tension joint should not be greater than 50%; The compression joint should not be greater than 75%; Structural parts that directly bear the dynamic load should not be welded; When the structural members that directly bear the dynamic load are mechanically connected, it should not exceed 50%. The quality staff of the project department found the roof coil flowing phenomenon on the site. After quality analysis and discussion, the reasons for the roof coil flowing phenomenon were analyzed as follows: the heat resistance of cement material was low; The partition joint of the screed layer is not set properly; The binder bonding layer is too thick; The roof panel expands and contracts due to temperature change; The lap length of the coil is too small. According to the cause analysis, the rectification plan adopts the nail method: nail a row of 20mm long round nails in the upper part of the coil within 200 ~ 350mm from the ridge, and paint the nail eyes with anti-rust paint. The supervision engineer thinks that the cause analysis of the roof coil flowing phenomenon and the nailing method are inappropriate, and requires modification. | 4、灌注桩桩身完整性检测方法还有哪些？桩身完整性抽检数量的标准规定有哪些？ | 4. What are the other testing methods for the integrity of pile body? What are the standard regulations for the quantity of sampling inspection of pile body integrity?
CBQ-005 | 5、某新建学校工程，总建筑面积12.5万平方米，由12栋单体建筑组成，其中主要教学楼为钢筋混凝土框架结构，体育馆屋盖为钢结构，合同要求工程达到绿色建筑三星标准，施工单位中标后，与甲方签订合同并组建项目部。 项目部安全检查制度规定了安全检查主要形式包括：日常巡查，专项检查，经常性安全检查、设备措施安全验收检查等。其中经常性安全检查方式有专职安全人员每天安全巡检，项目经理等专业人员，作业班组按要求时间进行安全检查等。 项目部在塔吊布置是充分考虑了吊装构件重量、运输和堆放，使用后拆除和运输等因素，按照《建筑工程安全检查标准》中“塔式起重机”的载荷限制装置，吊钩、滑轮、卷筒与钢丝绳、验收与使用等保证项目和结构设施等一般项目进行了检查验收。 屋盖钢结构施工高处作业安全专项方案规定如下： 钢结构构件宜地面组装，安全设施一并设置； 坠落高度超过2m的安装使用梯子攀登作业； 施工层搭设的水平通道不设置防护栏杆； 作为水平通道的钢梁一侧两端头设置安全绳； 安全防护采用工具化，定型化设置，防护盖板用黄色和红色标示。 施工单位管理部门在装修阶段对现场施工用电进行专项检查情况如下： 项目仅按照项目临时用电施工组织设计进行施工用电管理； 现场瓷砖切割机与砂浆搅拌机共用一个开关箱； 主教学楼一开关箱使用插座插头与配电箱连接； 专业电工在断电后对木工加工机械进行检查和清理。 | 5. A new school project, with a total construction area of 125,000 square meters, consists of 12 single buildings, among which the main teaching building is reinforced concrete frame structure and the gymnasium roof is steel structure. The contract requires the project to meet the green building three-star standard. After the construction unit wins the bid, it will sign a contract with Party A and set up the project department. The safety inspection system of the project department stipulates that the main forms of safety inspection include: daily inspection, special inspection, regular safety inspection, equipment safety acceptance inspection and so on. Among them, the regular safety inspection methods include daily safety inspection by full-time security personnel, professional personnel such as project managers, and safety inspection by operation teams according to the required time. The project department in the tower crane layout is to fully consider the weight of lifting components, transportation and stacking, demolition and transportation after use and other factors, in accordance with the "construction engineering safety inspection standards" in the "tower crane" load limiting device, hook, pulley, drum and wire rope, acceptance and use of guarantee projects and structural facilities and other general projects were inspected and accepted. Roof steel structure construction high operation safety special program provisions are as follows: steel structure components should be assembled on the ground, safety facilities set together; Falling height of more than 2m installation using ladders climbing operations; The horizontal channel set up by the construction layer does not set protective railings; The two ends of the steel beam on one side of the horizontal passage are provided with safety ropes; The safety protection adopts instrumentalized and standardized setting, and the protection cover plate is marked with yellow and red. The management department of the construction unit shall conduct special inspection on the on-site construction electricity consumption in the decoration stage as follows: The project shall only manage the construction electricity consumption according to the temporary construction organization design of the project; Field tile cutting machine and mortar mixer share a switch box; A switch box of the main teaching building is connected with the distribution box using a socket plug; Professional electricians check and clean the woodworking processing machinery after power failure. | 5、指出钢结构施工高处作业安全防护方案中的不妥之处，并写出正确做法。(本题有3项不妥，多答不得分）。全防护栏杆的条纹警戒标示用什么颜色? | 5. Point out the improper place in the safety protection scheme of steel structure construction height, and write out the correct method. (There are 3 improper items in this question, more answers do not score). What color should be used for the stripe warning mark of the full guard rail?
CBQ-006 | 6、某新建学校工程，总建筑面积12.5万平方米，由12栋单体建筑组成，其中主要教学楼为钢筋混凝土框架结构，体育馆屋盖为钢结构，合同要求工程达到绿色建筑三星标准，施工单位中标后，与甲方签订合同并组建项目部。 项目部安全检查制度规定了安全检查主要形式包括：日常巡查，专项检查，经常性安全检查、设备措施安全验收检查等。其中经常性安全检查方式有专职安全人员每天安全巡检，项目经理等专业人员，作业班组按要求时间进行安全检查等。 项目部在塔吊布置是充分考虑了吊装构件重量、运输和堆放，使用后拆除和运输等因素，按照《建筑工程安全检查标准》中“塔式起重机”的载荷限制装置，吊钩、滑轮、卷筒与钢丝绳、验收与使用等保证项目和结构设施等一般项目进行了检查验收。 屋盖钢结构施工高处作业安全专项方案规定如下： 钢结构构件宜地面组装，安全设施一并设置； 坠落高度超过2m的安装使用梯子攀登作业； 施工层搭设的水平通道不设置防护栏杆； 作为水平通道的钢梁一侧两端头设置安全绳； 安全防护采用工具化，定型化设置，防护盖板用黄色和红色标示。 施工单位管理部门在装修阶段对现场施工用电进行专项检查情况如下： 项目仅按照项目临时用电施工组织设计进行施工用电管理； 现场瓷砖切割机与砂浆搅拌机共用一个开关箱； 主教学楼一开关箱使用插座插头与配电箱连接； 专业电工在断电后对木工加工机械进行检查和清理。 | 6. A new school project, with a total construction area of 125,000 square meters, consists of 12 single buildings, among which the main teaching building is reinforced concrete frame structure and the gymnasium roof is steel structure. The contract requires the project to meet the green building three-star standard. After the construction unit wins the bid, it will sign a contract with Party A and set up the project department. The safety inspection system of the project department stipulates that the main forms of safety inspection include: daily inspection, special inspection, regular safety inspection, equipment safety acceptance inspection and so on. Among them, the regular safety inspection methods include daily safety inspection by full-time security personnel, professional personnel such as project managers, and safety inspection by operation teams according to the required time. The project department in the tower crane layout is to fully consider the weight of lifting components, transportation and stacking, demolition and transportation after use and other factors, in accordance with the "construction engineering safety inspection standards" in the "tower crane" load limiting device, hook, pulley, drum and wire rope, acceptance and use of guarantee projects and structural facilities and other general projects were inspected and accepted. Roof steel structure construction high operation safety special program provisions are as follows: steel structure components should be assembled on the ground, safety facilities set together; Falling height of more than 2m installation using ladders climbing operations; The horizontal channel set up by the construction layer does not set protective railings; The two ends of the steel beam on one side of the horizontal passage are provided with safety ropes; The safety protection adopts instrumentalized and standardized setting, and the protection cover plate is marked with yellow and red. The management department of the construction unit shall conduct special inspection on the on-site construction electricity consumption in the decoration stage as follows: The project shall only manage the construction electricity consumption according to the temporary construction organization design of the project; Field tile cutting machine and mortar mixer share a switch box; A switch box of the main teaching building is connected with the distribution box using a socket plug; Professional electricians check and clean the woodworking processing machinery after power failure. | 6、指出装修阶段施工用电专项安全检查中的不妥之处，并指出正确做法。（本题有3项不妥，多答不得分） | 6. Point out the improper place in the special safety inspection of construction electricity during the decoration stage, and point out the correct way. (There are 3 improper items in this topic, more answers do not score)
CBQ-007 | 7、新建住宅工程，建筑面积12000m2,地下一层，地上十一层，混合结构。 进场前，按质量管理手册要求，针对工程质量问题分类制定了专项防治方案，在工程质量缺陷防治方案中，因严重缺陷对结构构件的使用功能等方面有决定性影响，为此提出具体控制措施。 项目部对二层一单向板验收楼板钢筋绑扎检查时发现：上下层的钢筋网钢筋交叉点均进行了相隔交错扎牢,所有绑扎点的钢丝扣方向一致。对此提出整改要求。 施工员在砌筑工程施工技术交底中要求，先砌筑墙体、再砌筑砖垛，砖垛每隔2皮与砖墙搭砌，砖柱选用至少1/2砖长砌筑。砖柱砌筑应保证砖柱外表面上下皮垂直灰缝相互错开1/4砖长，并不得采用包心砌法。 项目部工程测量专项方案包括：采用国家现行的平面坐标系统及高程标准和时间基准，从地下室砌筑完成后开始到正常施工完成期间，按计划定期对工程进行沉降观测。 | 7. New residential project, construction area of 12000m2, one floor underground, 11 floors above the ground, mixed structure. Before entering the site, according to the requirements of the quality management manual, a special prevention and control plan has been formulated for the classification of engineering quality problems. In the prevention and control plan of engineering quality defects, specific control measures are proposed because serious defects have a decisive impact on the use function of structural members. When the project department checked the binding of steel bars on the two-story one-way plate acceptance floor, it was found that the crossing points of steel mesh bars on the upper and lower layers were separated and staggered, and the direction of the wire buckle at all binding points was the same. Put forward rectification requirements for this. In the disclosure of the construction technology of the masonry project, the construction worker requires that the wall be laid first and then the brick stack. The brick stack is built with the brick wall every 2 skins, and the brick column is constructed with at least 1/2 brick length. Brick column masonry should ensure that the upper and lower skin vertical ash joints on the outer surface of the brick column staggered 1/4 brick length, and shall not use the core building method. The project department's special project survey plan includes: using the current national plane coordinate system and elevation standard and time base, from the completion of basement masonry to the completion of normal construction period, the settlement observation of the project is carried out regularly as planned. | 7、指出楼板钢筋绑扎不妥之处?并写出正确做法。写出板、次梁与主梁交叉处，钢筋的布置位置。 | 7. Point out the improper binding of the floor reinforcement? And write out the correct way. Write the plate, the secondary beam and the main beam intersection, the placement of the steel bar.
CBQ-008 | 8、新建住宅工程，建筑面积12000m2,地下一层，地上十一层，混合结构。 进场前，按质量管理手册要求，针对工程质量问题分类制定了专项防治方案，在工程质量缺陷防治方案中，因严重缺陷对结构构件的使用功能等方面有决定性影响，为此提出具体控制措施。 项目部对二层一单向板验收楼板钢筋绑扎检查时发现：上下层的钢筋网钢筋交叉点均进行了相隔交错扎牢,所有绑扎点的钢丝扣方向一致。对此提出整改要求。 施工员在砌筑工程施工技术交底中要求，先砌筑墙体、再砌筑砖垛，砖垛每隔2皮与砖墙搭砌，砖柱选用至少1/2砖长砌筑。砖柱砌筑应保证砖柱外表面上下皮垂直灰缝相互错开1/4砖长，并不得采用包心砌法。 项目部工程测量专项方案包括：采用国家现行的平面坐标系统及高程标准和时间基准，从地下室砌筑完成后开始到正常施工完成期间，按计划定期对工程进行沉降观测。 | 8. New residential project, construction area of 12000m2, one floor underground, 11 floors above the ground, mixed structure. Before entering the site, according to the requirements of the quality management manual, a special prevention and control plan has been formulated for the classification of engineering quality problems. In the prevention and control plan of engineering quality defects, specific control measures are proposed because serious defects have a decisive impact on the use function of structural members. When the project department checked the binding of steel bars on the two-story one-way plate acceptance floor, it was found that the crossing points of steel mesh bars on the upper and lower layers were separated and staggered, and the direction of the wire buckle at all binding points was the same. Put forward rectification requirements for this. In the disclosure of the construction technology of the masonry project, the construction worker requires that the wall be laid first and then the brick stack. The brick stack is built with the brick wall every 2 skins, and the brick column is constructed with at least 1/2 brick length. Brick column masonry should ensure that the upper and lower skin vertical ash joints on the outer surface of the brick column staggered 1/4 brick length, and shall not use the core building method. The project department's special project survey plan includes: using the current national plane coordinate system and elevation standard and time base, from the completion of basement masonry to the completion of normal construction period, the settlement observation of the project is carried out regularly as planned. | 8、指出砌筑工程施工技术交底中的不妥之处?并写出正确做法。 | 8. Point out the improper place in the disclosure of construction technology of masonry engineering. And write out the correct way.
CBQ-009 | 9、某办公楼工程，地下二层，地上十六层，建筑面积 45000m2，标准间面积为200m2。 施工单位中标后进场施工。 项目部针对现浇混凝土易发生模板系统整体坍塌等安全事故的类型特点，明确现浇混凝土工程安全控制包括模板支撑系统设计、混凝土浇筑用电安全等多项内容，制定了混凝土浇筑施工安全技术措施。 项目部依据项目施工条件等因素，按照机械设备的适应性、高效性等原则，通过市场租赁选择了2台塔吊供现场使用。 公司安全管理部门对项目现场厕所和浴室进行检查时看到：项目在生活区设置有水冲式厕所，现场设有移动式厕所：生活区浴室设有淋浴喷头等设施。 在对现场临时用水管理检查时发现：水管直接埋地穿过临时道路；道路两侧排水沟纵向坡度 0.1%；消火栓最大间距 150m；DN100主供水管实测水流速度 1.5m/s，达不到设计流速 2.0m/s，满足不了设计总用水量 Q＝13.70L/s 的要求，建议更换主供水管。 | 9. An office building project, two underground floors, sixteen above-ground floors, construction area of 45000m2, standard room area of 200m2. The construction unit enters the building after winning the bid. In view of the type characteristics of cast-in-place concrete prone to the overall collapse of formwork system and other safety accidents, the project department clearly defines the safety control of cast-in-place concrete engineering, including formwork support system design, concrete pouring electricity safety and other contents, and formulates concrete pouring construction safety technical measures. According to the project construction conditions and other factors, in accordance with the principles of adaptability and efficiency of mechanical equipment, the project department selected 2 tower cranes for site use through market leasing. When the safety management department of the company inspected the toilets and bathrooms on the project site, it was found that: the project has a flushing toilet in the living area, and a mobile toilet on the site. The bathroom in the living area is equipped with a shower head and other facilities. During the inspection of temporary water management on site, it was found that: the water pipe was directly buried through the temporary road; The longitudinal slope of drainage ditches on both sides of the road is 0.1%; The maximum distance between fire hydrants is 150m; The measured water flow velocity of DN100 main water supply pipe is 1.5m/s, which can not reach the design flow velocity of 2.0m/s, and can not meet the requirements of the design total water consumption Q = 13.70L/s, it is recommended to replace the main water supply pipe. | 9、现浇混凝土工程易发生的安全事故类型还有哪些？现浇混凝土工程安全控制的主要内容还有哪些？ | 9. What other types of safety accidents are prone to occur in cast-in-place concrete projects? What are the main contents of safety control of cast-in-place concrete engineering?
CBQ-010 | 10、某办公楼工程，地下二层，地上十六层，建筑面积 45000m2，标准间面积为200m2。 施工单位中标后进场施工。 项目部针对现浇混凝土易发生模板系统整体坍塌等安全事故的类型特点，明确现浇混凝土工程安全控制包括模板支撑系统设计、混凝土浇筑用电安全等多项内容，制定了混凝土浇筑施工安全技术措施。 项目部依据项目施工条件等因素，按照机械设备的适应性、高效性等原则，通过市场租赁选择了2台塔吊供现场使用。 公司安全管理部门对项目现场厕所和浴室进行检查时看到：项目在生活区设置有水冲式厕所，现场设有移动式厕所：生活区浴室设有淋浴喷头等设施。 在对现场临时用水管理检查时发现：水管直接埋地穿过临时道路；道路两侧排水沟纵向坡度 0.1%；消火栓最大间距 150m；DN100主供水管实测水流速度 1.5m/s，达不到设计流速 2.0m/s，满足不了设计总用水量 Q＝13.70L/s 的要求，建议更换主供水管。 | 10. An office building project, two underground floors, sixteen above-ground floors, construction area of 45000m2, standard room area of 200m2. The construction unit enters the building after winning the bid. In view of the type characteristics of cast-in-place concrete prone to the overall collapse of formwork system and other safety accidents, the project department clearly defines the safety control of cast-in-place concrete engineering, including formwork support system design, concrete pouring electricity safety and other contents, and formulates concrete pouring construction safety technical measures. According to the project construction conditions and other factors, in accordance with the principles of adaptability and efficiency of mechanical equipment, the project department selected 2 tower cranes for site use through market leasing. When the safety management department of the company inspected the toilets and bathrooms on the project site, it was found that: the project has a flushing toilet in the living area, and a mobile toilet on the site. The bathroom in the living area is equipped with a shower head and other facilities. During the inspection of temporary water management on site, it was found that: the water pipe was directly buried through the temporary road; The longitudinal slope of drainage ditches on both sides of the road is 0.1%; The maximum distance between fire hydrants is 150m; The measured water flow velocity of DN100 main water supply pipe is 1.5m/s, which can not reach the design flow velocity of 2.0m/s, and can not meet the requirements of the design total water consumption Q = 13.70L/s, it is recommended to replace the main water supply pipe. | 10、项目在现场厕所、浴室的设施和管理方面还应做到哪些要求？ | 10. What other requirements should be achieved in the facilities and management of on-site toilets and bathrooms?
CBQ-011 | 11、某施工企业参加一建设项目投标，施工企业根据招标文件、工程量清单及其补充通知、答疑纪要、与建设项目相关的标准、规范等技术资料编制了投标文件。 又在工程合同签订前，企业合约部召集本企业的工程、技术、劳务、资金、财务等部门评审，确认了合同与招标、投标文件包含的合同内容、计价方式、工期等一致性。 项目部按计划招标选择劳务作业分包单位，对申请参加投标的劳务分包单位进行资格预审，审核包括劳务分包单位的企业性质、劳动力资源情况等。 施工中，建设单位对某特殊涂料使用范围提出了设计变更，经三方核实，已标价工程量清单中该涂料项目综合单价由35.68元/m3调整为30.68元/m3，工程量由165m3调整为236m3。 施工中，项目部及时提出了以下索赔事项： ①因建设单位未及时交付设计图纸造成工程停工9天，为此，项目部索赔工期9天，现场管理人员工资、奖金共16万元，现场工人窝工补偿费9万元。 ②因建设单位延迟30天支付进度款1000万元，项目部按约定利率索赔利息4.9万元。 ③项目部办公室发生2次位置变动索赔重建费用6万元。 工程竣工后，承包商按合同约定及时办理了工程结算书，合同价款调整包括了误期赔偿、暂列金额、暂估价、工程量偏差、物价变化、施工索赔、发承包双方约定的其他调整事项。 | 11. A construction enterprise participated in the bidding of a construction project, and the construction enterprise prepared the bidding document according to the bidding document, the bill of quantities and its supplementary notice, the minutes of questions and answers, the standards and specifications related to the construction project and other technical data. Before the signing of the project contract, the contract department of the enterprise convenes the engineering, technology, labor, capital, finance and other departments of the enterprise to review and confirm the consistency of the contract with the contract contents, pricing methods, and time limit contained in the bidding and bidding documents. The project department selects the labor subcontracting units according to the bidding plan, and prequalifies the labor subcontracting units that apply to participate in the bidding, including the review of the nature of the labor subcontracting units and the situation of labor resources. During the construction, the construction unit proposed a design change to the scope of use of a special paint. After verification by the three parties, the comprehensive unit price of the paint project in the list of priced quantities was adjusted from 35.68 yuan /m3 to 30.68 yuan /m3, and the quantity of the project was adjusted from 165m3 to 236m3. During the construction, the project department put forward the following claims in time: ① Because the construction unit did not deliver the design drawings in time, the project department stopped work for 9 days, for this reason, the project department claimed the construction period for 9 days, the salary and bonus of the site management staff were 160,000 yuan, and the compensation for the site workers was 90,000 yuan. ② Because the construction unit delayed the payment of 10 million yuan for the progress for 30 days, the project department claimed 49,000 yuan of interest at the agreed interest rate. ③ The office of the project department suffered two location changes, claiming 60,000 yuan for reconstruction costs. After the completion of the project, the contractor handled the project settlement statement in time according to the contract agreement. The adjustment of the contract price includes compensation for delay, provisional amount, provisional valuation, quantity deviation, price changes, construction claims, and other adjustment matters agreed upon by the contracting parties. | 11、工程量清单计价的特点?报价编制依据还有哪些? | 11. What are the characteristics of bill of Quantities pricing? What else is the basis of quotation compilation?
CBQ-012 | 12、某施工企业参加一建设项目投标，施工企业根据招标文件、工程量清单及其补充通知、答疑纪要、与建设项目相关的标准、规范等技术资料编制了投标文件。 又在工程合同签订前，企业合约部召集本企业的工程、技术、劳务、资金、财务等部门评审，确认了合同与招标、投标文件包含的合同内容、计价方式、工期等一致性。 项目部按计划招标选择劳务作业分包单位，对申请参加投标的劳务分包单位进行资格预审，审核包括劳务分包单位的企业性质、劳动力资源情况等。 施工中，建设单位对某特殊涂料使用范围提出了设计变更，经三方核实，已标价工程量清单中该涂料项目综合单价由35.68元/m3调整为30.68元/m3，工程量由165m3调整为236m3。 施工中，项目部及时提出了以下索赔事项： ①因建设单位未及时交付设计图纸造成工程停工9天，为此，项目部索赔工期9天，现场管理人员工资、奖金共16万元，现场工人窝工补偿费9万元。 ②因建设单位延迟30天支付进度款1000万元，项目部按约定利率索赔利息4.9万元。 ③项目部办公室发生2次位置变动索赔重建费用6万元。 工程竣工后，承包商按合同约定及时办理了工程结算书，合同价款调整包括了误期赔偿、暂列金额、暂估价、工程量偏差、物价变化、施工索赔、发承包双方约定的其他调整事项。 | 12. A construction enterprise participated in the bidding of a construction project, and the construction enterprise prepared the bidding document according to the bidding document, the bill of quantities and its supplementary notice, the minutes of questions and answers, the standards and specifications related to the construction project and other technical data. Before the signing of the project contract, the contract department of the enterprise convenes the engineering, technology, labor, capital, finance and other departments of the enterprise to review and confirm the consistency of the contract with the contract contents, pricing methods, and time limit contained in the bidding and bidding documents. The project department selects the labor subcontracting units according to the bidding plan, and prequalifies the labor subcontracting units that apply to participate in the bidding, including the review of the nature of the labor subcontracting units and the situation of labor resources. During the construction, the construction unit proposed a design change to the scope of use of a special paint. After verification by the three parties, the comprehensive unit price of the paint project in the list of priced quantities was adjusted from 35.68 yuan /m3 to 30.68 yuan /m3, and the quantity of the project was adjusted from 165m3 to 236m3. During the construction, the project department put forward the following claims in time: ① Because the construction unit did not deliver the design drawings in time, the project department stopped work for 9 days, for this reason, the project department claimed the construction period for 9 days, the salary and bonus of the site management staff were 160,000 yuan, and the compensation for the site workers was 90,000 yuan. ② Because the construction unit delayed the payment of 10 million yuan for the progress for 30 days, the project department claimed 49,000 yuan of interest at the agreed interest rate. ③ The office of the project department suffered two location changes, claiming 60,000 yuan for reconstruction costs. After the completion of the project, the contractor handled the project settlement statement in time according to the contract agreement. The adjustment of the contract price includes compensation for delay, provisional amount, provisional valuation, quantity deviation, price changes, construction claims, and other adjustment matters agreed upon by the contracting parties. | 12、分别判断索赔事项是否成立,并说明理由。 | 12. Determine whether the claim is established respectively and state the reasons.
CBQ-013 | 13、建设单位发布某新建工程招标文件， 部分条款有：发包范围为土建、水电、通风空调、消防、装饰等工程， 实行施工总承包管理；投标限额为65000.00万元，暂列金额为1500.00万元；工程款按月度完成工作量的80%支付；质量保修金为5%，履约保证金为15%；钢材指定采购本市钢厂的产品；消防及通风空调专项工程合同金额1200.00万元，由建设单位指定发包，总承包服务费3.00%。 投标单位对部分条款提出了异议。 经公开招标，某施工总承包单位中标，签订了施工总承包合同。合同价部分费用有：分部分项工程费48000.00万元，措施项目费为分部分项工程费的15%，规费费率为2.20%，增值税税率为9.00%。 施工总承包单位签订物资采购合同，购买800×800mm的地砖3900块，合同标的规定了地砖的名称、等级、技术标准等内容。地砖由A、B、C三地供应。 | 13. The construction unit issues the bidding document for a new construction project, and some of the terms are as follows: the scope of the contract is civil engineering, hydropower, ventilation and air conditioning, fire fighting, decoration and other projects, and the general contract management shall be implemented; The bidding limit is 650.00 million yuan, and the provisional amount is 1500.00 million yuan; The project payment shall be 80% of the monthly completed work amount; 5. The warranty fee is 5 percent and the performance bond is 15 percent; Steel designated to purchase the city's steel products; The contract value of the special project of fire protection and ventilation and air conditioning is 12.00 million yuan, and the contract is designated by the construction unit. The total contract service fee is 3.00%. 10. The bidder has raised objections to some terms. After public bidding, a general contractor won the bid and signed the general contract for construction. Part of the contract price includes: division project fee of 4800.00 million yuan, measure project fee of 15% of division project fee, fee rate of 2.20%, value-added tax rate of 9.00%. The general contractor of construction signed the material purchase contract to purchase 3,900 800×800mm floor tiles. The object of the contract specifies the name, grade and technical standard of the floor tiles. The floor tiles are supplied by A, B and C. | 13、指出招标文件中的不妥之处，分别说明理由。 | 13. Point out the inadequacies in the bidding documents and explain the reasons respectively.
CBQ-014 | 14、建设单位发布某新建工程招标文件， 部分条款有：发包范围为土建、水电、通风空调、消防、装饰等工程， 实行施工总承包管理；投标限额为65000.00万元，暂列金额为1500.00万元；工程款按月度完成工作量的80%支付；质量保修金为5%，履约保证金为15%；钢材指定采购本市钢厂的产品；消防及通风空调专项工程合同金额1200.00万元，由建设单位指定发包，总承包服务费3.00%。 投标单位对部分条款提出了异议。 经公开招标，某施工总承包单位中标，签订了施工总承包合同。合同价部分费用有：分部分项工程费48000.00万元，措施项目费为分部分项工程费的15%，规费费率为2.20%，增值税税率为9.00%。 施工总承包单位签订物资采购合同，购买800×800mm的地砖3900块，合同标的规定了地砖的名称、等级、技术标准等内容。地砖由A、B、C三地供应。 | 14. The construction unit issues the bidding document for a new construction project, and some of the terms are as follows: the scope of the contract is civil engineering, hydropower, ventilation and air conditioning, fire fighting, decoration and other projects, and the general contract management shall be implemented; The bidding limit is 650.00 million yuan, and the provisional amount is 1500.00 million yuan; The project payment shall be 80% of the monthly completed work amount; 5. The warranty fee is 5 percent and the performance bond is 15 percent; Steel designated to purchase the city's steel products; The contract value of the special project of fire protection and ventilation and air conditioning is 12.00 million yuan, and the contract is designated by the construction unit. The total contract service fee is 3.00%. 10. The bidder has raised objections to some terms. After public bidding, a general contractor won the bid and signed the general contract for construction. Part of the contract price includes: division project fee of 4800.00 million yuan, measure project fee of 15% of division project fee, fee rate of 2.20%, value-added tax rate of 9.00%. The general contractor of construction signed the material purchase contract to purchase 3,900 800×800mm floor tiles. The object of the contract specifies the name, grade and technical standard of the floor tiles. The floor tiles are supplied by A, B and C. | 14、建筑工人满足什么条件才能进入施工现场工作?除建筑工人外，还有哪些单位人员进入施工现场应纳入实名制管理? | 14. What conditions can a construction worker meet to work on a construction site? In addition to construction workers, which units of personnel entering the construction site should be included in the real-name system management?
CBQ-015 | 15、某新建医院工程，地下2层，地上8~16层，总建筑面积11.8万m2。基坑深度9.8m，沉管灌注桩基础，钢筋混凝土结构。 施工单位在桩基础专项施工方案中，根据工程所在地含水量较小的土质特点，确定沉管灌注桩选用单打法成桩工艺，其成桩过程包括桩机就位、锤击（振动）沉管、上料等工作内容。 基础底板大体积混凝土浇筑方案确定了包括环境温度、底板表面与大气温差等多项温度控制指标；明确了温控监测点布置方式，要求沿底板厚度方向测温点间距不大于500mm。 施工作业班组在一层梁、板混凝土强度未达到拆模标准的情况下，进行了部分模板拆除；拆模后，发现梁底表面出现了夹渣、麻面等质量缺陷。监理工程师要求进行整改。装饰工程施工前，项目部按照图纸“三交底”的施工准备工作要求，安排工长向班组长进行了图纸、施工方法和质量标准交底；施工中，认真执行包括工序交接检查等内容的“三检制”，做好质量管理工作。 | 15. A new hospital project has 2 underground floors and 8~16 above-ground floors, with a total construction area of 118,000 m2. The depth of foundation pit is 9.8m, the foundation of immersed pipe cast-in-place pile, reinforced concrete structure. In the special construction plan of pile foundation, according to the soil characteristics of the project location with small water content, the construction unit determines the single method of pile formation. The process of pile formation includes the installation of pile machine, hammer (vibration) sinking pipe, loading and other work contents. A number of temperature control indexes, including environmental temperature, temperature difference between the surface of the base plate and the atmosphere, are determined in the mass concrete pouring scheme of the foundation floor; The layout of temperature control monitoring points is defined, and the distance between temperature measurement points along the thickness direction of the bottom plate is required to be no more than 500mm. Under the condition that the strength of the beam and slab concrete on the first floor is not up to the standard of mold removal, part of the template is removed by the construction team; After the mold removal, it was found that there were quality defects such as slag inclusion and pocked surface on the bottom surface of the beam. The supervising engineer requested rectification. Before the construction of the decoration project, the project department arranged the foreman to disclose the drawings, construction methods and quality standards to the team leader in accordance with the construction preparation requirements of the drawing "three disclosure"; During construction, conscientiously implement the "three inspection system" including process handover inspection and other contents to do a good job in quality management. | 15、沉管灌注桩施工除单打法外，还有哪些方法？成桩过程还有哪些内容？ | 15. In addition to the single method, what are the other methods for the construction of immersed pipe cast-in-place pile? What are the other contents of pile forming process?
CBQ-016 | 16、某新建医院工程，地下2层，地上8~16层，总建筑面积11.8万m2。基坑深度9.8m，沉管灌注桩基础，钢筋混凝土结构。 施工单位在桩基础专项施工方案中，根据工程所在地含水量较小的土质特点，确定沉管灌注桩选用单打法成桩工艺，其成桩过程包括桩机就位、锤击（振动）沉管、上料等工作内容。 基础底板大体积混凝土浇筑方案确定了包括环境温度、底板表面与大气温差等多项温度控制指标；明确了温控监测点布置方式，要求沿底板厚度方向测温点间距不大于500mm。 施工作业班组在一层梁、板混凝土强度未达到拆模标准的情况下，进行了部分模板拆除；拆模后，发现梁底表面出现了夹渣、麻面等质量缺陷。监理工程师要求进行整改。装饰工程施工前，项目部按照图纸“三交底”的施工准备工作要求，安排工长向班组长进行了图纸、施工方法和质量标准交底；施工中，认真执行包括工序交接检查等内容的“三检制”，做好质量管理工作。 | 16. A new hospital project has 2 underground floors and 8~16 above-ground floors, with a total construction area of 118,000 m2. The depth of foundation pit is 9.8m, the foundation of immersed pipe cast-in-place pile, reinforced concrete structure. In the special construction plan of pile foundation, according to the soil characteristics of the project location with small water content, the construction unit determines the single method of pile formation. The process of pile formation includes the installation of pile machine, hammer (vibration) sinking pipe, loading and other work contents. A number of temperature control indexes, including environmental temperature, temperature difference between the surface of the base plate and the atmosphere, are determined in the mass concrete pouring scheme of the foundation floor; The layout of temperature control monitoring points is defined, and the distance between temperature measurement points along the thickness direction of the bottom plate is required to be no more than 500mm. Under the condition that the strength of the beam and slab concrete on the first floor is not up to the standard of mold removal, part of the template is removed by the construction team; After the mold removal, it was found that there were quality defects such as slag inclusion and pocked surface on the bottom surface of the beam. The supervising engineer requested rectification. Before the construction of the decoration project, the project department arranged the foreman to disclose the drawings, construction methods and quality standards to the team leader in accordance with the construction preparation requirements of the drawing "three disclosure"; During construction, conscientiously implement the "three inspection system" including process handover inspection and other contents to do a good job in quality management. | 16、大体积混凝土温控指标还有哪些？ | 16. What are the other temperature control indexes of mass concrete?
CBQ-017 | 17、某酒店工程，建筑面积2.5万m2，地下1层，地上12层。其中标准层10层，每层标准客房18间，35 m2/间；裙房设宴会厅1200m2，层高9m。施工单位中标后开始组织施工。 施工单位企业安全管理部门对项目贯彻企业安全生产管理制度情况进行了检查，检查内容有：安全生产教育培训、安全生产技术管理、分包方安全生产管理、安全生产检查和改进等。 宴会厅施工“满堂脚手架”搭设完成自检后，监理工程师按照《建筑施工安全检查标准》JGJ59要求的保证项目和一般项目对其进行了检查，检查项目包括：施工方案、架体稳定、杆件锁件、脚手板、构配件材质以及荷载。宴会厅顶板混凝土浇筑前，施工技术人员向作业班组进行了安全专项方案交底，针对混凝土浇筑过程中，可能出现的包括浇筑方案不当使支架受力不均衡，产生集中荷载、偏心荷载等多种安全隐患形式，提出了预防措施。 | 17. A hotel project, construction area of 25,000 square meters, 1 underground floor, 12 floors above ground. Among them, there are 10 standard floors, 18 standard rooms on each floor, 35 m2/ room; The skirt room has a banquet hall of 1200m2 with a height of 9m. The construction unit shall organize the construction after winning the bid. The enterprise safety management department of the construction unit inspected the implementation of the enterprise safety production management system of the project, including: safety production education and training, safety production technology management, subcontractor safety production management, safety production inspection and improvement. After the completion of the self-inspection of the "full hall scaffold" construction in the banquet hall, the supervision engineer inspected it according to the guarantee items and general items required by the "Building Construction Safety Inspection Standard" JGJ59. The inspection items include: construction scheme, frame stability, bar lock, foot and hand plate, structure and accessories material and load. Before the concrete pouring of the banquet hall roof, the construction technicians disclosed the special safety plan to the operation team. In view of the concrete pouring process, there may be a variety of safety hazards, including improper pouring plan to make the support unbalanced, concentrated load, eccentric load and so on, and put forward preventive measures. | 17、写出满堂脚手架检查内容中的空缺项，分别写出属于保证项目和一般项目的检查内容。 | 17. Write the empty items in the inspection content of the scaffolding, respectively write the inspection content of the guarantee project and the general project.
CBQ-018 | 18、某酒店工程，建筑面积2.5万m2，地下1层，地上12层。其中标准层10层，每层标准客房18间，35 m2/间；裙房设宴会厅1200m2，层高9m。施工单位中标后开始组织施工。 施工单位企业安全管理部门对项目贯彻企业安全生产管理制度情况进行了检查，检查内容有：安全生产教育培训、安全生产技术管理、分包方安全生产管理、安全生产检查和改进等。 宴会厅施工“满堂脚手架”搭设完成自检后，监理工程师按照《建筑施工安全检查标准》JGJ59要求的保证项目和一般项目对其进行了检查，检查项目包括：施工方案、架体稳定、杆件锁件、脚手板、构配件材质以及荷载。宴会厅顶板混凝土浇筑前，施工技术人员向作业班组进行了安全专项方案交底，针对混凝土浇筑过程中，可能出现的包括浇筑方案不当使支架受力不均衡，产生集中荷载、偏心荷载等多种安全隐患形式，提出了预防措施。 | 18. A hotel project, construction area of 25,000 square meters, 1 underground floor, 12 floors above ground. Among them, there are 10 standard floors, 18 standard rooms on each floor, 35 m2/ room; The skirt room has a banquet hall of 1200m2 with a height of 9m. The construction unit shall organize the construction after winning the bid. The enterprise safety management department of the construction unit inspected the implementation of the enterprise safety production management system of the project, including: safety production education and training, safety production technology management, subcontractor safety production management, safety production inspection and improvement. After the completion of the self-inspection of the "full hall scaffold" construction in the banquet hall, the supervision engineer inspected it according to the guarantee items and general items required by the "Building Construction Safety Inspection Standard" JGJ59. The inspection items include: construction scheme, frame stability, bar lock, foot and hand plate, structure and accessories material and load. Before the concrete pouring of the banquet hall roof, the construction technicians disclosed the special safety plan to the operation team. In view of the concrete pouring process, there may be a variety of safety hazards, including improper pouring plan to make the support unbalanced, concentrated load, eccentric load and so on, and put forward preventive measures. | 18、混凝土浇筑过程的安全隐患主要表现形式还有哪些? | 18. What are the main manifestations of the safety hazards in the concrete pouring process?
CBQ-019 | 19、某工程项目经理部为贯彻落实《住房和城乡建设部等部门关于加快培育新时代建筑产业工人队伍的指导意见》（住建部等12部委2020年12月印发）要求，在项目劳动用工管理中做了以下工作： 要求分包单位与招用的建筑工人签订劳务合同； 总包对农民工工资支付工作负总责，要求分包单位做好农民工工资发放工作； 改善工人生活区居住环境，在集中生活区配套了食堂等必要生活机构设施开展物业化管理。 项目经理部编制的《屋面工程施工方案》中规定： 工程采用倒置式屋面，屋面构造层包括防水层、保温层、找平层、找坡层、隔离层、结构层和保护层。构造示意图见图1所示； 防水层选用三元乙丙高分子防水卷材； 防水层施工完成后进行雨后观察或淋水、蓄水试验，持续时间应符合规范要求。合格后再进行隔离层施工。 | 19. A project management department in order to implement the "Ministry of Housing and Urban-Rural Development and other departments on accelerating the cultivation of a new era of construction industry workers Guidance" (Ministry of Housing and other 12 ministries issued in December 2020) requirements, in the project labor management to do the following work: The subcontractor is required to sign a labor contract with the hired construction workers; The general contractor shall assume the overall responsibility for the wage payment of migrant workers, and require the subcontractor to do a good job in the wage payment of migrant workers; Improve the living environment of workers' living areas, and set up canteens and other necessary living facilities in centralized living areas to carry out materialistic management. The "Roof engineering construction Plan" prepared by the project management Department stipulates that the project adopts inverted roof, and the roof construction layer includes waterproof layer, thermal insulation layer, leveling layer, slope finding layer, isolation layer, structural layer and protective layer. The schematic diagram of structure is shown in Figure 1; Epdm polymer waterproof coil is selected for waterproof layer; Waterproof layer after the completion of the construction after the rain observation or shower, water storage test, the duration should meet the requirements of the code. The isolation layer shall be constructed after passing the test. | 19、指出项目劳动用工管理工作中不妥之处，并写出正确做法。 | 19. Point out the improper place in the project labor management, and write out the correct approach.
CBQ-020 | 20、某工程项目经理部为贯彻落实《住房和城乡建设部等部门关于加快培育新时代建筑产业工人队伍的指导意见》（住建部等12部委2020年12月印发）要求，在项目劳动用工管理中做了以下工作： 要求分包单位与招用的建筑工人签订劳务合同； 总包对农民工工资支付工作负总责，要求分包单位做好农民工工资发放工作； 改善工人生活区居住环境，在集中生活区配套了食堂等必要生活机构设施开展物业化管理。 项目经理部编制的《屋面工程施工方案》中规定： 工程采用倒置式屋面，屋面构造层包括防水层、保温层、找平层、找坡层、隔离层、结构层和保护层。构造示意图见图1所示； 防水层选用三元乙丙高分子防水卷材； 防水层施工完成后进行雨后观察或淋水、蓄水试验，持续时间应符合规范要求。合格后再进行隔离层施工。 | 20. A project management department in order to implement the "Ministry of Housing and Urban-Rural Development and other departments on accelerating the cultivation of a new era of construction industry workers Guidance" (Ministry of Housing and other 12 ministries issued in December 2020) requirements, in the project labor management to do the following work: The subcontractor is required to sign a labor contract with the hired construction workers; The general contractor shall assume the overall responsibility for the wage payment of migrant workers, and require the subcontractor to do a good job in the wage payment of migrant workers; Improve the living environment of workers' living areas, and set up canteens and other necessary living facilities in centralized living areas to carry out materialistic management. The "Roof engineering construction Plan" prepared by the project management Department stipulates that the project adopts inverted roof, and the roof construction layer includes waterproof layer, thermal insulation layer, leveling layer, slope finding layer, isolation layer, structural layer and protective layer. The schematic diagram of structure is shown in Figure 1; Epdm polymer waterproof coil is selected for waterproof layer; Waterproof layer after the completion of the construction after the rain observation or shower, water storage test, the duration should meet the requirements of the code. The isolation layer shall be constructed after passing the test. | 20、常用屋面隔离层材料有哪些？屋面防水层淋水、蓄水试验持续时间各是多少小时？ | 20. What are the commonly used roofing insulation materials? How many hours are the duration of the roof waterproof layer drenching and water storage test?
CBQ-021 | 21、某施工单位承建一高档住宅楼工程。钢筋混凝土剪力墙结构，地下2层，地上26层，建筑面积36000㎡，施工单位项目部根据该工程特点，编制了“施工期变形测量专项方案"，明确了建筑测量精度等级为一等，规定了两类变形测量基准点设置均不少于4个。首层楼板混凝土出现明显的塑态收缩现象，造成混凝土结构表面收缩裂缝。项目部质量专题会议分析其主要原因是骨料含泥量过大和水泥及掺合料的用量超出规范要求等，要求及时采取防治措施。 二次结构填充墙施工时，为抢工期，项目工程部门安排作业人员将刚生产7天的蒸压加气混凝土砌块用于砌筑作业要求砌体灰缝厚度、饱满度等质量满足要求。后被监理工程师发现，责令停工整改。 项目经理巡查到二层样板间时，地面瓷砖铺设施工人员正按照基层处理、放线、浸砖等工艺流程进行施工。 其检查了施工质量，强调后续工作要严格按照正确施工工艺作业，铺装完成28d后，用专用勾缝剂勾缝，做到清晰、顺直，保证地面整体质量。 | 21. A construction unit undertakes the construction of a high-grade residential building project. Reinforced concrete shear wall structure, 2 underground floors, 26 floors on the ground, construction area of 36000 square meters, construction unit project department according to the characteristics of the project, the preparation of the "construction period deformation measurement special plan", clear the construction measurement accuracy level for the first class, the two types of deformation measurement base point set are not less than 4. The first floor concrete appears obvious plastic shrinkage phenomenon, resulting in shrinkage cracks on the surface of the concrete structure. The quality conference of the project department analyzed the main reason is that the mud content of the aggregate is too large and the amount of cement and admixture exceeds the standard requirements, requiring timely prevention and control measures. During the construction of the secondary structure filling wall, in order to rush the construction period, the project engineering department arranged the operators to use the autoclaved aerated concrete blocks that have just been produced for 7 days to meet the requirements of the masonry ash joint thickness, fullness and other qualities. After being discovered by the supervising engineer, they were ordered to stop work for rectification. When the project manager inspected the second-floor model room, the floor tile laying construction personnel were carrying out construction in accordance with the basic treatment, pay-off, brick dipping and other technological processes. It checked the construction quality, emphasizing that the follow-up work should be in strict accordance with the correct construction process, and after the completion of 28d of paving, the joint should be pointed with special pointing agent to make it clear and straight, and ensure the overall quality of the ground. | 21、除塑态收缩外，还有哪些收缩现象易引起泥凝土表面收缩裂缝？收缩裂缝产生的原因还有哪些？ | 21. In addition to the plastic shrinkage, what shrinkage phenomena are easy to cause the clay surface shrinkage cracks? What are the other causes of shrinkage cracks?
CBQ-022 | 22、某施工单位承建一高档住宅楼工程。钢筋混凝土剪力墙结构，地下2层，地上26层，建筑面积36000㎡，施工单位项目部根据该工程特点，编制了“施工期变形测量专项方案"，明确了建筑测量精度等级为一等，规定了两类变形测量基准点设置均不少于4个。首层楼板混凝土出现明显的塑态收缩现象，造成混凝土结构表面收缩裂缝。项目部质量专题会议分析其主要原因是骨料含泥量过大和水泥及掺合料的用量超出规范要求等，要求及时采取防治措施。 二次结构填充墙施工时，为抢工期，项目工程部门安排作业人员将刚生产7天的蒸压加气混凝土砌块用于砌筑作业要求砌体灰缝厚度、饱满度等质量满足要求。后被监理工程师发现，责令停工整改。 项目经理巡查到二层样板间时，地面瓷砖铺设施工人员正按照基层处理、放线、浸砖等工艺流程进行施工。 其检查了施工质量，强调后续工作要严格按照正确施工工艺作业，铺装完成28d后，用专用勾缝剂勾缝，做到清晰、顺直，保证地面整体质量。 | 22. A construction unit undertakes the construction of a high-grade residential building project. Reinforced concrete shear wall structure, 2 underground floors, 26 floors on the ground, construction area of 36000 square meters, construction unit project department according to the characteristics of the project, the preparation of the "construction period deformation measurement special plan", clear the construction measurement accuracy level for the first class, the two types of deformation measurement base point set are not less than 4. The first floor concrete appears obvious plastic shrinkage phenomenon, resulting in shrinkage cracks on the surface of the concrete structure. The quality conference of the project department analyzed the main reason is that the mud content of the aggregate is too large and the amount of cement and admixture exceeds the standard requirements, requiring timely prevention and control measures. During the construction of the secondary structure filling wall, in order to rush the construction period, the project engineering department arranged the operators to use the autoclaved aerated concrete blocks that have just been produced for 7 days to meet the requirements of the masonry ash joint thickness, fullness and other qualities. After being discovered by the supervising engineer, they were ordered to stop work for rectification. When the project manager inspected the second-floor model room, the floor tile laying construction personnel were carrying out construction in accordance with the basic treatment, pay-off, brick dipping and other technological processes. It checked the construction quality, emphasizing that the follow-up work should be in strict accordance with the correct construction process, and after the completion of 28d of paving, the joint should be pointed with special pointing agent to make it clear and straight, and ensure the overall quality of the ground. | 22、地面瓷砖面层施工工艺内容还有哪些？瓷砖勾缝要求还有哪些？ | 22. What are the construction process contents of the ground tile surface? What are the requirements for tile pointing?
CBQ-023 | 23、某工程项目，地上15-18层，地下2层，钢筋混凝土剪力墙结构，总建筑面积57000㎡，施工单位中标后成立项目经理部组织施工。项目经理部计划施工组织方式采用流水施工，根据劳动力储备和工程结构特点确定流水施工的工艺参数、时间参数和空间参数，如空间参数中的施工段、施工层划分等，合理配置组织和资源。 主体结构完成后，项目部为结构验收做了以下准备工作； 将所有模板拆除并清理干净； 工程技术资料整理、整改完成； 完成了合同图纸和洽商所有内容； 各类管道预埋完成，位置尺寸准确，相应测试完成； 各类整改通知已完成，并形成整改报告。 项目部认为达到了验收条件，向监理单位申请组织结构验收，并决定由项目技术负责人、相关部门经理和工长参加。监理工程师认为存在验收条件不具备、参与验收人员不全等问题，要求完善验收条件。 | 23. A project, the ground 15-18 layers, underground 2 layers, reinforced concrete shear wall structure, a total construction area of 57000 square meters, the construction unit after winning the bid to set up the project management department to organize construction. The project management department plans to use flow construction organization, according to labor reserves and engineering structure characteristics to determine the flow construction process parameters, time parameters and spatial parameters, such as space parameters in the construction section, construction layer division, reasonable allocation of organization and resources. After the completion of the main structure, the project department made the following preparations for the acceptance of the structure; All templates were removed and cleaned; Finishing and rectification of engineering and technical data; Completed the contract drawing and negotiation of all content; All kinds of pipelines have been pre-buried, the position and size are accurate, and the corresponding tests have been completed; All kinds of rectification notices have been completed, and rectification reports have been formed. The project department thinks that the acceptance conditions have been met, and applies to the supervision unit for the acceptance of the organizational structure, and decides that the project technical leader, the manager of the relevant department and the foreman will participate. The supervision engineer believes that there are problems such as lack of acceptance conditions and incomplete personnel participating in acceptance, and requires improvement of acceptance conditions. | 23、工程施工组织方式还有哪些？组织流水施工时，应考虑的工艺参数和时间参数分别包括哪些内容？ | 23. What are the other ways of engineering construction organization? What are the process parameters and time parameters that should be considered when organizing flow construction?
CBQ-024 | 24、某工程项目，地上15-18层，地下2层，钢筋混凝土剪力墙结构，总建筑面积57000㎡，施工单位中标后成立项目经理部组织施工。项目经理部计划施工组织方式采用流水施工，根据劳动力储备和工程结构特点确定流水施工的工艺参数、时间参数和空间参数，如空间参数中的施工段、施工层划分等，合理配置组织和资源。 主体结构完成后，项目部为结构验收做了以下准备工作； 将所有模板拆除并清理干净； 工程技术资料整理、整改完成； 完成了合同图纸和洽商所有内容； 各类管道预埋完成，位置尺寸准确，相应测试完成； 各类整改通知已完成，并形成整改报告。 项目部认为达到了验收条件，向监理单位申请组织结构验收，并决定由项目技术负责人、相关部门经理和工长参加。监理工程师认为存在验收条件不具备、参与验收人员不全等问题，要求完善验收条件。 | 24. A project, the ground 15-18 layers, underground 2 layers, reinforced concrete shear wall structure, a total construction area of 57000 square meters, the construction unit after winning the bid to set up the project management department to organize construction. The project management department plans to use flow construction organization, according to labor reserves and engineering structure characteristics to determine the flow construction process parameters, time parameters and spatial parameters, such as space parameters in the construction section, construction layer division, reasonable allocation of organization and resources. After the completion of the main structure, the project department made the following preparations for the acceptance of the structure; All templates were removed and cleaned; Finishing and rectification of engineering and technical data; Completed the contract drawing and negotiation of all content; All kinds of pipelines have been pre-buried, the position and size are accurate, and the corresponding tests have been completed; All kinds of rectification notices have been completed, and rectification reports have been formed. The project department thinks that the acceptance conditions have been met, and applies to the supervision unit for the acceptance of the organizational structure, and decides that the project technical leader, the manager of the relevant department and the foreman will participate. The supervision engineer believes that there are problems such as lack of acceptance conditions and incomplete personnel participating in acceptance, and requires improvement of acceptance conditions. | 24、主体结构验收工程实体还应具备哪些条件？施工单位应参与结构验收的人员还有哪些？ | 24. What conditions should the main structure acceptance engineering entity have? What other personnel should the construction unit participate in the structure acceptance?
CBQ-025 | 25、某新建住宅楼工程，建筑面积25000㎡，装配式钢筋混凝土结构。建设单位编制了招标工程量清单等招标文件，其中部分条款内容为：本工程实行施工总承包模式，承包范围为土建、电气等全部工程内容，质量标准为合格，开工前业主向承包商支付合同工程造价的25%作为预付备料款；保修金为总价的3%。 经公开招投标，某施工总承包单位以12500万元中标。其中：工地总成本9200万元，公司管理费按10%计，利润按5%计，暂列金额1000万元。主要材料及构配件金额占合同额70%。双方签订了工程施工总承包合同。 项目经理部按照包括统一管理、资金集中等内容的资金管理原则，编制年、季、月度资金收支计划，认真做好项目资金管理工作。施工单位按照建设单位要求，通过专家论证，采用了一种新型预制钢筋混凝土剪力墙结构体系，致使实际工地总成本增加到9500万元。施工单位在工程结算时，对增加费用进行了索赔。 项目经理部按照优先选择单位工程量使用成本费用（包括可变费用和固定费用，如大修理费、小修理费等）较低的原则，施工塔吊供应渠道选择企业自有设备调配。 项目检验试验由建设单位委托具有资质的检测机构负责，施工单位支付了相关费用，并向建设单位提出以下索赔事项： 现场自建试验室费用超预算费用3.5万； 新型钢筋混凝土预制剪力墙结构验证试验费25万元； 新型钢筋混凝土剪力墙预制构件抽样检测费用12万元； 预制钢筋混凝土剪力墙板破坏性试验费用8万元； 施工企业采购的钢筋连接套筒抽检不合格而增加的检测费用1.5万元。 | 25. A new residential building project, construction area of 25,000 square meters, prefabricated reinforced concrete structure. The construction unit has prepared the bidding project quantity list and other bidding documents, some of which are as follows: the project carries out the construction general contracting mode, the scope of contracting is civil, electrical and other all engineering content, the quality standard is qualified, the owner pays 25% of the contract project cost to the contractor before the start as the prepayment for materials; The warranty fee is 3% of the total price. After public bidding, a construction contractor won the bid with 125 million yuan. Among them: the total cost of the site is 92 million yuan, the company's management fee is calculated by 10%, the profit is calculated by 5%, and the provisional amount is 10 million yuan. The main materials and construction parts account for 70% of the contract amount. The two parties signed the general contract for the construction of the project. The project management department shall, in accordance with the principles of fund management including unified management and centralization of funds, formulate annual, quarterly and monthly fund revenue and expenditure plans, and conscientiously manage the project fund. According to the requirements of the construction unit, the construction unit adopted a new type of precast reinforced concrete shear wall structure system through expert demonstration, resulting in the actual total site cost increased to 95 million yuan. At the time of project settlement, the construction unit made a claim for the increased cost. Project management Department in accordance with the principle of giving priority to the use of cost costs per unit of project volume (including variable costs and fixed costs, such as large repair costs, small repair costs, etc.) lower, construction tower crane supply channels choose enterprise own equipment deployment. The project inspection and test is entrusted by the construction unit with a qualified testing institution to be responsible for the construction unit to pay the relevant costs, and to the construction unit to lodge the following claims: the on-site self-built laboratory cost exceeds the budget cost of 35,000; The new reinforced concrete prefabricated shear wall structure verification test fee of 250,000 yuan; The sampling and testing cost of new reinforced concrete shear wall precast members is 120,000 yuan; The destructive test cost of precast reinforced concrete shear wall panel is 80,000 yuan; The increased testing cost of 15,000 yuan due to the unqualified sampling of the steel bar connection sleeve purchased by the construction enterprise. | 25、施工总承包通常还包括哪些工程内容？（如土建、电气） | 25. What other engineering contents are usually included in the general construction contract? (e.g. civil engineering, electrical)
CBQ-026 | 26、某新建住宅楼工程，建筑面积25000㎡，装配式钢筋混凝土结构。建设单位编制了招标工程量清单等招标文件，其中部分条款内容为：本工程实行施工总承包模式，承包范围为土建、电气等全部工程内容，质量标准为合格，开工前业主向承包商支付合同工程造价的25%作为预付备料款；保修金为总价的3%。 经公开招投标，某施工总承包单位以12500万元中标。其中：工地总成本9200万元，公司管理费按10%计，利润按5%计，暂列金额1000万元。主要材料及构配件金额占合同额70%。双方签订了工程施工总承包合同。 项目经理部按照包括统一管理、资金集中等内容的资金管理原则，编制年、季、月度资金收支计划，认真做好项目资金管理工作。施工单位按照建设单位要求，通过专家论证，采用了一种新型预制钢筋混凝土剪力墙结构体系，致使实际工地总成本增加到9500万元。施工单位在工程结算时，对增加费用进行了索赔。 项目经理部按照优先选择单位工程量使用成本费用（包括可变费用和固定费用，如大修理费、小修理费等）较低的原则，施工塔吊供应渠道选择企业自有设备调配。 项目检验试验由建设单位委托具有资质的检测机构负责，施工单位支付了相关费用，并向建设单位提出以下索赔事项： 现场自建试验室费用超预算费用3.5万； 新型钢筋混凝土预制剪力墙结构验证试验费25万元； 新型钢筋混凝土剪力墙预制构件抽样检测费用12万元； 预制钢筋混凝土剪力墙板破坏性试验费用8万元； 施工企业采购的钢筋连接套筒抽检不合格而增加的检测费用1.5万元。 | 26. A new residential building project, construction area of 25,000 square meters, prefabricated reinforced concrete structure. The construction unit has prepared the bidding project quantity list and other bidding documents, some of which are as follows: the project carries out the construction general contracting mode, the scope of contracting is civil, electrical and other all engineering content, the quality standard is qualified, the owner pays 25% of the contract project cost to the contractor before the start as the prepayment for materials; The warranty fee is 3% of the total price. After public bidding, a construction contractor won the bid with 125 million yuan. Among them: the total cost of the site is 92 million yuan, the company's management fee is calculated by 10%, the profit is calculated by 5%, and the provisional amount is 10 million yuan. The main materials and construction parts account for 70% of the contract amount. The two parties signed the general contract for the construction of the project. The project management department shall, in accordance with the principles of fund management including unified management and centralization of funds, formulate annual, quarterly and monthly fund revenue and expenditure plans, and conscientiously manage the project fund. According to the requirements of the construction unit, the construction unit adopted a new type of precast reinforced concrete shear wall structure system through expert demonstration, resulting in the actual total site cost increased to 95 million yuan. At the time of project settlement, the construction unit made a claim for the increased cost. Project management Department in accordance with the principle of giving priority to the use of cost costs per unit of project volume (including variable costs and fixed costs, such as large repair costs, small repair costs, etc.) lower, construction tower crane supply channels choose enterprise own equipment deployment. The project inspection and test is entrusted by the construction unit with a qualified testing institution to be responsible for the construction unit to pay the relevant costs, and to the construction unit to lodge the following claims: the on-site self-built laboratory cost exceeds the budget cost of 35,000; The new reinforced concrete prefabricated shear wall structure verification test fee of 250,000 yuan; The sampling and testing cost of new reinforced concrete shear wall precast members is 120,000 yuan; The destructive test cost of precast reinforced concrete shear wall panel is 80,000 yuan; The increased testing cost of 15,000 yuan due to the unqualified sampling of the steel bar connection sleeve purchased by the construction enterprise. | 26、分别判断检测试验索赔事项的各项费用是否成立？（如1万元成立） | 26. Determine whether the costs of the test claim items are established respectively? (if 10,000 yuan is established)
CBQ-027 | 27、某住宅工程由7栋单体组成，地下2层，地上10-13层，总建筑面积11.5万㎡。施工总承包单位中标后成立项目经理部组织施工。 项目总工程师编制了《临时用电组织设计》，其内容包括：总配电箱设在用电设备相对集中的区域；电缆直接埋地敷设穿过临建设施时应设置警示标识进行保护；临时用电施工完成后，由编制和使用单位共同验收合格后方可使用；各类用电人员经考试合格后持证上岗工作；发现用电安全隐患，经电工排除后继续使用；维修临时用电设备由电工独立完成；临时用电定期检查按分部、分项工程进行。《临时用电组织设计》报企业技术部批准后，上报监理单位。监理工程师认为《临时用电组织设计》存在不妥之处，要求修改完善后再报。项目经理部结合各级政府新冠肺炎疫情防控工作政策，制定了《绿色施工专项方案》。监理工程师审查时指出不妥之处： 生产经理是绿色施工组织实施第一责任人； 施工工地内的生活区实施封闭管理； 实行每日核酸检测； 现场生活区采取灭鼠、灭蚊、灭蝇等措施，不定期投放和喷洒灭虫、消毒药物。 同时要求补充发现施工人员患有法定传染病时，施工单位采取的应对措施。 | 27. A residential project consists of 7 monomer, underground 2 layers, ground 10-13 layers, a total construction area of 115,000 square meters. After winning the bid, the general contractor will set up the project management department to organize the construction. The chief engineer of the project prepared the Temporary Power Consumption Organization Design, which includes: the main distribution box is located in the area where the power equipment is relatively concentrated; When the cable is directly buried and laid through the temporary construction facilities, warning signs should be set for protection; After the construction of temporary electricity use is completed, it can be used only after the preparation and use units have passed the acceptance check; After passing the examination, all kinds of power users shall hold the certificate to work; Found the hidden danger of electricity safety, after the electrician ruled out continue to use; Maintenance of temporary electrical equipment shall be completed independently by electricians; Periodic inspection of temporary power consumption shall be carried out by branch and item projects. Temporary power Usage Organization Design shall be submitted to the technical Department of the enterprise for approval and shall be submitted to the supervision unit. The supervising engineer thinks that there is some inadequateness in the Organization Design of Temporary Electricity Use, and requests to revise and improve it before submitting it. The project Management Department formulated the "Special Plan for Green Construction" based on the policies of governments at all levels for the prevention and control of the novel coronavirus epidemic. The supervision engineer pointed out the inadequacies in the review: the production manager is the first person responsible for organizing the implementation of green construction; The living area in the construction site shall be closed; Daily nucleic acid testing; Rodent, mosquito and fly control measures shall be taken in on-site living areas, and insecticidal and disinfection drugs shall be injected and sprayed from time to time. At the same time, it is required to supplement the countermeasures taken by the construction unit when the construction personnel is found to be suffering from statutory infectious diseases. | 27、写出《临时用电组织设计》内容与管理中不妥之处的正确做法。 | 27. Write out the correct way of the improper content and management of "Temporary electricity organization Design".
CBQ-028 | 28、某住宅工程由7栋单体组成，地下2层，地上10-13层，总建筑面积11.5万㎡。施工总承包单位中标后成立项目经理部组织施工。 项目总工程师编制了《临时用电组织设计》，其内容包括：总配电箱设在用电设备相对集中的区域；电缆直接埋地敷设穿过临建设施时应设置警示标识进行保护；临时用电施工完成后，由编制和使用单位共同验收合格后方可使用；各类用电人员经考试合格后持证上岗工作；发现用电安全隐患，经电工排除后继续使用；维修临时用电设备由电工独立完成；临时用电定期检查按分部、分项工程进行。《临时用电组织设计》报企业技术部批准后，上报监理单位。监理工程师认为《临时用电组织设计》存在不妥之处，要求修改完善后再报。项目经理部结合各级政府新冠肺炎疫情防控工作政策，制定了《绿色施工专项方案》。监理工程师审查时指出不妥之处： 生产经理是绿色施工组织实施第一责任人； 施工工地内的生活区实施封闭管理； 实行每日核酸检测； 现场生活区采取灭鼠、灭蚊、灭蝇等措施，不定期投放和喷洒灭虫、消毒药物。 同时要求补充发现施工人员患有法定传染病时，施工单位采取的应对措施。 | 28. A residential project consists of 7 monomer, underground 2 layers, ground 10-13 layers, a total construction area of 115,000 square meters. After winning the bid, the general contractor will set up the project management department to organize the construction. The chief engineer of the project prepared the Temporary Power Consumption Organization Design, which includes: the main distribution box is located in the area where the power equipment is relatively concentrated; When the cable is directly buried and laid through the temporary construction facilities, warning signs should be set for protection; After the construction of temporary electricity use is completed, it can be used only after the preparation and use units have passed the acceptance check; After passing the examination, all kinds of power users shall hold the certificate to work; Found the hidden danger of electricity safety, after the electrician ruled out continue to use; Maintenance of temporary electrical equipment shall be completed independently by electricians; Periodic inspection of temporary power consumption shall be carried out by branch and item projects. Temporary power Usage Organization Design shall be submitted to the technical Department of the enterprise for approval and shall be submitted to the supervision unit. The supervising engineer thinks that there is some inadequateness in the Organization Design of Temporary Electricity Use, and requests to revise and improve it before submitting it. The project Management Department formulated the "Special Plan for Green Construction" based on the policies of governments at all levels for the prevention and control of the novel coronavirus epidemic. The supervision engineer pointed out the inadequacies in the review: the production manager is the first person responsible for organizing the implementation of green construction; The living area in the construction site shall be closed; Daily nucleic acid testing; Rodent, mosquito and fly control measures shall be taken in on-site living areas, and insecticidal and disinfection drugs shall be injected and sprayed from time to time. At the same time, it is required to supplement the countermeasures taken by the construction unit when the construction personnel is found to be suffering from statutory infectious diseases. | 28、写出《绿色施工专项方案》中不妥之处的正确做法。施工人员患有法定传染病时病时，施工单位应对措施有哪些？ | 28. Write out the correct practice of the improper place in the "Special Plan for Green Construction". What are the measures taken by the construction unit when the construction personnel is sick from notifiable infectious diseases?
CBQ-029 | 29、招标文件中内容“投标人为本省一级资质证书的企业，投标保证金500.00万，工程质量为合格”，投标有效期从3 月1日到4月15日。招标人对投标人提出的疑问，以书面形式回复对应的投标人。5 月17 日与中标人以1.7亿的中标价签订合同，约定工程质量为优良。政府主管部门检查《建设工程质量检测管理办法》(住房和城乡建设部第7号令)执行情况：施工单位委托了监理单位控股的具有检测资质的检测机构负责工程的质量检测工作，建设单位按照合同采用一批钢材时，要求钢材供应商在总承包单位材料人员见证下，从其货场对该批钢材取样送检，检测合格后送到施工现场使用。要求相关单位对存在的问题进行整改。 施工单位没有隐蔽验收直接施工，监理要求验收。 静压力桩，“先深后浅，先大后小，先长后短，先密后疏”。使用抱箍式方法接桩，接头高出地面0.8m。存在部分二类桩。 | 29. In the bidding documents, "the bidder is an enterprise with a provincial-level qualification certificate, the bid deposit is 500.00 million yuan, and the project quality is qualified", and the bid is valid from March 1 to April 15. The tenderer shall reply the corresponding bidder in written form to any question raised by the bidder. On May 17, the contract was signed with the winning bidder at the winning price of 170 million, and the quality of the project was agreed to be excellent. The competent government department inspects the implementation of the "Measures for the Administration of Quality Inspection of Construction Projects" (Order No. 7 of the Ministry of Housing and Urban-Rural Development) : The construction unit entrusts the supervision unit to hold a testing institution with testing qualifications to be responsible for the quality testing of the project. When the construction unit adopts a batch of steel in accordance with the contract, it requires the steel supplier to sample the batch of steel from its yard and send it for inspection under the witness of the material personnel of the general contractor, and send it to the construction site for use after passing the test. The relevant units are required to rectify the existing problems. The construction unit does not carry out concealed acceptance directly, and the supervision requires acceptance. Static pressure pile, "first deep after shallow, first big after small, first long after short, first dense after sparse". Use the hoop method to connect the pile, and the joint is 0.8m higher than the ground. There are some second class piles. | 29、招投标过程中的不妥之处？ | 29. What is wrong in the bidding process?
CBQ-030 | 30、招标文件中内容“投标人为本省一级资质证书的企业，投标保证金500.00万，工程质量为合格”，投标有效期从3 月1日到4月15日。招标人对投标人提出的疑问，以书面形式回复对应的投标人。5 月17 日与中标人以1.7亿的中标价签订合同，约定工程质量为优良。政府主管部门检查《建设工程质量检测管理办法》(住房和城乡建设部第7号令)执行情况：施工单位委托了监理单位控股的具有检测资质的检测机构负责工程的质量检测工作，建设单位按照合同采用一批钢材时，要求钢材供应商在总承包单位材料人员见证下，从其货场对该批钢材取样送检，检测合格后送到施工现场使用。要求相关单位对存在的问题进行整改。 施工单位没有隐蔽验收直接施工，监理要求验收。 静压力桩，“先深后浅，先大后小，先长后短，先密后疏”。使用抱箍式方法接桩，接头高出地面0.8m。存在部分二类桩。 | 30. In the bidding documents, "the bidder is an enterprise with a provincial-level qualification certificate, the bid deposit is 500.00 million yuan, and the project quality is qualified", and the bid is valid from March 1 to April 15. The tenderer shall reply the corresponding bidder in written form to any question raised by the bidder. On May 17, the contract was signed with the winning bidder at the winning price of 170 million, and the quality of the project was agreed to be excellent. The competent government department inspects the implementation of the "Measures for the Administration of Quality Inspection of Construction Projects" (Order No. 7 of the Ministry of Housing and Urban-Rural Development) : The construction unit entrusts the supervision unit to hold a testing institution with testing qualifications to be responsible for the quality testing of the project. When the construction unit adopts a batch of steel in accordance with the contract, it requires the steel supplier to sample the batch of steel from its yard and send it for inspection under the witness of the material personnel of the general contractor, and send it to the construction site for use after passing the test. The relevant units are required to rectify the existing problems. The construction unit does not carry out concealed acceptance directly, and the supervision requires acceptance. Static pressure pile, "first deep after shallow, first big after small, first long after short, first dense after sparse". Use the hoop method to connect the pile, and the joint is 0.8m higher than the ground. There are some second class piles. | 30、指出《建设工程质量检测管理办法》执行中的不妥之处，并写出正确理由。 | 30. Point out the inadequacies in the implementation of the Measures for the Management of Quality Inspection of Construction Projects, and write out the correct reasons.
CBQ-031 | 31、某建筑地下2层，地上18层。框架结构。地下建筑面积0.4万㎡，地上建筑面积2.1万㎡，某施工单位中标后派赵佑项目经理组织施工，施工至5层时，公司安全部叶军带队对项目进行了定期安全检查。公司安全部门在年初的安全检查规划中按照相关要求明确了对项目安全检查的主要形式，包括定期安全检查开工，复工安全检查，季节性安全检查等。确保项目施工过程中全覆盖，进入夏季后，公司项目管理部对该项目工人宿舍和食堂进行了检查。个别宿舍内床铺均为2层，住有18人，设置有生活用品专用柜，窗户为封闭式窗户，人进入通道宽度为0.8米，食堂办理了卫生许可证成绩单，炊事人员均有健康证，上岗符合个人卫生相关规定。检查后项目管理部对工人宿舍的不足提出了整改要求，并限期达标。 | 31. A building has 2 floors underground and 18 floors above ground. Frame structure. Underground construction area of 0.4 thousand square meters, the ground construction area of 21,000 square meters, a construction unit after the bid sent Zhao You project manager to organize the construction, construction to the 5th floor, the company security department Ye Jun led the team to carry out regular safety inspection of the project. The company's security department at the beginning of the year in the safety inspection planning in accordance with the relevant requirements of the project safety inspection of the main forms, including regular safety inspection start, return to work safety inspection, seasonal safety inspection and so on. To ensure that the project construction process is fully covered, after entering the summer, the company's project management department inspected the project workers' dormitories and canteens. Individual dormitory beds are 2 floors, living 18 people, set up a special cabinet of daily necessities, the Windows are closed Windows, the width of people entering the passage is 0.8 meters, the canteen has a health license report card, the cook has a health certificate, work in line with the relevant regulations of personal hygiene. After the inspection, the project management department put forward rectification requirements for the deficiencies of the workers' dormitories, and set a deadline to meet the standards. | 31、建筑工程施工安全检查还有哪些形式？ | 31. What are the other forms of construction safety inspection of construction projects?
CBQ-032 | 32、某建筑地下2层，地上18层。框架结构。地下建筑面积0.4万㎡，地上建筑面积2.1万㎡，某施工单位中标后派赵佑项目经理组织施工，施工至5层时，公司安全部叶军带队对项目进行了定期安全检查。公司安全部门在年初的安全检查规划中按照相关要求明确了对项目安全检查的主要形式，包括定期安全检查开工，复工安全检查，季节性安全检查等。确保项目施工过程中全覆盖，进入夏季后，公司项目管理部对该项目工人宿舍和食堂进行了检查。个别宿舍内床铺均为2层，住有18人，设置有生活用品专用柜，窗户为封闭式窗户，人进入通道宽度为0.8米，食堂办理了卫生许可证成绩单，炊事人员均有健康证，上岗符合个人卫生相关规定。检查后项目管理部对工人宿舍的不足提出了整改要求，并限期达标。 | 32. A building has 2 floors underground and 18 floors above ground. Frame structure. Underground construction area of 0.4 thousand square meters, the ground construction area of 21,000 square meters, a construction unit after the bid sent Zhao You project manager to organize the construction, construction to the 5th floor, the company security department Ye Jun led the team to carry out regular safety inspection of the project. The company's security department at the beginning of the year in the safety inspection planning in accordance with the relevant requirements of the project safety inspection of the main forms, including regular safety inspection start, return to work safety inspection, seasonal safety inspection and so on. To ensure that the project construction process is fully covered, after entering the summer, the company's project management department inspected the project workers' dormitories and canteens. Individual dormitory beds are 2 floors, living 18 people, set up a special cabinet of daily necessities, the Windows are closed Windows, the width of people entering the passage is 0.8 meters, the canteen has a health license report card, the cook has a health certificate, work in line with the relevant regulations of personal hygiene. After the inspection, the project management department put forward rectification requirements for the deficiencies of the workers' dormitories, and set a deadline to meet the standards. | 32、指出工人宿舍管理的不妥之处并改正。在炊事员上岗期间，从个人卫生角度还有哪些具体管理？ | 32. Point out the inadequacies in the management of workers' dormitories and correct them. 3. What other specific management are there from the point of view of personal hygiene during the cook's tenure?
CBQ-033 | 33、某新建住宅工程，建筑面积22000m2，地下一层，地上十六层，框架-剪力墙结构，抗震设防烈度7度。施工单位项目部在施工前，由项目技术负责人组织编写了项目质量计划书，报请施工单位质量管理部门审批后实施。质量计划要求项目部施工过程中建立包括使用机具和设备管理记录图纸、设计变更收发记录，检查和整改复查记录，质量管理文件及其他记录等质量管理记录制度。240mm厚灰砂砖填充墙与主体结构连接施工的要求有：填充墙与柱连接钢筋为2φ6@600，伸入墙内500mm；填充墙与结构梁下最后三皮砖空隙部位，在墙体砌筑7d后，采取两边对称斜砌填实；化学植筋连接筋φ6做拉拔试验时，将轴向受拉非破坏承载力检验值设为5.0KN，持荷时间2min，期间各检测结果符合相关要求，即判定该试样合格。屋面防水层选用2mm厚的改性沥青防水卷材，铺贴顺序和方向按照平行于屋脊、上下层不得相互垂直等要求，采用热粘法施工。项目部在对卫生间装修工程电气分部工程进行专项检查时发现，施工人员将卫生间内安装的金属管道、浴缸、沐浴器、暖气片等导体与等电位端子进行了连接，局部等电位联接排与各连接点使用截面积2.5mm²黄色标单根铜芯导线进行串联连接。对此，监理工程师提出了整改要求。 | 33. A new residential project, construction area of 22000m2, one underground floor, 16 floors on the ground, frame-shear wall structure, seismic fortification intensity 7 degrees. Before construction, the project department of the construction unit shall organize and prepare the project quality plan by the project technical person in charge, and submit it to the quality management department of the construction unit for approval and implementation. The quality plan requires the project department to establish a quality management record system in the construction process, including the use of tools and equipment management record drawings, design change receipt and delivery records, inspection and rectification review records, quality management documents and other records. The requirements for the construction of the connection between the 240mm thick gray sand brick wall and the main structure are as follows: the steel bar connecting the filling wall and the column is 2φ6@600, extending into the wall 500mm; Fill the space of the last three leather bricks under the wall and the structural beam, after 7d of wall masonry, both sides of the symmetrical diagonal building is taken to fill; When the chemical planting reinforcement is connected to φ6 for drawing test, the test value of the axial tensile non-destructive bearing capacity is set to 5.0KN, the load holding time is 2min, during which the test results meet the relevant requirements, that is, the sample is judged to be qualified. The waterproof layer of the roof is made of 2mm thick modified asphalt waterproof coil. The laying sequence and direction are parallel to the roof ridge, and the upper and lower layers are not perpendicular to each other. The hot bonding method is adopted for construction. When the project department carried out a special inspection on the electrical branch of the bathroom decoration project, it was found that the construction personnel connected the metal pipes, bathtubs, bathtubs, radiators and other conductors installed in the bathroom with equal potential terminals, and the local equal potential connection row and each connection point were connected in series with a cross-sectional area of 2.5mm² yellow standard single copper core wire. In this regard, the supervising engineer put forward the rectification requirements. | 33、指出项目质量计划书编、审、批和确认手续的不妥之处。质量计划应用中，施工单位应建立的质量管理记录还有哪些？ | 33. Point out the inadequacies of project quality plan preparation, review, approval and confirmation procedures. In the application of quality plan, what other quality management records should be established by the construction unit?
CBQ-034 | 34、某新建住宅工程，建筑面积22000m2，地下一层，地上十六层，框架-剪力墙结构，抗震设防烈度7度。施工单位项目部在施工前，由项目技术负责人组织编写了项目质量计划书，报请施工单位质量管理部门审批后实施。质量计划要求项目部施工过程中建立包括使用机具和设备管理记录图纸、设计变更收发记录，检查和整改复查记录，质量管理文件及其他记录等质量管理记录制度。240mm厚灰砂砖填充墙与主体结构连接施工的要求有：填充墙与柱连接钢筋为2φ6@600，伸入墙内500mm；填充墙与结构梁下最后三皮砖空隙部位，在墙体砌筑7d后，采取两边对称斜砌填实；化学植筋连接筋φ6做拉拔试验时，将轴向受拉非破坏承载力检验值设为5.0KN，持荷时间2min，期间各检测结果符合相关要求，即判定该试样合格。屋面防水层选用2mm厚的改性沥青防水卷材，铺贴顺序和方向按照平行于屋脊、上下层不得相互垂直等要求，采用热粘法施工。项目部在对卫生间装修工程电气分部工程进行专项检查时发现，施工人员将卫生间内安装的金属管道、浴缸、沐浴器、暖气片等导体与等电位端子进行了连接，局部等电位联接排与各连接点使用截面积2.5mm²黄色标单根铜芯导线进行串联连接。对此，监理工程师提出了整改要求。 | 34. A new residential project, construction area of 22000m2, one underground floor, 16 floors on the ground, frame-shear wall structure, seismic fortification intensity 7 degrees. Before construction, the project department of the construction unit shall organize and prepare the project quality plan by the project technical person in charge, and submit it to the quality management department of the construction unit for approval and implementation. The quality plan requires the project department to establish a quality management record system in the construction process, including the use of tools and equipment management record drawings, design change receipt and delivery records, inspection and rectification review records, quality management documents and other records. The requirements for the construction of the connection between the 240mm thick gray sand brick wall and the main structure are as follows: the steel bar connecting the filling wall and the column is 2φ6@600, extending into the wall 500mm; Fill the space of the last three leather bricks under the wall and the structural beam, after 7d of wall masonry, both sides of the symmetrical diagonal building is taken to fill; When the chemical planting reinforcement is connected to φ6 for drawing test, the test value of the axial tensile non-destructive bearing capacity is set to 5.0KN, the load holding time is 2min, during which the test results meet the relevant requirements, that is, the sample is judged to be qualified. The waterproof layer of the roof is made of 2mm thick modified asphalt waterproof coil. The laying sequence and direction are parallel to the roof ridge, and the upper and lower layers are not perpendicular to each other. The hot bonding method is adopted for construction. When the project department carried out a special inspection on the electrical branch of the bathroom decoration project, it was found that the construction personnel connected the metal pipes, bathtubs, bathtubs, radiators and other conductors installed in the bathroom with equal potential terminals, and the local equal potential connection row and each connection point were connected in series with a cross-sectional area of 2.5mm² yellow standard single copper core wire. In this regard, the supervising engineer put forward the rectification requirements. | 34、改正卫生间等电位连接中的错误做法。 | 34. Correct the wrong practice in the bathroom equipotential connection.
CBQ-035 | 35、某施工单位通过竞标承建一工程项目，甲乙双方通过协商，对工程合同协议书（编号HT-XY-201909001），以及专用合同条款（编号HT-ZY-201909001）和通用合同条款（编号HT-TY-201909001）修改意见达成一致，签订了施工合同。确认包括投标函、中标通知书等合同文件按照《建设工程施工合同（示范文本）GF-2017-0201）规定的优先顺序进行解释。施工合同中包含以下工程价款主要内容：工程中标价为5800万元，暂列金额为580万元，主要材料所占比重为60%；工程预付款为工程造价的20%；工程进度款逐月计算；工程质量保修金3%，在每月工程进度款中扣除，质保期满后返还。项目部按照劳动力均衡实用、分析劳动需用总工日、确定人员数量和比例等劳动力计划编制要求，编制了劳动力需求计划。重点解决了因劳动力使用不均衡，给劳动力调配带来的困难，和避免出现过多、过大的需求高峰等诸多问题。项目部材料管理制度要求对物资采购合同的标的、价格、结算、特殊要求等条款加强重点管理。其中，对合同标的的管理要包括物资的名称、花色、技术标准、质量要求等内容。建设单位对一关键线路上的工序内容提出修改，由设计单位发出设计变更通知，为此造成工程停工10天。施工单位对此提出索赔事项如下：按当地造价部门发布的工资标准计算停窝工人工费8.5万元；塔吊等机械停窝工台班费5.1万元；索赔工期10天。 | 35. A construction unit undertook a project through bidding, and Party A and Party B reached an agreement on the modification of the project contract agreement (No. HT-XY-201909001), the special contract terms (No. HT-ZY-201909001) and the general contract terms (No. HT-TY-201909001) through negotiation. And the construction contract is signed. The confirmation includes the letter of bid, Notice of acceptance and other contract documents shall be interpreted in accordance with the priority order stipulated in the Construction Contract (Model Text) GF-2017-0201. The construction contract contains the following main contents of the project price: The price of the project is 58 million yuan, the temporary amount is 5.8 million yuan, the proportion of the main materials is 60%; the advance payment of the project is 20% of the project cost; the project progress payment is calculated month by month; the project quality warranty payment is 3%, deducted in the monthly project progress payment, and the warranty is returned after the expiration of the term. The project department has prepared the labor demand plan according to the requirements of labor planning, such as labor balance and practicality, analysis of the total working days required for labor, determination of the number and proportion of personnel, etc. The project has focused on solving the difficulties brought by the uneven use of labor force, and avoiding many problems such as excessive and excessive demand peaks. The material management system of the project Department requires to strengthen the key management of the object, price, settlement and special requirements of the material procurement contract, among which the management of the object of the contract shall include the name, color, technical standard and quality requirements of the material. The construction unit proposed to modify the content of the process on a key line, and the design unit issued a notice of design change, which caused the project to stop for 10 days. The construction unit made claims as follows: according to the wage standard issued by the local cost department, the labor cost of the lockout workers was 85,000 yuan; the shift cost of the tower crane and other machinery lockout workers was 51,000 yuan; the claim period was 10 days. | 35、指出合同签订中的不妥之处，写出背景资料中5个合同文件解释的优先顺序。 | 35. Point out the inadequacies in contract signing and write the priority order of interpretation of the five contract documents in the background information.
CBQ-036 | 36、某施工单位通过竞标承建一工程项目，甲乙双方通过协商，对工程合同协议书（编号HT-XY-201909001），以及专用合同条款（编号HT-ZY-201909001）和通用合同条款（编号HT-TY-201909001）修改意见达成一致，签订了施工合同。确认包括投标函、中标通知书等合同文件按照《建设工程施工合同（示范文本）GF-2017-0201）规定的优先顺序进行解释。施工合同中包含以下工程价款主要内容：工程中标价为5800万元，暂列金额为580万元，主要材料所占比重为60%；工程预付款为工程造价的20%；工程进度款逐月计算；工程质量保修金3%，在每月工程进度款中扣除，质保期满后返还。项目部按照劳动力均衡实用、分析劳动需用总工日、确定人员数量和比例等劳动力计划编制要求，编制了劳动力需求计划。重点解决了因劳动力使用不均衡，给劳动力调配带来的困难，和避免出现过多、过大的需求高峰等诸多问题。项目部材料管理制度要求对物资采购合同的标的、价格、结算、特殊要求等条款加强重点管理。其中，对合同标的的管理要包括物资的名称、花色、技术标准、质量要求等内容。建设单位对一关键线路上的工序内容提出修改，由设计单位发出设计变更通知，为此造成工程停工10天。施工单位对此提出索赔事项如下：按当地造价部门发布的工资标准计算停窝工人工费8.5万元；塔吊等机械停窝工台班费5.1万元；索赔工期10天。 | 36. A construction unit undertook a project through bidding, and Party A and Party B reached an agreement on the modification of the project contract agreement (No. HT-XY-201909001), the special contract terms (No. HT-ZY-201909001) and the general contract terms (No. HT-TY-201909001) through negotiation. And the construction contract is signed. The confirmation includes the letter of bid, Notice of acceptance and other contract documents shall be interpreted in accordance with the priority order stipulated in the Construction Contract (Model Text) GF-2017-0201. The construction contract contains the following main contents of the project price: The price of the project is 58 million yuan, the temporary amount is 5.8 million yuan, the proportion of the main materials is 60%; the advance payment of the project is 20% of the project cost; the project progress payment is calculated month by month; the project quality warranty payment is 3%, deducted in the monthly project progress payment, and the warranty is returned after the expiration of the term. The project department has prepared the labor demand plan according to the requirements of labor planning, such as labor balance and practicality, analysis of the total working days required for labor, determination of the number and proportion of personnel, etc. The project has focused on solving the difficulties brought by the uneven use of labor force, and avoiding many problems such as excessive and excessive demand peaks. The material management system of the project Department requires to strengthen the key management of the object, price, settlement and special requirements of the material procurement contract, among which the management of the object of the contract shall include the name, color, technical standard and quality requirements of the material. The construction unit proposed to modify the content of the process on a key line, and the design unit issued a notice of design change, which caused the project to stop for 10 days. The construction unit made claims as follows: according to the wage standard issued by the local cost department, the labor cost of the lockout workers was 85,000 yuan; the shift cost of the tower crane and other machinery lockout workers was 51,000 yuan; the claim period was 10 days. | 36、办理设计变更的步骤有哪些？施工单位的索赔事项是否成立？并说明理由。 | 36. What are the steps for handling a design change? Is the construction unit's claim established? And state the reasons.
CBQ-037 | 37、某高级住宅工程，建筑面积80000m2，由3栋塔楼构成，地下2层（含车库），地上28层，底板厚度800mm，由A施工总承包单位承建。合同约定工程最终达到绿色建筑评价二星级。工程开始施工正值冬季，A施工单位项目部编制了冬期施工专项方案，根据当地资源和气候情况对底板混凝土的养护采用综合蓄热法，对底板混凝土的测温方案和温差控制，降温梯度，及混凝土养护时间提出了控制指标要求。项目部制定了项目风险管理制度和应对负面风险的措施。规范了包括风险识别、风险应对等风险管理程序的管理流程；制定了向保险公司投保的风险转移等措施，达到了应对负面风险管理的目的。施工中，施工员对气割作业人员进行安全作业交底，主要内容有：气瓶要防止暴晒；气瓶在楼层内滚动时应设置防震圈；严禁用带油的手套开气瓶。切割时，氧气瓶和乙炔瓶的放置距离不得小于5m，气瓶离明火的距离不得小于8m；作业点离易燃物的距离不小于20m；气瓶内的气体应尽量用完，减少浪费。 | 37. A senior residential project, construction area of 80000m2, composed of 3 towers, 2 floors underground (including garage), 28 floors above the ground, the thickness of the bottom plate 800mm, by the general contractor of A construction unit. It is agreed in the contract that the project will eventually reach the two-star green building evaluation. When the project began construction in winter, the project department of the construction unit A prepared a special construction plan in winter. According to the local resources and climate conditions, comprehensive heat storage method was adopted for the maintenance of concrete on the floor, and the control index requirements were put forward for the temperature measurement scheme, temperature difference control, cooling gradient and concrete maintenance time of concrete on the floor. The project department has formulated the project risk management system and measures to deal with negative risks. The management process including risk identification, risk response and other risk management procedures has been standardized; Measures such as risk transfer to insurance companies have been formulated to achieve the purpose of coping with negative risk management. During the construction, the constructors disclose the safety operation of the gas cutting operators, the main contents are: the gas cylinder should be prevented from exposure to sunlight; When the gas cylinder is rolling in the floor, an anti-shock ring should be set; It is strictly forbidden to open the gas cylinder with oil gloves. When cutting, the distance between the oxygen cylinder and the acetylene cylinder should not be less than 5m, and the distance between the gas cylinder and the open flame should not be less than 8m; The distance between the operation point and the flammable material shall not be less than 20m; The gas in the cylinder should be used up as far as possible to reduce waste. | 37、冬期施工混凝土养护方法还有那些？对底板混凝土养护中温差控制、温降梯度、养护时间应提出的控制指标是什么？ | 37. Winter construction concrete curing methods and those? What are the control indexes of temperature difference control, temperature drop gradient and curing time in the curing of concrete on the bottom plate?
CBQ-038 | 38、某高级住宅工程，建筑面积80000m2，由3栋塔楼构成，地下2层（含车库），地上28层，底板厚度800mm，由A施工总承包单位承建。合同约定工程最终达到绿色建筑评价二星级。工程开始施工正值冬季，A施工单位项目部编制了冬期施工专项方案，根据当地资源和气候情况对底板混凝土的养护采用综合蓄热法，对底板混凝土的测温方案和温差控制，降温梯度，及混凝土养护时间提出了控制指标要求。项目部制定了项目风险管理制度和应对负面风险的措施。规范了包括风险识别、风险应对等风险管理程序的管理流程；制定了向保险公司投保的风险转移等措施，达到了应对负面风险管理的目的。施工中，施工员对气割作业人员进行安全作业交底，主要内容有：气瓶要防止暴晒；气瓶在楼层内滚动时应设置防震圈；严禁用带油的手套开气瓶。切割时，氧气瓶和乙炔瓶的放置距离不得小于5m，气瓶离明火的距离不得小于8m；作业点离易燃物的距离不小于20m；气瓶内的气体应尽量用完，减少浪费。 | 38. A senior residential project, construction area of 80000m2, composed of 3 towers, 2 floors underground (including garage), 28 floors above the ground, the thickness of the bottom plate 800mm, by the general contractor of A construction unit. It is agreed in the contract that the project will eventually reach the two-star green building evaluation. When the project began construction in winter, the project department of the construction unit A prepared a special construction plan in winter. According to the local resources and climate conditions, comprehensive heat storage method was adopted for the maintenance of concrete on the floor, and the control index requirements were put forward for the temperature measurement scheme, temperature difference control, cooling gradient and concrete maintenance time of concrete on the floor. The project department has formulated the project risk management system and measures to deal with negative risks. The management process including risk identification, risk response and other risk management procedures has been standardized; Measures such as risk transfer to insurance companies have been formulated to achieve the purpose of coping with negative risk management. During the construction, the constructors disclose the safety operation of the gas cutting operators, the main contents are: the gas cylinder should be prevented from exposure to sunlight; When the gas cylinder is rolling in the floor, an anti-shock ring should be set; It is strictly forbidden to open the gas cylinder with oil gloves. When cutting, the distance between the oxygen cylinder and the acetylene cylinder should not be less than 5m, and the distance between the gas cylinder and the open flame should not be less than 8m; The distance between the operation point and the flammable material shall not be less than 20m; The gas in the cylinder should be used up as far as possible to reduce waste. | 38、指出施工员安全作业交底中的不妥之处，并写出正确做法。 | 38. Point out the improper place in the construction worker's safety operation disclosure, and write out the correct approach.
CBQ-039 | 39、某开发商拟建一城市综合体项目，预计总投资十五亿元。发包方式采用施工总承包，施工单位承担部分垫资，按月度实际完成工作量的75%支付工程款，工程质量为合格，保修金为3%，合同总工期为32个月。 某总包单位对该开发商社会信誉，偿债备付率、利息备付率等偿债能力及其他情况进行了尽职调查。中标后，双方依据《建设工程工程量清单计价规范》GB50500-2013，对工程量清单编制方法等强制性规定进行了确认，对工程造价进行了全面审核。最终确定有关费用如下：分部分项工程费82000.00万元，措施费20500.00万元，其他项目费12800.00万元，暂列金额8200.00万元，规费2470.00万元，税金3750.00万元。双方依据《建设工程施工合同（示范文本》GF-2017-0201签订了工程施工总承包合同。 项目部对基坑围护提出了三个方案：A方案成本为8750.00万元，功能系数为0.33； B方案成本为8640.00万元，功能系数为0.35；C方案成本为8525.00万元，功能系数为0.32。最终运用价值工程方法确定了实施方案。 竣工结算时，总包单位提出索赔事项如下：1、特大暴雨造成停工7天，开发商要求总包单位安排20人留守现场照管工地，发生费用5.60万元。2、本工程设计采用了某种新材料， 总包单位为此支付给检测单位检验试验费4.60万元，要求开发商承担。3、工程主体完工3个月后，总包单位为配合开发商自行发包的燃气等专业工程施工，脚手架留置比计划延长2个月拆除。为此要求开发商支付2个月脚手架租赁费68.00万元。4、总包单位要求开发商按照银行同期同类贷款利率，支付垫资利息1142.00万元。 | 39. A developer is planning to build an urban complex project with an estimated total investment of 1.5 billion yuan. The contracting method adopts the general contract of construction, the construction unit bears part of the capital, pays the project fee according to 75% of the actual work completed each month, the project quality is qualified, the warranty fee is 3%, the total contract period is 32 months. A general contractor has conducted due diligence on the developer's social reputation, debt repayment provision rate, interest provision rate and other solvency conditions. After winning the bid, the two parties confirmed the compilation method of the bill of quantities and other mandatory provisions and conducted a comprehensive audit of the project cost according to GB50500-2013, the Code for Valuation of the Bill of Quantities of Construction Projects. The final determination of the relevant costs is as follows: division project fee 82000.00 million yuan, measure fee 20500.00 million yuan, other project fee 12800.00 million yuan, provisional amount 8200.00 million yuan, fee 24.70.00 million yuan, tax 37.50.00 million yuan. The two parties have signed the general contract for the construction of the project in accordance with the Construction Contract (Model Text) GF-2017-0201. The project department put forward three plans for the foundation pit enclosure: the cost of plan A is 87.50.00 million yuan, and the function coefficient is 0.33; The cost of plan B is 8640.00 million yuan, the function coefficient is 0.35; The cost of plan C is 85.2500 million yuan, and the functional coefficient is 0.32. Finally, the implementation plan is determined by the method of value engineering. At the time of completion settlement, the general contractor put forward the claims as follows: 1. The heavy rainstorm caused a shutdown of 7 days, and the developer required the general contractor to arrange 20 people to stay at the site to take care of the construction site, and the cost was 5600 yuan. 2. Some new material was used in the design of the project, for which the contractor paid the inspection and test fee of 4600 yuan to the testing unit, which was required to be borne by the developer. 3, 3 months after the completion of the main project, the total contractor in order to cooperate with the developer to contract gas and other professional engineering construction, scaffolding retention than planned to extend the demolition of 2 months. To this end, the developer is required to pay the scaffolding rental fee of 680,000 yuan for 2 months. 4, the total contract unit requires the developer to pay the cushion interest of 1142.00 million yuan in accordance with the same loan rate of the bank during the same period. | 39、对总包合同实施管理的原则有哪些？ | 39. What are the principles of managing the general contract?
CBQ-040 | 40、某开发商拟建一城市综合体项目，预计总投资十五亿元。发包方式采用施工总承包，施工单位承担部分垫资，按月度实际完成工作量的75%支付工程款，工程质量为合格，保修金为3%，合同总工期为32个月。 某总包单位对该开发商社会信誉，偿债备付率、利息备付率等偿债能力及其他情况进行了尽职调查。中标后，双方依据《建设工程工程量清单计价规范》GB50500-2013，对工程量清单编制方法等强制性规定进行了确认，对工程造价进行了全面审核。最终确定有关费用如下：分部分项工程费82000.00万元，措施费20500.00万元，其他项目费12800.00万元，暂列金额8200.00万元，规费2470.00万元，税金3750.00万元。双方依据《建设工程施工合同（示范文本》GF-2017-0201签订了工程施工总承包合同。 项目部对基坑围护提出了三个方案：A方案成本为8750.00万元，功能系数为0.33； B方案成本为8640.00万元，功能系数为0.35；C方案成本为8525.00万元，功能系数为0.32。最终运用价值工程方法确定了实施方案。 竣工结算时，总包单位提出索赔事项如下：1、特大暴雨造成停工7天，开发商要求总包单位安排20人留守现场照管工地，发生费用5.60万元。2、本工程设计采用了某种新材料， 总包单位为此支付给检测单位检验试验费4.60万元，要求开发商承担。3、工程主体完工3个月后，总包单位为配合开发商自行发包的燃气等专业工程施工，脚手架留置比计划延长2个月拆除。为此要求开发商支付2个月脚手架租赁费68.00万元。4、总包单位要求开发商按照银行同期同类贷款利率，支付垫资利息1142.00万元。 | 40. A developer is planning to build an urban complex project with an estimated total investment of 1.5 billion yuan. The contracting method adopts the general contract of construction, the construction unit bears part of the capital, pays the project fee according to 75% of the actual work completed each month, the project quality is qualified, the warranty fee is 3%, the total contract period is 32 months. A general contractor has conducted due diligence on the developer's social reputation, debt repayment provision rate, interest provision rate and other solvency conditions. After winning the bid, the two parties confirmed the compilation method of the bill of quantities and other mandatory provisions and conducted a comprehensive audit of the project cost according to GB50500-2013, the Code for Valuation of the Bill of Quantities of Construction Projects. The final determination of the relevant costs is as follows: division project fee 82000.00 million yuan, measure fee 20500.00 million yuan, other project fee 12800.00 million yuan, provisional amount 8200.00 million yuan, fee 24.70.00 million yuan, tax 37.50.00 million yuan. The two parties have signed the general contract for the construction of the project in accordance with the Construction Contract (Model Text) GF-2017-0201. The project department put forward three plans for the foundation pit enclosure: the cost of plan A is 87.50.00 million yuan, and the function coefficient is 0.33; The cost of plan B is 8640.00 million yuan, the function coefficient is 0.35; The cost of plan C is 85.2500 million yuan, and the functional coefficient is 0.32. Finally, the implementation plan is determined by the method of value engineering. At the time of completion settlement, the general contractor put forward the claims as follows: 1. The heavy rainstorm caused a shutdown of 7 days, and the developer required the general contractor to arrange 20 people to stay at the site to take care of the construction site, and the cost was 5600 yuan. 2. Some new material was used in the design of the project, for which the contractor paid the inspection and test fee of 4600 yuan to the testing unit, which was required to be borne by the developer. 3, 3 months after the completion of the main project, the total contractor in order to cooperate with the developer to contract gas and other professional engineering construction, scaffolding retention than planned to extend the demolition of 2 months. To this end, the developer is required to pay the scaffolding rental fee of 680,000 yuan for 2 months. 4, the total contract unit requires the developer to pay the cushion interest of 1142.00 million yuan in accordance with the same loan rate of the bank during the same period. | 40、总包单位提出的索赔是否成立？并说明理由。 | 40. Is the claim made by the general contractor valid? And state the reasons.
CBQ-041 | 41、一新建工程，地下二层，地上二十层，高度70m，建筑面积40000m2，标准层平面为40m×40m。项目部根据施工条件和需求，按照施工机械设备选择的经济性等原则，采用单位工程量成本比较法选择确定了塔吊型号。施工总承包单位根据项目部制定的安全技术措施、安全评价等安全管理内容提取了项目安全生产费用。 施工中，项目部技术负责人组织编写了项目检测试验计划，内容包括试验项目名称、计划试验时间等，报项目经理审批同意后实施。 项目部在“X工程施工组织设计”中制定了临边作业、攀登与悬空作业等高处作业项目安全技术措施。在“绿色施工专项方案”的节能与能源利用中，分别设定了生产等用电项的控制指标，规定了包括分区计量等定期管理要求，制定了指标控制预防与纠正措施。 在一次塔吊起吊荷载达到其额定起重量95%的起吊作业中，安全人员让操作人员先将重物吊起离地面15cm，然后对重物的平稳性，设备和绑扎等各项内容进行了检查，确认安全后同意其继续起吊作业。 | 41. A new construction project, two underground floors, 20 floors above the ground, height 70m, construction area 4000m2, the standard floor plane is 40m×40m. Project department according to the construction conditions and needs, in accordance with the construction machinery and equipment selection of economic principles, the use of unit project cost comparison method to select and determine the tower crane model. The general contractor of construction extracts the project safety production cost according to the safety technical measures, safety evaluation and other safety management contents formulated by the project department. During the construction, the technical leader of the project department organizes and prepares the project test plan, including the name of the test project, the planned test time, etc., which shall be implemented after approval by the project manager. In the "X Project Construction Organization Design", the project department has formulated safety technical measures for high altitude operation projects such as edge operation, climbing and hanging operation. In the energy saving and energy utilization of the "green construction special plan", the control indicators of production and other electricity consumption items are set respectively, the regular management requirements including zoning measurement are specified, and the prevention and corrective measures for index control are formulated. In a lifting operation where the lifting load of the tower crane reaches 95% of its rated lifting weight, the safety personnel let the operator lift the heavy object 15cm from the ground first, and then check the stability of the heavy object, equipment and lashing and other contents, and agree to continue the lifting operation after confirming the safety. | 41、安全生产费用还应包括哪些内容？需要在施工组织设计中制定安全技术措施的高处作业项还有哪些？ | 41. What else should be included in production safety costs? What are the other high work items that need to formulate safety technical measures in the construction organization design?
CBQ-042 | 42、一新建工程，地下二层，地上二十层，高度70m，建筑面积40000m2，标准层平面为40m×40m。项目部根据施工条件和需求，按照施工机械设备选择的经济性等原则，采用单位工程量成本比较法选择确定了塔吊型号。施工总承包单位根据项目部制定的安全技术措施、安全评价等安全管理内容提取了项目安全生产费用。 施工中，项目部技术负责人组织编写了项目检测试验计划，内容包括试验项目名称、计划试验时间等，报项目经理审批同意后实施。 项目部在“X工程施工组织设计”中制定了临边作业、攀登与悬空作业等高处作业项目安全技术措施。在“绿色施工专项方案”的节能与能源利用中，分别设定了生产等用电项的控制指标，规定了包括分区计量等定期管理要求，制定了指标控制预防与纠正措施。 在一次塔吊起吊荷载达到其额定起重量95%的起吊作业中，安全人员让操作人员先将重物吊起离地面15cm，然后对重物的平稳性，设备和绑扎等各项内容进行了检查，确认安全后同意其继续起吊作业。 | 42. A new construction project, two underground floors, 20 floors above the ground, height 70m, construction area 4000m2, the standard floor plane is 40m×40m. Project department according to the construction conditions and needs, in accordance with the construction machinery and equipment selection of economic principles, the use of unit project cost comparison method to select and determine the tower crane model. The general contractor of construction extracts the project safety production cost according to the safety technical measures, safety evaluation and other safety management contents formulated by the project department. During the construction, the technical leader of the project department organizes and prepares the project test plan, including the name of the test project, the planned test time, etc., which shall be implemented after approval by the project manager. In the "X Project Construction Organization Design", the project department has formulated safety technical measures for high altitude operation projects such as edge operation, climbing and hanging operation. In the energy saving and energy utilization of the "green construction special plan", the control indicators of production and other electricity consumption items are set respectively, the regular management requirements including zoning measurement are specified, and the prevention and corrective measures for index control are formulated. In a lifting operation where the lifting load of the tower crane reaches 95% of its rated lifting weight, the safety personnel let the operator lift the heavy object 15cm from the ground first, and then check the stability of the heavy object, equipment and lashing and other contents, and agree to continue the lifting operation after confirming the safety. | 42、指出项目检测试验计划管理中的不妥之处，并说明理由。施工检测试验计划内容还有哪些？ | 42. Point out the inadequacies in the management of project inspection and test plan, and explain the reasons. What are the other contents of the construction inspection test plan?
CBQ-043 | 43、某新建高层住宅工程，建筑面积16000㎡。地下一层，地上十二层，二层以下为现浇钢筋混凝土结构，二层以上为装配式混凝土结构，预制墙板钢筋采用套筒灌浆连接施工工艺。 施工总承包合同签订后，施工单位项目经理遵循项目质量管理程序，按照质量管理PDCA循环工作方法持续改进质量工作。 监理工程师在检查土方回填施工时发现：回填土料混有建筑垃圾；土料铺填厚度大于400mm；采用振动压实机压实2遍成活；每天将回填2-3层的环刀法取的土样统一送检测单位检测压实系数。对此提出整改要求。 "后浇带施工专项方案″中确定∶模板独立支设；剔除模板用钢丝网；因设计无要求，基础底板后浇带10d后封闭等。 监理工程师在检查第4层外墙板安装质量时发现： 钢筋套筒连接灌浆满足规范要求；留置了3组边长为70.7mm的立方体灌浆料标准养护试件；留置了1组边长为70.7mm的立方体坐浆料标准养护试件；施工单位选取第4层外墙板竖缝两侧11㎡的部位在现场进行淋水试验，对此要求整改。 | 43. A new high-rise residential project, construction area of 16000 square meters. One underground layer, twelve floors on the ground, two floors below the cast-in-place reinforced concrete structure, two floors above the prefabricated concrete structure, the precast wall slab reinforcement adopts sleeve grouting connection construction technology. After the general contract of construction is signed, the project manager of the construction unit shall follow the project quality management procedure and continuously improve the quality work according to the PDCA cycle working method of quality management. When the supervision engineer inspected the earthwork backfill construction, he found that: the backfill soil material was mixed with construction waste; The thickness of earthfill is greater than 400mm; Vibratory compactor is used to compact 2 times to live; Every day, the soil sample taken by the ring knife method of backfilling 2-3 layers is sent to the testing unit to detect the compaction coefficient. Put forward rectification requirements for this. In the "Special plan for the construction of the post-casting belt", it is determined that: the template is independently supported; Remove the template with steel wire mesh; Because there is no requirement in the design, the base plate is closed after 10d pouring belt. When the supervision engineer checked the installation quality of the fourth layer outer wall panel, it was found that the grouting of the reinforcement sleeve met the requirements of the specification; 3 sets of standard curing specimens of cubic grout material with side length of 70.7mm were retained; A set of standard curing specimens of cube sizing material with side length of 70.7mm were retained; The construction unit selected 11 square meters on both sides of the vertical seam of the fourth layer wall panel to carry out the dripping test on site, which requires rectification. | 43、指出土方回填施工中的不妥之处？并写出正确做法。 | 43. Point out the improper place in the construction of earthwork backfill? And write out the correct practice.
CBQ-044 | 44、某新建高层住宅工程，建筑面积16000㎡。地下一层，地上十二层，二层以下为现浇钢筋混凝土结构，二层以上为装配式混凝土结构，预制墙板钢筋采用套筒灌浆连接施工工艺。 施工总承包合同签订后，施工单位项目经理遵循项目质量管理程序，按照质量管理PDCA循环工作方法持续改进质量工作。 监理工程师在检查土方回填施工时发现：回填土料混有建筑垃圾；土料铺填厚度大于400mm；采用振动压实机压实2遍成活；每天将回填2-3层的环刀法取的土样统一送检测单位检测压实系数。对此提出整改要求。 "后浇带施工专项方案″中确定∶模板独立支设；剔除模板用钢丝网；因设计无要求，基础底板后浇带10d后封闭等。 监理工程师在检查第4层外墙板安装质量时发现： 钢筋套筒连接灌浆满足规范要求；留置了3组边长为70.7mm的立方体灌浆料标准养护试件；留置了1组边长为70.7mm的立方体坐浆料标准养护试件；施工单位选取第4层外墙板竖缝两侧11㎡的部位在现场进行淋水试验，对此要求整改。 | 44. A new high-rise residential project, construction area of 16000 square meters. One underground layer, twelve floors on the ground, two floors below the cast-in-place reinforced concrete structure, two floors above the prefabricated concrete structure, the precast wall slab reinforcement adopts sleeve grouting connection construction technology. After the general contract of construction is signed, the project manager of the construction unit shall follow the project quality management procedure and continuously improve the quality work according to the PDCA cycle working method of quality management. When the supervision engineer inspected the earthwork backfill construction, he found that: the backfill soil material was mixed with construction waste; The thickness of earthfill is greater than 400mm; Vibratory compactor is used to compact 2 times to live; Every day, the soil sample taken by the ring knife method of backfilling 2-3 layers is sent to the testing unit to detect the compaction coefficient. Put forward rectification requirements for this. In the "Special plan for the construction of the post-casting belt", it is determined that: the template is independently supported; Remove the template with steel wire mesh; Because there is no requirement in the design, the base plate is closed after 10d pouring belt. When the supervision engineer checked the installation quality of the fourth layer outer wall panel, it was found that the grouting of the reinforcement sleeve met the requirements of the specification; 3 sets of standard curing specimens of cubic grout material with side length of 70.7mm were retained; A set of standard curing specimens of cube sizing material with side length of 70.7mm were retained; The construction unit selected 11 square meters on both sides of the vertical seam of the fourth layer wall panel to carry out the dripping test on site, which requires rectification. | 44、指出“后浇带专项方案”中的不妥之处？写出后浇带混凝土施工的主要技术措施。 | 44. Point out the inadequacies in the "special program of after-pouring belt". Write out the main technical measures of concrete construction in the post-pouring belt.
CBQ-045 | 45、某建设单位投资兴建一办公楼，投资概算25000.00万元，建筑面积21000m³；钢筋混凝土框架-剪力墙结构，地下2层，层高4.5m；地上18层，层高3.6m；采取工程总承包交钥匙方式对外公开招标，招标范围为工程至交付使用全过程。经公开招投标，A工程总承包单位中标。A单位对工程施工等工程内容进行了招标。 B施工单位中标了本工程施工标段，中标价为18060万元。部分费用如下：安全文明施工费340万元，其中按照施工计划2014年度安全文明施工费为226万元；夜间施工增加费22万元；特殊地区施工增加费36万元；大型机械进出场及安拆费86万元；脚手架费220万元；模板费用105万元；施工总包管理费54万元；暂列金额300万元。 B施工单位中标后第8天，双方签订了项目工程施工承包合同，规定了双方的权利、义务和责任。部分条款如下：工程质量为合格；除钢材及混凝土材料价格浮动超出±10%（含10%）、工程设计变更允许调整以外，其他一律不允许调整；工程预付款比例为10%；合同工期为485日历天，于2014年2月1日起至2015年5月31日止。 B施工单位根据工程特点、工作量和施工方法等影响劳动效率因素，计划主体结构施工工期为120天，预计总用工为5.76万个工日，每天安排2个班次，每个班次工作时间为7个小时。 A工程总承包单位审查结算资料时，发现B施工单位提供的部分索赔资料不完整，如：原图纸设计室外回填土为2:8灰土，实际施工时变更为级配砂石，B施工单位仅仅提供了一份设计变更单，要求B施工单位补充相关资料。 | 45. A construction unit to invest in the construction of an office building, the investment estimate of 25 million yuan, construction area of 21000m³; Reinforced concrete frame shear wall structure, 2 underground floors, height 4.5m; 18 floors above ground, height 3.6m; Adopt the turnkey method of project general contracting and open bidding, the bidding scope covers the whole process from project to delivery and use. After the public bidding, the general contractor of the project A wins the bid. Unit A made a tender for the project construction and other engineering contents. B The construction unit won the bid for the construction section of the project, and the winning price was 180.6 million yuan. Part of the expenses are as follows: 3.4 million yuan for safe and civilized construction, including 2.26 million yuan for safe and civilized construction in 2014 according to the construction plan; The additional cost of night construction is 220,000 yuan; 360,000 yuan added for construction in special areas; 860,000 yuan for large machinery entry and exit and installation and demolition; Scaffolding cost 2.2 million yuan; Template cost 1.05 million yuan; The total construction contract management fee is 540,000 yuan; The provisional amount is 3 million yuan. B On the 8th day after the construction unit wins the bid, the two parties sign the project construction contract, which stipulates the rights, obligations and responsibilities of both parties. Part of the terms are as follows: The quality of the project shall be qualified; No adjustment is allowed except for the price fluctuation of steel and concrete materials exceeding ±10% (including 10%) and the adjustment of engineering design changes; The proportion of advance payment of the project is 10%; The contract period is 485 calendar days from February 1, 2014 to May 31, 2015. B According to the project characteristics, workload and construction method and other factors affecting labor efficiency, the construction unit plans the construction period of the main structure to be 120 days, and the total labor is expected to be 57,600 working days. Two shifts are arranged every day, and the working time of each shift is 7 hours. When the general contractor of project A reviewed the settlement information, it was found that part of the claim information provided by the construction unit B was incomplete, such as: the outdoor backfill in the original drawing was 2:8 gray soil, but the actual construction time changed more graded sand and gravel, and the construction unit B only provided a design change order, requiring the construction unit B to supplement the relevant information. | 45、与B施工单位签订的工程施工承包合同中，A工程总承包单位应承担哪些主要义务？ | 45. In the project construction contract signed with the construction unit B, what main obligations should the general contractor of the project A undertake?
CBQ-046 | 46、某建设单位投资兴建一办公楼，投资概算25000.00万元，建筑面积21000m³；钢筋混凝土框架-剪力墙结构，地下2层，层高4.5m；地上18层，层高3.6m；采取工程总承包交钥匙方式对外公开招标，招标范围为工程至交付使用全过程。经公开招投标，A工程总承包单位中标。A单位对工程施工等工程内容进行了招标。 B施工单位中标了本工程施工标段，中标价为18060万元。部分费用如下：安全文明施工费340万元，其中按照施工计划2014年度安全文明施工费为226万元；夜间施工增加费22万元；特殊地区施工增加费36万元；大型机械进出场及安拆费86万元；脚手架费220万元；模板费用105万元；施工总包管理费54万元；暂列金额300万元。 B施工单位中标后第8天，双方签订了项目工程施工承包合同，规定了双方的权利、义务和责任。部分条款如下：工程质量为合格；除钢材及混凝土材料价格浮动超出±10%（含10%）、工程设计变更允许调整以外，其他一律不允许调整；工程预付款比例为10%；合同工期为485日历天，于2014年2月1日起至2015年5月31日止。 B施工单位根据工程特点、工作量和施工方法等影响劳动效率因素，计划主体结构施工工期为120天，预计总用工为5.76万个工日，每天安排2个班次，每个班次工作时间为7个小时。 A工程总承包单位审查结算资料时，发现B施工单位提供的部分索赔资料不完整，如：原图纸设计室外回填土为2:8灰土，实际施工时变更为级配砂石，B施工单位仅仅提供了一份设计变更单，要求B施工单位补充相关资料。 | 46. A construction unit to invest in the construction of an office building, the investment estimate of 25 million yuan, construction area of 21000m³; Reinforced concrete frame shear wall structure, 2 underground floors, height 4.5m; 18 floors above ground, height 3.6m; Adopt the turnkey method of project general contracting and open bidding, the bidding scope covers the whole process from project to delivery and use. After the public bidding, the general contractor of the project A wins the bid. Unit A made a tender for the project construction and other engineering contents. B The construction unit won the bid for the construction section of the project, and the winning price was 180.6 million yuan. Part of the expenses are as follows: 3.4 million yuan for safe and civilized construction, including 2.26 million yuan for safe and civilized construction in 2014 according to the construction plan; The additional cost of night construction is 220,000 yuan; 360,000 yuan added for construction in special areas; 860,000 yuan for large machinery entry and exit and installation and demolition; Scaffolding cost 2.2 million yuan; Template cost 1.05 million yuan; The total construction contract management fee is 540,000 yuan; The provisional amount is 3 million yuan. B On the 8th day after the construction unit wins the bid, the two parties sign the project construction contract, which stipulates the rights, obligations and responsibilities of both parties. Part of the terms are as follows: The quality of the project shall be qualified; No adjustment is allowed except for the price fluctuation of steel and concrete materials exceeding ±10% (including 10%) and the adjustment of engineering design changes; The proportion of advance payment of the project is 10%; The contract period is 485 calendar days from February 1, 2014 to May 31, 2015. B According to the project characteristics, workload and construction method and other factors affecting labor efficiency, the construction unit plans the construction period of the main structure to be 120 days, and the total labor is expected to be 57,600 working days. Two shifts are arranged every day, and the working time of each shift is 7 hours. When the general contractor of project A reviewed the settlement information, it was found that part of the claim information provided by the construction unit B was incomplete, such as: the outdoor backfill in the original drawing was 2:8 gray soil, but the actual construction time changed more graded sand and gravel, and the construction unit B only provided a design change order, requiring the construction unit B to supplement the relevant information. | 46、A工程总承包单位的费用变更控制程序有哪些？B施工单位还需补充哪些索赔资料？ | 46. What are the cost change control procedures of the general contractor of Project A? B What claim information does the construction unit need to supplement?
CBQ-047 | 47、某新建别墅群项目，总建筑面积45000㎡；各幢别墅均为地下1层，地上3层，砖混结构。 总承包单位项目部按幢编制了单幢工程施工进度计划，某幢计划工期为180天。项目部对地下室M5水泥砂浆防水层施工提出了技术要求：采用普通硅酸盐水泥、自来水、中砂、防水剂等材料拌和，中砂含泥量不得大于3%；防水层施工前应采用强度等级M5aaa的普通砂浆将基层表面的孔洞、缝隙堵塞抹平；防水层施工要求一遍成活，涂抹时应压实、表面应提浆压光，并及时进行保湿养护7天。 监理工程师对室内装饰装修工程检查验收后，要求在装饰装修完工后第5天进行TVOC等室内环境污染物检测。项目部对检测时间提出异议。 | 47. A new villa group project, the total construction area of 45,000 square meters; Each villa is underground 1 floor, 3 floors on the ground, brick-concrete structure. The project department of the general contracting unit has prepared the construction schedule of a single building according to the building, and the planned construction period of a building is 180 days. The project department put forward technical requirements for the construction of M5 cement mortar waterproof layer in the basement: ordinary Portland cement, tap water, medium sand, waterproofing agent and other materials are used to mix, and the mud content of medium sand shall not be more than 3%; Before the construction of waterproof layer, ordinary mortar with strength grade M5aaa should be used to smooth the holes and gaps on the surface of the base layer; Waterproof layer construction requirements once live, should be compacted when smearing, the surface should be lifted pulp pressed, and timely moisturizing maintenance for 7 days. After the inspection and acceptance of the interior decoration project, the supervision engineer requires the detection of indoor environmental pollutants such as TVOC on the 5th day after the completion of the decoration. The project department raised objections to the testing time. | 47、指出项目部对地下室水泥砂浆防水层施工技术要求的不妥之处，并分别说明理由。 | 47. Point out the inadequacy of the project department's technical requirements for the construction of cement mortar waterproof layer in the basement, and explain the reasons respectively.
CBQ-048 | 48、某新建别墅群项目，总建筑面积45000㎡；各幢别墅均为地下1层，地上3层，砖混结构。 总承包单位项目部按幢编制了单幢工程施工进度计划，某幢计划工期为180天。项目部对地下室M5水泥砂浆防水层施工提出了技术要求：采用普通硅酸盐水泥、自来水、中砂、防水剂等材料拌和，中砂含泥量不得大于3%；防水层施工前应采用强度等级M5aaa的普通砂浆将基层表面的孔洞、缝隙堵塞抹平；防水层施工要求一遍成活，涂抹时应压实、表面应提浆压光，并及时进行保湿养护7天。 监理工程师对室内装饰装修工程检查验收后，要求在装饰装修完工后第5天进行TVOC等室内环境污染物检测。项目部对检测时间提出异议。 | 48. A new villa group project, the total construction area of 45,000 square meters; Each villa is underground 1 floor, 3 floors on the ground, brick-concrete structure. The project department of the general contracting unit has prepared the construction schedule of a single building according to the building, and the planned construction period of a building is 180 days. The project department put forward technical requirements for the construction of M5 cement mortar waterproof layer in the basement: ordinary Portland cement, tap water, medium sand, waterproofing agent and other materials are used to mix, and the mud content of medium sand shall not be more than 3%; Before the construction of waterproof layer, ordinary mortar with strength grade M5aaa should be used to smooth the holes and gaps on the surface of the base layer; Waterproof layer construction requirements once live, should be compacted when smearing, the surface should be lifted pulp pressed, and timely moisturizing maintenance for 7 days. After the inspection and acceptance of the interior decoration project, the supervision engineer requires the detection of indoor environmental pollutants such as TVOC on the 5th day after the completion of the decoration. The project department raised objections to the testing time. | 48、项目部对检测时间提出异议是否正确？并说明理由。针对本工程，室内环境污染物浓度检测还应包括哪些项目？ | 48. Is it correct for the project department to raise objections to the testing time? And state the reasons. For this project, what other items should be included in indoor environmental pollutant concentration detection?
CBQ-049 | 49、某新建住宅工程项目，建筑面积23000㎡，地下2层，地上18层，现浇钢筋混凝土剪力墙结构，项目实行施工总承包管理。 施工总承包单位项目部技术负责人组织编制了项目质量计划，由项目经理审核后报监理单位审批，该质量计划要求建立的施工过程质量管理记录有：使用机具和检验，测量及试验设备管理记录，质量检查和整改、复查记录，质量管理文件记录及规定的其他记录等。监理工程师对此提出了整改要求。 施工前，项目部根据本工程施工管理和质量控制需要，对分项工程按照工种等条件，检验批按照楼层等条件，制定了分项工程和检验批划分方案，报监理单位审核。 该工程的外墙保温材料和粘接材料等进场后，项目部会同监理工程师核查了其导热系数、燃烧性能等质量证明文件：在监理工程师见证下，对保温、粘接和增强材料进行了复验取样。 项目部针对屋面卷材防水层出现的起鼓（直径＞300mm）问题，制定了割补法处理方案。方案规定了修补工序，并要求按照先铲除保护层、把空鼓卷材割除，对基层清理干净等修补工序依次进行处理整改。 | 49. A new residential engineering project, construction area of 23000 square meters, 2 floors underground, 18 floors above the ground, cast-in-place reinforced concrete shear wall structure, the project implementation of construction general contract management. The technical person in charge of the project department of the general contractor organized the preparation of the project quality plan, which was reviewed by the project manager and submitted to the supervision unit for approval. The quality plan required the establishment of the quality management records of the construction process include: the use of machinery and inspection, measurement and test equipment management records, quality inspection and rectification, review records, quality management document records and other records specified. The supervision engineer put forward rectification requirements for this. Before the construction, according to the needs of the construction management and quality control of the project, the project Department formulated the division plan of the sub-project and the inspection lot according to the conditions of the work type and the inspection lot according to the conditions of the floor, and submitted it to the supervision unit for examination and approval. After the external wall thermal insulation materials and adhesive materials of the project entered the field, the project department and the supervision engineer checked the quality certification documents such as thermal conductivity and combustion performance. Under the witness of the supervision engineer, the thermal insulation, adhesive and reinforcement materials were reinspected and sampled. The project department formulated the cutting and repairing method to solve the problem of bulging (diameter > 300mm) in the waterproof layer of the roofing coil. The plan stipulates the repair process, and requires that the protective layer should be eradicated first, the empty drum coil should be cut off, and the repair process such as the basic cleaning should be processed and rectified in turn. | 49、项目部编制质量计划的做法是否妥当？质量计划中管理记录还应该包括哪些内容？ | 49. Is it appropriate for the project department to prepare the quality plan? What else should the management record include in the quality plan?
CBQ-050 | 50、某新建住宅工程项目，建筑面积23000㎡，地下2层，地上18层，现浇钢筋混凝土剪力墙结构，项目实行施工总承包管理。 施工总承包单位项目部技术负责人组织编制了项目质量计划，由项目经理审核后报监理单位审批，该质量计划要求建立的施工过程质量管理记录有：使用机具和检验，测量及试验设备管理记录，质量检查和整改、复查记录，质量管理文件记录及规定的其他记录等。监理工程师对此提出了整改要求。 施工前，项目部根据本工程施工管理和质量控制需要，对分项工程按照工种等条件，检验批按照楼层等条件，制定了分项工程和检验批划分方案，报监理单位审核。 该工程的外墙保温材料和粘接材料等进场后，项目部会同监理工程师核查了其导热系数、燃烧性能等质量证明文件：在监理工程师见证下，对保温、粘接和增强材料进行了复验取样。 项目部针对屋面卷材防水层出现的起鼓（直径＞300mm）问题，制定了割补法处理方案。方案规定了修补工序，并要求按照先铲除保护层、把空鼓卷材割除，对基层清理干净等修补工序依次进行处理整改。 | 50. A new residential engineering project, construction area of 23000 square meters, 2 floors underground, 18 floors above the ground, cast-in-place reinforced concrete shear wall structure, the project implementation of construction general contract management. The technical person in charge of the project department of the general contractor organized the preparation of the project quality plan, which was reviewed by the project manager and submitted to the supervision unit for approval. The quality plan required the establishment of the quality management records of the construction process include: the use of machinery and inspection, measurement and test equipment management records, quality inspection and rectification, review records, quality management document records and other records specified. The supervision engineer put forward rectification requirements for this. Before the construction, according to the needs of the construction management and quality control of the project, the project Department formulated the division plan of the sub-project and the inspection lot according to the conditions of the work type and the inspection lot according to the conditions of the floor, and submitted it to the supervision unit for examination and approval. After the external wall thermal insulation materials and adhesive materials of the project entered the field, the project department and the supervision engineer checked the quality certification documents such as thermal conductivity and combustion performance. Under the witness of the supervision engineer, the thermal insulation, adhesive and reinforcement materials were reinspected and sampled. The project department formulated the cutting and repairing method to solve the problem of bulging (diameter > 300mm) in the waterproof layer of the roofing coil. The plan stipulates the repair process, and requires that the protective layer should be eradicated first, the empty drum coil should be cut off, and the repair process such as the basic cleaning should be processed and rectified in turn. | 50、分别指出分项工程和检验批划分的条件还有哪些？ | 50. What other conditions indicate the division of project and inspection lot separately?
CBQ-051 | 51、某新建仓储工程，建筑面积8000㎡，地下1层，地上1层，采用钢筋混凝土筏板基础，建筑高度12m；地下室为钢筋混凝土框架结构，地上部分为钢结构；筏板基础混凝土强度等级为C30，内配双层钢筋网，主筋为HRB400 20螺纹钢。基础筏板下三七灰土夯实，无混凝土垫层。 施工单位安全生产管理部门在安全文明施工巡检时，发现工程告示牌及施工总平面布置的五牌一图布置在了现场主入口处围墙外侧，即要求项目部将五牌一图布置在主入口内侧。 项目部制定的基础筏板钢筋施工技术方案中规定：钢筋保护层厚度控制在40mm；主筋通过直螺纹连接接长，钢筋交叉点按照相隔交错扎牢，绑扎点的绑扎方向要求一致；上、下层钢筋网之间的拉钩要绑扎牢固，以保证上、下层钢筋网相对位置准确。监理工程师审查后认为有些规定不妥，要求改正。 屋面梁安装过程中，发现两名施工人员高处坠物事故，一人死亡。当地人民政府接到事故报告后，按照事故调查的规定组织安全生产监督管理部门、公安机关等相关部门委派的人员和2名专家组成事故调查组。调查组检查了项目部制定的项目施工安全管理制度，其中规定了项目经理至少每旬组织开展一次定期安全检查，专职安全人员定期进行巡视检查。调查组认为项目部经常性安全检查制度规定内容不全，要求完善。 | 51. A new storage project, construction area of 8000 square meters, underground 1 layer, ground 1 layer, using reinforced concrete raft foundation, building height 12m; The basement is a reinforced concrete frame structure, the ground part is a steel structure; Raft foundation concrete strength grade is C30, equipped with double reinforcement mesh, the main reinforcement is HRB400 20 rebar. The foundation raft is compacted with tamped grey earth without concrete cushion. When the safety production management department of the construction unit inspected the safe and civilized construction, it was found that the five plates and one diagram of the project sign and the construction general layout were arranged on the outside of the wall of the main entrance of the site, that is, the project department was required to arrange the five plates and one diagram on the inside of the main entrance. According to the technical plan of reinforcement construction of foundation raft formulated by the project department, the thickness of reinforcement protective layer is controlled at 40mm; The main reinforcement is connected by straight thread, the intersections of the reinforcement are staggered and fastened according to the distance, and the binding direction of the binding points is the same; The pull hook between the upper and lower steel mesh should be tied firmly to ensure that the relative position of the upper and lower steel mesh is accurate. After review, the supervision engineer thinks that some provisions are improper and requires correction. During the installation of the roof beam, two construction workers were found to have fallen objects from high places, and one died. After receiving the report of the accident, the local people's government shall, in accordance with the provisions of the accident investigation, organize the personnel appointed by the work safety supervision and administration department, the public security organ and other relevant departments and two experts to form an accident investigation team. The investigation team inspected the project construction safety management system formulated by the project department, which stipulates that the project manager shall organize and carry out regular safety inspections at least once every ten days, and full-time safety personnel shall carry out regular inspections. The investigation team believes that the provisions of the regular safety inspection system of the project department are incomplete and should be improved. | 51、写出基础筏板钢筋技术方案中的不妥之处，并分别说明理由。 | 51. Write out the inadequacies in the technical scheme of reinforcement of foundation raft, and explain the reasons respectively.
CBQ-052 | 52、某新建仓储工程，建筑面积8000㎡，地下1层，地上1层，采用钢筋混凝土筏板基础，建筑高度12m；地下室为钢筋混凝土框架结构，地上部分为钢结构；筏板基础混凝土强度等级为C30，内配双层钢筋网，主筋为HRB400 20螺纹钢。基础筏板下三七灰土夯实，无混凝土垫层。 施工单位安全生产管理部门在安全文明施工巡检时，发现工程告示牌及施工总平面布置的五牌一图布置在了现场主入口处围墙外侧，即要求项目部将五牌一图布置在主入口内侧。 项目部制定的基础筏板钢筋施工技术方案中规定：钢筋保护层厚度控制在40mm；主筋通过直螺纹连接接长，钢筋交叉点按照相隔交错扎牢，绑扎点的绑扎方向要求一致；上、下层钢筋网之间的拉钩要绑扎牢固，以保证上、下层钢筋网相对位置准确。监理工程师审查后认为有些规定不妥，要求改正。 屋面梁安装过程中，发现两名施工人员高处坠物事故，一人死亡。当地人民政府接到事故报告后，按照事故调查的规定组织安全生产监督管理部门、公安机关等相关部门委派的人员和2名专家组成事故调查组。调查组检查了项目部制定的项目施工安全管理制度，其中规定了项目经理至少每旬组织开展一次定期安全检查，专职安全人员定期进行巡视检查。调查组认为项目部经常性安全检查制度规定内容不全，要求完善。 | 52. A new storage project, construction area of 8000 square meters, underground 1 layer, ground 1 layer, using reinforced concrete raft foundation, building height 12m; The basement is a reinforced concrete frame structure, the ground part is a steel structure; Raft foundation concrete strength grade is C30, equipped with double reinforcement mesh, the main reinforcement is HRB400 20 rebar. The foundation raft is compacted with tamped grey earth without concrete cushion. When the safety production management department of the construction unit inspected the safe and civilized construction, it was found that the five plates and one diagram of the project sign and the construction general layout were arranged on the outside of the wall of the main entrance of the site, that is, the project department was required to arrange the five plates and one diagram on the inside of the main entrance. According to the technical plan of reinforcement construction of foundation raft formulated by the project department, the thickness of reinforcement protective layer is controlled at 40mm; The main reinforcement is connected by straight thread, the intersections of the reinforcement are staggered and fastened according to the distance, and the binding direction of the binding points is the same; The pull hook between the upper and lower steel mesh should be tied firmly to ensure that the relative position of the upper and lower steel mesh is accurate. After review, the supervision engineer thinks that some provisions are improper and requires correction. During the installation of the roof beam, two construction workers were found to have fallen objects from high places, and one died. After receiving the report of the accident, the local people's government shall, in accordance with the provisions of the accident investigation, organize the personnel appointed by the work safety supervision and administration department, the public security organ and other relevant departments and two experts to form an accident investigation team. The investigation team inspected the project construction safety management system formulated by the project department, which stipulates that the project manager shall organize and carry out regular safety inspections at least once every ten days, and full-time safety personnel shall carry out regular inspections. The investigation team believes that the provisions of the regular safety inspection system of the project department are incomplete and should be improved. | 52、项目部经常性安全检查的方式还应有哪些？ | 52. What other ways should the project department carry out regular safety inspection?
CBQ-053 | 53、某住宅楼工程，场地占地面积约10000m²，结构设计为筏板基础。剪力墙结构，施工总承包单位为外地企业，在本项目所在地设有分公司。本工程项目技术负责人组织编制项目施工组织设计，经分公司技术部经理审核后，报分公司总工程师（公司总工程师授权）审批;专业承包单位编制塔吊安装拆卸方案，按规定组织专家论证会。会上相关人员对专项方案内容的完整性和可行性进行了详细论证，提出了通过的一致意见。在施工现场消防技术方案中，临时施工道路（宽4m）与施工（消防）用主水管沿在建筑住宅楼环装布置，消火栓设在施工道路内侧，据路中线5m，在建住宅楼外边线距道路中线9m，施工用水管计算中，现场施工用水量（q1+q2+q3+q4）为8.5L/S，管网水流速度1.6m/s，漏水损失10%，消防用水量按最小用水量计算。根据项目试验计划，项目总工程师会同实验员选定1、3、5、7、9、11、13、16层各留置1组C30混凝土同条件养护试件，试件在浇筑点制作，脱模后放置在下一层楼梯口处，第5层C30混凝土同条件养护试件强度试验结果为28MPa。 施工过程中发生塔吊倒塌事故，在调查塔吊基础时发现：塔吊基础为6m×6m×0.9m，混凝土强度等级为C20，天然地基持力层承载力特征值（fak）为130kpa，施工单位仅对地基承载力进行计算，并据此判断满足安全要求。 施工过程中发生塔吊倒塌事故，在调查塔吊基础时发现：塔吊基础为6m×6m×0.9m，混凝土强度等级为C20，天然地基持力层承载力特征值（fak）为130kPa，施工单位仅对地基承载力进行计算，并据此判断满足安全要求。 针对项目发生的塔吊事故，当地建设行政主管部门认定为施工总承包单位的不良行为记录，对其诚信行为记录及时进行了公布、上报，并向施工总承包单位工商注册所在地的建设行政主管部门进行了通报。 | 53. A residential building project, the site covers an area of about 10000m², the structure design is the raft foundation. Shear wall structure, the general contractor for construction is a foreign enterprise, with a branch office in the location of the project. The technical person in charge of the project shall organize the preparation of the project construction organization design, which shall be reviewed by the manager of the technical department of the Branch company and submitted to the chief engineer of the Branch company (authorized by the chief engineer of the company) for approval; The professional contractor shall prepare the installation and disassembly plan of the tower crane, and organize the expert demonstration meeting according to the regulations. At the meeting, the relevant personnel demonstrated the completeness and feasibility of the special program in detail, and put forward the consensus of adoption. In the construction site fire control technical scheme, the temporary construction road (4m wide) and the construction (fire control) main water pipe are arranged along the ring of the building residential building, the fire hydrant is located inside the construction road, according to the middle line of the road 5m, the outer edge line of the residential building under construction is 9m from the middle line of the road, the construction water consumption (q1+q2+q3+q4) is 8.5L/S. The water flow rate of the pipe network is 1.6m/s, the leakage loss is 10%, and the fire protection water consumption is calculated according to the minimum water consumption. According to the project test plan, the chief engineer of the project and the experimentor selected 1 group of C30 concrete under the same condition curing specimens on floors 1, 3, 5, 7, 9, 11, 13 and 16. The specimens were made at the pouring point and placed at the landing of the next floor after mold release. The strength test result of the C30 concrete under the same condition curing specimens on the fifth floor was 28MPa. During the construction process, a tower crane collapse accident occurred. During the investigation of the tower crane foundation, it was found that the tower crane foundation was 6m×6m×0.9m, the concrete strength grade was C20, and the bearing capacity characteristic value (fak) of the natural foundation was 130kpa. The construction unit only calculated the bearing capacity of the foundation and judged that it met the safety requirements. The tower crane collapse accident occurred during the construction process. When investigating the tower crane foundation, it was found that the tower crane foundation was 6m×6m×0.9m, the concrete strength grade was C20, and the bearing capacity characteristic value (fak) of the natural foundation was 130kPa. The construction unit only calculated the bearing capacity of the foundation, and judged that the safety requirements were met. In view of the tower crane accident occurred in the project, the local construction administrative department identified it as the bad behavior record of the general contractor of the construction unit, published and reported the good faith behavior record in a timely manner, and notified the construction administrative department where the general contractor of the construction unit was registered. | 53、指出项目施工组织设计、外脚手架施工方案、塔吊安装拆卸方案编制、审批及专家论证的不妥之处，并写出相应的正确做法。 | 53. Point out the inadequacies of project construction organization design, external scaffold construction scheme, tower crane installation and disassembly scheme preparation, approval and expert demonstration, and write out the corresponding correct practices.
CBQ-054 | 54、某住宅楼工程，场地占地面积约10000m²，结构设计为筏板基础。剪力墙结构，施工总承包单位为外地企业，在本项目所在地设有分公司。本工程项目技术负责人组织编制项目施工组织设计，经分公司技术部经理审核后，报分公司总工程师（公司总工程师授权）审批;专业承包单位编制塔吊安装拆卸方案，按规定组织专家论证会。会上相关人员对专项方案内容的完整性和可行性进行了详细论证，提出了通过的一致意见。在施工现场消防技术方案中，临时施工道路（宽4m）与施工（消防）用主水管沿在建筑住宅楼环装布置，消火栓设在施工道路内侧，据路中线5m，在建住宅楼外边线距道路中线9m，施工用水管计算中，现场施工用水量（q1+q2+q3+q4）为8.5L/S，管网水流速度1.6m/s，漏水损失10%，消防用水量按最小用水量计算。根据项目试验计划，项目总工程师会同实验员选定1、3、5、7、9、11、13、16层各留置1组C30混凝土同条件养护试件，试件在浇筑点制作，脱模后放置在下一层楼梯口处，第5层C30混凝土同条件养护试件强度试验结果为28MPa。 施工过程中发生塔吊倒塌事故，在调查塔吊基础时发现：塔吊基础为6m×6m×0.9m，混凝土强度等级为C20，天然地基持力层承载力特征值（fak）为130kpa，施工单位仅对地基承载力进行计算，并据此判断满足安全要求。 施工过程中发生塔吊倒塌事故，在调查塔吊基础时发现：塔吊基础为6m×6m×0.9m，混凝土强度等级为C20，天然地基持力层承载力特征值（fak）为130kPa，施工单位仅对地基承载力进行计算，并据此判断满足安全要求。 针对项目发生的塔吊事故，当地建设行政主管部门认定为施工总承包单位的不良行为记录，对其诚信行为记录及时进行了公布、上报，并向施工总承包单位工商注册所在地的建设行政主管部门进行了通报。 | 54. A residential building project, the site covers an area of about 10000m², the structure design is the raft foundation. Shear wall structure, the general contractor for construction is a foreign enterprise, with a branch office in the location of the project. The technical person in charge of the project shall organize the preparation of the project construction organization design, which shall be reviewed by the manager of the technical department of the Branch company and submitted to the chief engineer of the Branch company (authorized by the chief engineer of the company) for approval; The professional contractor shall prepare the installation and disassembly plan of the tower crane, and organize the expert demonstration meeting according to the regulations. At the meeting, the relevant personnel demonstrated the completeness and feasibility of the special program in detail, and put forward the consensus of adoption. In the construction site fire control technical scheme, the temporary construction road (4m wide) and the construction (fire control) main water pipe are arranged along the ring of the building residential building, the fire hydrant is located inside the construction road, according to the middle line of the road 5m, the outer edge line of the residential building under construction is 9m from the middle line of the road, the construction water consumption (q1+q2+q3+q4) is 8.5L/S. The water flow rate of the pipe network is 1.6m/s, the leakage loss is 10%, and the fire protection water consumption is calculated according to the minimum water consumption. According to the project test plan, the chief engineer of the project and the experimentor selected 1 group of C30 concrete under the same condition curing specimens on floors 1, 3, 5, 7, 9, 11, 13 and 16. The specimens were made at the pouring point and placed at the landing of the next floor after mold release. The strength test result of the C30 concrete under the same condition curing specimens on the fifth floor was 28MPa. During the construction process, a tower crane collapse accident occurred. During the investigation of the tower crane foundation, it was found that the tower crane foundation was 6m×6m×0.9m, the concrete strength grade was C20, and the bearing capacity characteristic value (fak) of the natural foundation was 130kpa. The construction unit only calculated the bearing capacity of the foundation and judged that it met the safety requirements. The tower crane collapse accident occurred during the construction process. When investigating the tower crane foundation, it was found that the tower crane foundation was 6m×6m×0.9m, the concrete strength grade was C20, and the bearing capacity characteristic value (fak) of the natural foundation was 130kPa. The construction unit only calculated the bearing capacity of the foundation, and judged that the safety requirements were met. In view of the tower crane accident occurred in the project, the local construction administrative department identified it as the bad behavior record of the general contractor of the construction unit, published and reported the good faith behavior record in a timely manner, and notified the construction administrative department where the general contractor of the construction unit was registered. | 54、分别指出项目塔吊基础设计计算和构造中的不妥之处。并写出正确做法。 | 54. The inadequacies in the design calculation and construction of tower crane foundation are pointed out respectively. And write out the correct method.
CBQ-055 | 55、某新建体育馆工程，建筑面积约23000m2，现浇钢筋混凝土结构，钢结构网架屋盖，地下一层，地上四层，地下室顶板设计有后张法预应力混凝土梁。 地下室顶板同条件养护试件强度达到设计要求时，施工单位现场生产经理立即向监理工程师口头申请拆除地下室顶板模板，监理工程师同意后，现场将地下室顶板及支架全部拆除。“两年专项治理行动”检查时，二层混凝土结构经回弹-取芯法检验，其强度不满足设计要求，经设计单位验算，需对二层结构进行加固处理，造成直接经济损失300余万元，工程质量事故发生后，现场有关人员立即向本单位负责人报告，并在规定的时间内逐级上报至市（设区）级人民政府住房和城乡建设主管部门，施工单位提交的质量事故报告内容包括：1.事故发生的时间、地点、工程项目名称；2.事故发生的简要经过，无伤亡，3.事故发生后采取的措施及事故控制情况；4.事故报告单位。屋盖网架采用Q390GJ钢，因钢结构制作单位首次采用该材料，施工前，监理工程师要求其对首次采用的Q390GJ钢及相关的接头形式、焊接工艺参数、预热和后热措施等焊接参数组合条件进行焊接工艺评定。填充墙砌体采用单排孔轻骨料混凝土小砌块，专用小彻块砂浆建筑，现场检查中发现：进场的小砌块产品期达到21d后，即开始浇水湿润，待小砌块表面现浮水后，开始彻筑施工：砌筑时将小砌块的底面朝上反砌于墙上，小砌块的搭接长度为块体长度的1/3，砌体的砂浆饱满度要求为：水平灰缝90％以上，竖向灰缝85％以上；墙体每天砌筑高度为1.5m，填充墙彻筑7d后进行顶砌施工，为施工方便，在部分墙体上留置了净宽度为1.2m的临时施工洞口，监理工程师要求对错误之处进行整改。 | 55. A new gymnasium project, construction area of about 23000m2, cast-in reinforced concrete structure, steel structure grid roof, one underground layer, four above-ground layers, the roof of the basement is designed with post-tensioned prestressed concrete beams. When the strength of the basement roof under the same conditions reaches the design requirements, the site production manager of the construction unit immediately applies orally to the supervision engineer for the removal of the basement roof template, and after the supervision engineer agrees, the basement roof and support will be removed on site. "Two years of special treatment action" inspection, the two-storey concrete structure after the rebound - coring method test, its strength does not meet the design requirements, the design unit check, need to strengthen the two-storey structure, resulting in direct economic losses of more than 3 million yuan, after the project quality accident, the site personnel immediately report to the person in charge of the unit. And in the prescribed time, step by step to the municipal (district) level people's government housing and urban and rural construction departments, the construction unit submitted quality accident report includes: 1. The time, place and name of the project where the accident occurred; 2. a brief history of the accident, no casualties, 3. measures taken after the accident and accident control situation; 4. Accident reporting unit. Roof grid adopts Q390GJ steel, because the steel structure production unit uses this material for the first time, before construction, the supervision engineer requires the first use of Q390GJ steel and related joint forms, welding process parameters, preheating and post-heat measures and other welding parameter combination conditions for welding process assessment. The filling wall masonry is made of single row hole light aggregate concrete small block, special small block mortar construction. It is found in the on-site inspection that: after the product period of the small block enters the field reaches 21d, it starts watering and wetting. After the surface of the small block is floating, the construction begins: When masonry, the bottom side of the small block is laid on the wall, the lap length of the small block is 1/3 of the length of the block, and the requirements of the mortar fullness of the masonry are: more than 90% of the horizontal ash joint and more than 85% of the vertical ash joint; The masonry height of the wall is 1.5m every day, and the top masonry construction will be carried out after 7d of construction of the filling wall. For the convenience of construction, temporary construction holes with a net width of 1.2m are left on some walls. The supervision engineer requires rectification of the errors. | 55、监理工程师同意地下室顶板拆模是否正确？背景资料中地下室顶板预应力梁拆除底模及支架的前置条件有哪些？ | 55. Is it correct for the supervising engineer to agree to remove the mold from the basement roof? 3. What are the preconditions for removing the bottom mold and support of the prestressed beam on the basement roof in the background information?
CBQ-056 | 56、某新建体育馆工程，建筑面积约23000m2，现浇钢筋混凝土结构，钢结构网架屋盖，地下一层，地上四层，地下室顶板设计有后张法预应力混凝土梁。 地下室顶板同条件养护试件强度达到设计要求时，施工单位现场生产经理立即向监理工程师口头申请拆除地下室顶板模板，监理工程师同意后，现场将地下室顶板及支架全部拆除。“两年专项治理行动”检查时，二层混凝土结构经回弹-取芯法检验，其强度不满足设计要求，经设计单位验算，需对二层结构进行加固处理，造成直接经济损失300余万元，工程质量事故发生后，现场有关人员立即向本单位负责人报告，并在规定的时间内逐级上报至市（设区）级人民政府住房和城乡建设主管部门，施工单位提交的质量事故报告内容包括：1.事故发生的时间、地点、工程项目名称；2.事故发生的简要经过，无伤亡，3.事故发生后采取的措施及事故控制情况；4.事故报告单位。屋盖网架采用Q390GJ钢，因钢结构制作单位首次采用该材料，施工前，监理工程师要求其对首次采用的Q390GJ钢及相关的接头形式、焊接工艺参数、预热和后热措施等焊接参数组合条件进行焊接工艺评定。填充墙砌体采用单排孔轻骨料混凝土小砌块，专用小彻块砂浆建筑，现场检查中发现：进场的小砌块产品期达到21d后，即开始浇水湿润，待小砌块表面现浮水后，开始彻筑施工：砌筑时将小砌块的底面朝上反砌于墙上，小砌块的搭接长度为块体长度的1/3，砌体的砂浆饱满度要求为：水平灰缝90％以上，竖向灰缝85％以上；墙体每天砌筑高度为1.5m，填充墙彻筑7d后进行顶砌施工，为施工方便，在部分墙体上留置了净宽度为1.2m的临时施工洞口，监理工程师要求对错误之处进行整改。 | 56. A new gymnasium project, construction area of about 23000m2, cast-in reinforced concrete structure, steel structure grid roof, one underground layer, four above-ground layers, the roof of the basement is designed with post-tensioned prestressed concrete beams. When the strength of the basement roof under the same conditions reaches the design requirements, the site production manager of the construction unit immediately applies orally to the supervision engineer for the removal of the basement roof template, and after the supervision engineer agrees, the basement roof and support will be removed on site. "Two years of special treatment action" inspection, the two-storey concrete structure after the rebound - coring method test, its strength does not meet the design requirements, the design unit check, need to strengthen the two-storey structure, resulting in direct economic losses of more than 3 million yuan, after the project quality accident, the site personnel immediately report to the person in charge of the unit. And in the prescribed time, step by step to the municipal (district) level people's government housing and urban and rural construction departments, the construction unit submitted quality accident report includes: 1. The time, place and name of the project where the accident occurred; 2. a brief history of the accident, no casualties, 3. measures taken after the accident and accident control situation; 4. Accident reporting unit. Roof grid adopts Q390GJ steel, because the steel structure production unit uses this material for the first time, before construction, the supervision engineer requires the first use of Q390GJ steel and related joint forms, welding process parameters, preheating and post-heat measures and other welding parameter combination conditions for welding process assessment. The filling wall masonry is made of single row hole light aggregate concrete small block, special small block mortar construction. It is found in the on-site inspection that: after the product period of the small block enters the field reaches 21d, it starts watering and wetting. After the surface of the small block is floating, the construction begins: When masonry, the bottom side of the small block is laid on the wall, the lap length of the small block is 1/3 of the length of the block, and the requirements of the mortar fullness of the masonry are: more than 90% of the horizontal ash joint and more than 85% of the vertical ash joint; The masonry height of the wall is 1.5m every day, and the top masonry construction will be carried out after 7d of construction of the filling wall. For the convenience of construction, temporary construction holes with a net width of 1.2m are left on some walls. The supervision engineer requires rectification of the errors. | 56、案例中的质量事故属于哪个等级？指出事故上报的不妥之处，质量事故报告还应包括哪些内容？ | 56. What is the grade of the quality accident in this case? 4. Point out the inadequacies of the accident report and what else should be included in the quality accident report?
CBQ-057 | 57、某综合办公楼工程，地下三层，地上二十层，总建筑面积68000㎡，地基基础设计等级为甲级，灌注桩筏板基础，现浇钢筋混凝土框架剪力墙结构，建设单位与施工单位按照《建设工程施工合同（示范文本）》（GF-2013-0201）签订了施工合同。约定竣工时需向建设单位移交变形测量报告。部分主要材料由建设单位采购提供，施工单位委托第三方测量单位进行施工阶段的建筑变形测量。基础桩设计直径800mm，长度35m~42m,混凝土强度等级C30共计900根，施工单位编制的桩基础施工方案中列明：采用泥浆护壁成孔，导管法水下灌注C30混凝土，灌注时桩顶混凝土面超过设计标高500mm，每根留置1组混凝土试件；成桩后按总桩数20%对桩身质量进行检验，监理工程师审查时认为方案存在错误，要求施工单位改正后重新上报。地下结构施工过程中，测量单位按变形测量方案实施监测时，发现基坑周边地表出现明显裂缝，立即将词异常情况报告给施工单位。施工单位立即要求测量单位及时采取相应监测措施，并根据观测数据指定了后续防控对策。建设单位采购的材料进场复验结果不合格。监理工程师要求退场；因停工待料导致窝工，施工单位提出8万元费用索赔。材料重新进场施工完毕后，监理验收通过；由于该部位的特殊性，建设单位要求进行剥离检验，检验结果符合要求；剥离检验及恢复共发生费用4万元，施工单位提出4万元费用索赔，上述索赔均在要求时限内提出，数据经监理工程师核实无误。 | 57. A comprehensive office building project, three underground floors, twenty floors on the ground, a total construction area of 68000 square meters, the foundation design grade is A grade, cast-in-place pile raft foundation, cast-in-place reinforced concrete frame shear wall structure, the construction unit and the construction unit in accordance with the "construction Contract (Demonstration text)" (GF-2013-0201) signed the construction contract. It is agreed that the deformation measurement report should be handed over to the construction unit at the time of completion. Part of the main materials shall be purchased and provided by the construction unit, and the construction unit shall entrust a third-party surveying unit to carry out deformation measurement of the building during the construction phase. The design diameter of the foundation pile is 800mm, the length is 35m~42m, and the concrete strength level of C30 is 900. The construction plan of the pile foundation prepared by the construction unit lists: using mud wall to form holes, underwater pouring of C30 concrete by conduit method, and the concrete surface of the top of the pile exceeds the design elevation by 500mm, and 1 group of concrete specimens are left in each pile; After the pile is formed, the quality of the pile body is tested according to 20% of the total number of piles. The supervision engineer thinks that there are mistakes in the scheme when reviewing, and requires the construction unit to correct and report again. In the process of underground structure construction, when the measuring unit monitors according to the deformation measurement plan, it finds obvious cracks on the surface around the foundation pit, and immediately reports the abnormal situation to the construction unit. The construction unit immediately requires the surveying unit to take corresponding monitoring measures in a timely manner, and assigns follow-up prevention and control countermeasures according to the observed data. The re-inspection results of the materials purchased by the construction unit were unqualified. The supervising engineer asked to leave the site; The construction unit made a claim for 80,000 yuan of expenses due to idle work. After the re-entry of materials and completion of construction, the supervision acceptance passed; Due to the particularity of this part, the construction unit requires stripping inspection, and the inspection results meet the requirements; The stripping inspection and restoration cost 40,000 yuan, the construction unit put forward 40,000 yuan cost claims, the claims are within the required time limit, the data verified by the supervision engineer is correct. | 57、指出桩基础施工方案中的错误之处，并分别写出相应的正确做法。 | 57. Point out the mistakes in the pile foundation construction scheme, and write out the corresponding correct practices.
CBQ-058 | 58、某综合办公楼工程，地下三层，地上二十层，总建筑面积68000㎡，地基基础设计等级为甲级，灌注桩筏板基础，现浇钢筋混凝土框架剪力墙结构，建设单位与施工单位按照《建设工程施工合同（示范文本）》（GF-2013-0201）签订了施工合同。约定竣工时需向建设单位移交变形测量报告。部分主要材料由建设单位采购提供，施工单位委托第三方测量单位进行施工阶段的建筑变形测量。基础桩设计直径800mm，长度35m~42m,混凝土强度等级C30共计900根，施工单位编制的桩基础施工方案中列明：采用泥浆护壁成孔，导管法水下灌注C30混凝土，灌注时桩顶混凝土面超过设计标高500mm，每根留置1组混凝土试件；成桩后按总桩数20%对桩身质量进行检验，监理工程师审查时认为方案存在错误，要求施工单位改正后重新上报。地下结构施工过程中，测量单位按变形测量方案实施监测时，发现基坑周边地表出现明显裂缝，立即将词异常情况报告给施工单位。施工单位立即要求测量单位及时采取相应监测措施，并根据观测数据指定了后续防控对策。建设单位采购的材料进场复验结果不合格。监理工程师要求退场；因停工待料导致窝工，施工单位提出8万元费用索赔。材料重新进场施工完毕后，监理验收通过；由于该部位的特殊性，建设单位要求进行剥离检验，检验结果符合要求；剥离检验及恢复共发生费用4万元，施工单位提出4万元费用索赔，上述索赔均在要求时限内提出，数据经监理工程师核实无误。 | 58. A comprehensive office building project, three underground floors, twenty floors on the ground, a total construction area of 68000 square meters, the foundation design grade is A grade, cast-in-place pile raft foundation, cast-in-place reinforced concrete frame shear wall structure, the construction unit and the construction unit in accordance with the "construction Contract (Demonstration text)" (GF-2013-0201) signed the construction contract. It is agreed that the deformation measurement report should be handed over to the construction unit at the time of completion. Part of the main materials shall be purchased and provided by the construction unit, and the construction unit shall entrust a third-party surveying unit to carry out deformation measurement of the building during the construction phase. The design diameter of the foundation pile is 800mm, the length is 35m~42m, and the concrete strength level of C30 is 900. The construction plan of the pile foundation prepared by the construction unit lists: using mud wall to form holes, underwater pouring of C30 concrete by conduit method, and the concrete surface of the top of the pile exceeds the design elevation by 500mm, and 1 group of concrete specimens are left in each pile; After the pile is formed, the quality of the pile body is tested according to 20% of the total number of piles. The supervision engineer thinks that there are mistakes in the scheme when reviewing, and requires the construction unit to correct and report again. In the process of underground structure construction, when the measuring unit monitors according to the deformation measurement plan, it finds obvious cracks on the surface around the foundation pit, and immediately reports the abnormal situation to the construction unit. The construction unit immediately requires the surveying unit to take corresponding monitoring measures in a timely manner, and assigns follow-up prevention and control countermeasures according to the observed data. The re-inspection results of the materials purchased by the construction unit were unqualified. The supervising engineer asked to leave the site; The construction unit made a claim for 80,000 yuan of expenses due to idle work. After the re-entry of materials and completion of construction, the supervision acceptance passed; Due to the particularity of this part, the construction unit requires stripping inspection, and the inspection results meet the requirements; The stripping inspection and restoration cost 40,000 yuan, the construction unit put forward 40,000 yuan cost claims, the claims are within the required time limit, the data verified by the supervision engineer is correct. | 58、分别判断施工单位提出的两项费用索赔是否成立，并写出相应理由？ | 58. Judge whether the two expense claims put forward by the construction unit are established, and write out the corresponding reasons.
CBQ-059 | 59、某新建高层住宅项目，地下1层，地上20层，建筑面积18000m2，施工承建总承包项目部进场组织施工。项目部提出了现场文明施工管理做到围挡、大门、标牌标准化，材料码放整齐化等“六化”的基本要求。施工现场大门处设置了包括工程概况牌、管理人员名单及监督电话牌、施工现场总平面图等“五牌一图”。公司主管部门检查了临时用电安全技术档案，内容包括了用电组织设计资料，电气设备试、检验凭单和调试记录，接地电阻、绝缘电阻和漏电保护器漏电动作参数测定记录表等。同时指出了以下问题：土建工程师编制临时用电组织设计；总配电箱设置在用电设备相对集中区域的中心地带；开关箱内装配总漏电保护器，由编制人和使用单位进行验收。悬挑脚手架搭设到设计高度后，监理工程师组织总承包单位技术负责人(委派技术人员)，项目负责人等相关人员进行验收。验收内容包括技术资料(专项施工方案、产品合格证、检查记录)等。 | 59. A new high-rise residential project, 1 underground, 20 floors above the ground, construction area of 18000m2, the construction contractor general contracting project department came to organize the construction. The project department put forward the basic requirements of "six modernization" in civilized construction management of the site, such as standardization of enclosures, gates, signs, and orderly placement of materials. The gate of the construction site is set up including the project overview card, the list of management personnel and the supervision telephone card, the general plan of the construction site and other "five cards and one map". The competent department of the company checked the temporary power safety technical files, including the power organization design data, electrical equipment test, inspection vouchers and debugging records, grounding resistance, insulation resistance and leakage protection device leakage action parameter measurement record table. At the same time, the following problems are pointed out: civil engineers to prepare temporary electricity organization design; The main distribution box is set in the central area of the relatively concentrated area of electrical equipment; The switch box is equipped with a total leakage protector, which is accepted by the preparation and use unit. After the cantilever scaffold is set up to the design height, the supervision engineer shall organize the technical person in charge of the general contractor unit (assign technical personnel), the project person in charge and other relevant personnel to carry out acceptance. Acceptance includes technical data (special construction scheme, product certificate, inspection record). | 59、现场文明施工管理“六化”中安全设施、生活设施、职工行为、工作生活的基本要求是什么?"五牌一图"的内容还有哪些? | 59. What are the basic requirements of safety facilities, living facilities, employee behavior and work life in the "six modernizations" of site civilized construction management? What else is the content of "five cards and one map"?
CBQ-060 | 60、某新建高层住宅项目，地下1层，地上20层，建筑面积18000m2，施工承建总承包项目部进场组织施工。项目部提出了现场文明施工管理做到围挡、大门、标牌标准化，材料码放整齐化等“六化”的基本要求。施工现场大门处设置了包括工程概况牌、管理人员名单及监督电话牌、施工现场总平面图等“五牌一图”。公司主管部门检查了临时用电安全技术档案，内容包括了用电组织设计资料，电气设备试、检验凭单和调试记录，接地电阻、绝缘电阻和漏电保护器漏电动作参数测定记录表等。同时指出了以下问题：土建工程师编制临时用电组织设计；总配电箱设置在用电设备相对集中区域的中心地带；开关箱内装配总漏电保护器，由编制人和使用单位进行验收。悬挑脚手架搭设到设计高度后，监理工程师组织总承包单位技术负责人(委派技术人员)，项目负责人等相关人员进行验收。验收内容包括技术资料(专项施工方案、产品合格证、检查记录)等。 | 60. A new high-rise residential project, 1 underground, 20 floors above the ground, construction area of 18000m2, the construction contractor general contracting project department came to organize the construction. The project department put forward the basic requirements of "six modernization" in civilized construction management of the site, such as standardization of enclosures, gates, signs, and orderly placement of materials. The gate of the construction site is set up including the project overview card, the list of management personnel and the supervision telephone card, the general plan of the construction site and other "five cards and one map". The competent department of the company checked the temporary power safety technical files, including the power organization design data, electrical equipment test, inspection vouchers and debugging records, grounding resistance, insulation resistance and leakage protection device leakage action parameter measurement record table. At the same time, the following problems are pointed out: civil engineers to prepare temporary electricity organization design; The main distribution box is set in the central area of the relatively concentrated area of electrical equipment; The switch box is equipped with a total leakage protector, which is accepted by the preparation and use unit. After the cantilever scaffold is set up to the design height, the supervision engineer shall organize the technical person in charge of the general contractor unit (assign technical personnel), the project person in charge and other relevant personnel to carry out acceptance. Acceptance includes technical data (special construction scheme, product certificate, inspection record). | 60、改正临时用电管理中的错误做法，临时用电安全技术档案的内容还有哪些? | 60. Correct the wrong practice in temporary electricity management, temporary electricity safety technology files what else?
CBQ-061 | 61、某国有资金投资的项目，采用工程量清单公开招标，规定了最高限价，要求工程清单的项目编码等内容必须与招标人提供的内容保持一致。合同工期190天。招标人使用《建设工程施工合同(示范文本)》时，对认为不适用本项目的通用条款进行了删减。竣工结算约定：风险费用包含在综合单价中全部风险由施工单位承担。工程量按实结算，但竣工结算款总额不得高于招标最高限价。投标人A等共八家单位参加了投标。投标人A针对2万㎡的模板工程，提出了两种可行方案，依据价值工程(V=F/C)进行比选。方案一的成本为146万元，功能系数为0.54。方案二的成本为139万元，功能系数为0.46。投标人F在投标报价中降低了部分清单项目的综合单价和措施项目费中的二次搬运费，将招标清单中材料暂估价下调3%。 | 61. For a project invested by a certain state-owned capital, the project quantity list shall be used for public bidding, which stipulates the maximum price and requires the project code and other contents of the project list to be consistent with those provided by the tenderee. The duration of the contract is 190 days. When the tenderer uses the Construction Contract of Construction Project (Model Text), he has deleted the general clauses that are not applicable to the project. Completion settlement agreement: The risk cost is included in the comprehensive unit price. All risks shall be borne by the construction unit. The amount of the project shall be settled according to the actual settlement, but the total settlement amount shall not be higher than the maximum bidding price. A total of eight units including Bidder A participated in the bidding. Bidder A proposed two feasible plans for the 20,000-square-meter formwork project and compared them according to value engineering (V=F/C). The cost of scheme one is 1.46 million yuan, and the function coefficient is 0.54. The cost of Plan 2 is 1.39 million yuan with a functional coefficient of 0.46. Tenderer F reduced the comprehensive unit price of part of the list items and the secondary handling fee of the measure project fee in the bid quotation, and lowered the provisional estimate of the materials in the bidding list by 3%. | 61、指出招标人在招投标过程中的不妥之处，分别说明理由。 | 61. Point out the inadequacies of the tenderer in the bidding process, and explain the reasons respectively.
CBQ-062 | 62、某国有资金投资的项目，采用工程量清单公开招标，规定了最高限价，要求工程清单的项目编码等内容必须与招标人提供的内容保持一致。合同工期190天。招标人使用《建设工程施工合同(示范文本)》时，对认为不适用本项目的通用条款进行了删减。竣工结算约定：风险费用包含在综合单价中全部风险由施工单位承担。工程量按实结算，但竣工结算款总额不得高于招标最高限价。投标人A等共八家单位参加了投标。投标人A针对2万㎡的模板工程，提出了两种可行方案，依据价值工程(V=F/C)进行比选。方案一的成本为146万元，功能系数为0.54。方案二的成本为139万元，功能系数为0.46。投标人F在投标报价中降低了部分清单项目的综合单价和措施项目费中的二次搬运费，将招标清单中材料暂估价下调3%。 | 62. For a project invested by a certain state-owned capital, the project quantity list shall be used for public bidding, which stipulates the maximum price and requires the project code and other contents of the project list to be consistent with those provided by the tenderee. The duration of the contract is 190 days. When the tenderer uses the Construction Contract of Construction Project (Model Text), he has deleted the general clauses that are not applicable to the project. Completion settlement agreement: The risk cost is included in the comprehensive unit price. All risks shall be borne by the construction unit. The amount of the project shall be settled according to the actual settlement, but the total settlement amount shall not be higher than the maximum bidding price. A total of eight units including Bidder A participated in the bidding. Bidder A proposed two feasible plans for the 20,000-square-meter formwork project and compared them according to value engineering (V=F/C). The cost of scheme one is 1.46 million yuan, and the function coefficient is 0.54. The cost of Plan 2 is 1.39 million yuan with a functional coefficient of 0.46. Tenderer F reduced the comprehensive unit price of part of the list items and the secondary handling fee of the measure project fee in the bid quotation, and lowered the provisional estimate of the materials in the bidding list by 3%. | 62、指出投标人F的做法不妥之处，说明理由。投标人填报的工程量清单中的哪些内容需要与招标文件保持一致? | 62. Point out the inadequacies of tenderer F's practices and explain the reasons. What contents of the bill of quantities completed by the bidder should be consistent with the bidding documents?
CBQ-063 | 63、甲公司投资建造一座太阳能电池厂，工程包括：1个厂房及附属设施、1栋办公楼、2栋宿舍楼。甲公司按工程量清单计价规范进行了公开招标，乙公司中标，合同价2800万元。双方合同约定，甲公司合同价的10%向乙公司支付工程预付款，乙公司向甲公司提供预付款保函。签订合同后，乙公司向甲公司提交了预付款支付申请，甲公司核实后于2020年3月1日向乙公司发出工程预付款支付证书，并于2020年3月21日向乙公司支付了预付款。乙公司以合同价为基数，以2%目标利润率预测目标成本，并向工程直接成本和间接成本进行成本分解。乙公司在施工过程中由于资金困难，自行决定将2栋宿舍楼全部交给具有相应资质的丙公司施工，仅收取10%的管理费。甲公司与乙公司合同约定竣工时间为2021年5月20日，每延期竣工1天，乙公司向甲公司支付2万元的工期违约金。2021年5月20日工程竣工验收时，发现宿舍楼存在质量问题，需要修复后才能使用，因工程修复于2021年6月20日通过了甲公司组织的竣工验收。 | 63. Company A invested in the construction of a solar cell factory, including: 1 workshop and ancillary facilities, 1 office building, 2 dormitories. Company A conducted the public bidding according to the bill of quantities valuation standard, and Company B won the contract price of 28 million yuan. According to the contract, Company A shall pay 10% of the contract price as advance payment to Company B, and Company B shall provide advance payment guarantee to Company A. After signing the contract, Company B submitted the application for advance payment to Company A. After verification, Company A issued the certificate of advance payment to Company B on March 1, 2020, and paid the advance payment to Company B on March 21, 2020. Based on the contract price, Company B predicted the target cost with the target profit rate of 2%, and decomposed the cost into the direct cost and indirect cost of the project. Due to financial difficulties during the construction process, Company B decided to entrust all the 2 dormitory buildings to Company C with corresponding qualifications for construction, and only charged 10% management fee. According to the contract between Company A and Company B, the completion date is May 20, 2021. For each day of delay in completion, Company B shall pay Company A liquidated damages of 20,000 Yuan for the construction period. When the project was completed and accepted on May 20, 2021, it was found that there were quality problems in the dormitory building, which needed to be repaired before it could be used, because the project restoration passed the completion acceptance organized by Company A on June 20, 2021. | 63、甲公司签发工程预付款支付证书后向乙公司支付预付款的最后期限是什么时间？ | 63. What is the deadline for Company A to pay the advance payment to Company B after Company A issues the project advance payment certificate?
CBQ-064 | 64、甲公司投资建造一座太阳能电池厂，工程包括：1个厂房及附属设施、1栋办公楼、2栋宿舍楼。甲公司按工程量清单计价规范进行了公开招标，乙公司中标，合同价2800万元。双方合同约定，甲公司合同价的10%向乙公司支付工程预付款，乙公司向甲公司提供预付款保函。签订合同后，乙公司向甲公司提交了预付款支付申请，甲公司核实后于2020年3月1日向乙公司发出工程预付款支付证书，并于2020年3月21日向乙公司支付了预付款。乙公司以合同价为基数，以2%目标利润率预测目标成本，并向工程直接成本和间接成本进行成本分解。乙公司在施工过程中由于资金困难，自行决定将2栋宿舍楼全部交给具有相应资质的丙公司施工，仅收取10%的管理费。甲公司与乙公司合同约定竣工时间为2021年5月20日，每延期竣工1天，乙公司向甲公司支付2万元的工期违约金。2021年5月20日工程竣工验收时，发现宿舍楼存在质量问题，需要修复后才能使用，因工程修复于2021年6月20日通过了甲公司组织的竣工验收。 | 64. Company A invested in the construction of a solar cell factory, including: 1 workshop and ancillary facilities, 1 office building, 2 dormitories. Company A conducted the public bidding according to the bill of quantities valuation standard, and Company B won the contract price of 28 million yuan. According to the contract, Company A shall pay 10% of the contract price as advance payment to Company B, and Company B shall provide advance payment guarantee to Company A. After signing the contract, Company B submitted the application for advance payment to Company A. After verification, Company A issued the certificate of advance payment to Company B on March 1, 2020, and paid the advance payment to Company B on March 21, 2020. Based on the contract price, Company B predicted the target cost with the target profit rate of 2%, and decomposed the cost into the direct cost and indirect cost of the project. Due to financial difficulties during the construction process, Company B decided to entrust all the 2 dormitory buildings to Company C with corresponding qualifications for construction, and only charged 10% management fee. According to the contract between Company A and Company B, the completion date is May 20, 2021. For each day of delay in completion, Company B shall pay Company A liquidated damages of 20,000 Yuan for the construction period. When the project was completed and accepted on May 20, 2021, it was found that there were quality problems in the dormitory building, which needed to be repaired before it could be used, because the project restoration passed the completion acceptance organized by Company A on June 20, 2021. | 64、乙公司向丙公司做法属于什么行为？说明理由。 | 64. What is the behavior of Company B to Company C? State the reason.
CBQ-065 | 65、某新建住宅工程，地上18层，首层为非标准层，结构现浇，工期8天。2层~18层为标准层，采用装配式结构体系。其中，墙体以预制墙板为主，楼板以预制叠合板为主。所有构件通过塔吊吊装。经验收合格的预制构件按计划要求分批进场，构件生产单位向施工单位提供了相关质量证明文件。某A型预制叠合板，进场后在指定区域按不超过6层码放。最下层直接放在通长型钢支垫上，其它层与层之间使用垫木。垫木距板端300mm，间距1800mm。预制叠合板安装工艺包含：①测量放线；②支撑架体搭设；③叠合板起吊；④位置、标高确认；⑤叠合板落位；⑥支撑架体调节；⑦摘钩。存放区靠放于专用支架的某B型预制外墙板，与地面倾斜角度为60°。即将起吊时突遇6级大风及大雨，施工人员立即停止作业，塔吊吊钩仍挂在外墙板预埋吊环上。风雨过后，施工人员直接将该预制外墙板吊至所在楼层，利用外轮廓线控制就位后，设置2道可调斜撑临时固定。验收合格后进行叠合层和叠合板接缝处混凝土浇筑。 | 65. A new residential project has 18 floors on the ground, the first floor is a non-standard layer, the structure is cast in situ, and the construction period is 8 days. 2 ~18 layers for the standard layer, the use of prefabricated structure system. Among them, the wall is mainly prefabricated wall board, and the floor is mainly prefabricated laminated board. All the components are hoisted by tower crane. The qualified prefabricated components entered the site in batches according to the requirements as planned, and the component production unit provided the relevant quality certification documents to the construction unit. A type A prefabricated laminated board shall be placed in no more than 6 layers in the designated area after entering the site. The lowest layer is directly placed on the full-length steel support pad, and the other layers are interlayer with the cushion wood. The cushion wood is 300mm away from the end of the plate, and the spacing is 1800mm. The installation process of prefabricated laminated board includes: ① measurement and pay-off; ② erection of support frame body; ③ the composite board lifting; ④ Position and elevation confirmation; ⑤ position of composite plate; ⑥ support frame body adjustment; ⑦ Pick the hook. The storage area depends on a B-type prefabricated outer wall panel placed on a special bracket, and the tilt Angle with the ground is 60°. When the crane is about to be lifted, the construction personnel will immediately stop the operation, and the tower crane hook is still hung on the embedded hanging ring of the outer wall panel. After the wind and rain, the construction personnel will directly lift the prefabricated wall panel to the floor where it is located, and after it is controlled by the external contour line, two adjustable diagonal braces will be set for temporary fixation. After acceptance, concrete pouring is carried out at the joint of the laminated layer and the laminated board. | 65、针对A型预制叠合板码放的不妥之处，写出正确做法。 | 65. Write the correct practice for the improper place of type A prefabricated laminated board.
CBQ-066 | 66、某新建住宅工程，地上18层，首层为非标准层，结构现浇，工期8天。2层~18层为标准层，采用装配式结构体系。其中，墙体以预制墙板为主，楼板以预制叠合板为主。所有构件通过塔吊吊装。经验收合格的预制构件按计划要求分批进场，构件生产单位向施工单位提供了相关质量证明文件。某A型预制叠合板，进场后在指定区域按不超过6层码放。最下层直接放在通长型钢支垫上，其它层与层之间使用垫木。垫木距板端300mm，间距1800mm。预制叠合板安装工艺包含：①测量放线；②支撑架体搭设；③叠合板起吊；④位置、标高确认；⑤叠合板落位；⑥支撑架体调节；⑦摘钩。存放区靠放于专用支架的某B型预制外墙板，与地面倾斜角度为60°。即将起吊时突遇6级大风及大雨，施工人员立即停止作业，塔吊吊钩仍挂在外墙板预埋吊环上。风雨过后，施工人员直接将该预制外墙板吊至所在楼层，利用外轮廓线控制就位后，设置2道可调斜撑临时固定。验收合格后进行叠合层和叠合板接缝处混凝土浇筑。 | 66. A new residential project has 18 floors on the ground, the first floor is a non-standard layer, the structure is cast in situ, and the construction period is 8 days. 2 ~18 layers for the standard layer, the use of prefabricated structure system. Among them, the wall is mainly prefabricated wall board, and the floor is mainly prefabricated laminated board. All the components are hoisted by tower crane. The qualified prefabricated components entered the site in batches according to the requirements as planned, and the component production unit provided the relevant quality certification documents to the construction unit. A type A prefabricated laminated board shall be placed in no more than 6 layers in the designated area after entering the site. The lowest layer is directly placed on the full-length steel support pad, and the other layers are interlayer with the cushion wood. The cushion wood is 300mm away from the end of the plate, and the spacing is 1800mm. The installation process of prefabricated laminated board includes: ① measurement and pay-off; ② erection of support frame body; ③ the composite board lifting; ④ Position and elevation confirmation; ⑤ position of composite plate; ⑥ support frame body adjustment; ⑦ Pick the hook. The storage area depends on a B-type prefabricated outer wall panel placed on a special bracket, and the tilt Angle with the ground is 60°. When the crane is about to be lifted, the construction personnel will immediately stop the operation, and the tower crane hook is still hung on the embedded hanging ring of the outer wall panel. After the wind and rain, the construction personnel will directly lift the prefabricated wall panel to the floor where it is located, and after it is controlled by the external contour line, two adjustable diagonal braces will be set for temporary fixation. After acceptance, concrete pouring is carried out at the joint of the laminated layer and the laminated board. | 66、针对B型预制外墙板在靠放和吊装过程中的不妥之处，写出正确做法。 | 66. In view of the improper place of type B prefabricated outer wall board in the process of placing and lifting, write the correct way.
CBQ-067 | 67、某体能训练场馆工程，建筑面积3300㎡，建筑物长72m，宽45m，地上一层，钢筋混凝土框架结构，屋面采用球形网架结构。框架柱、梁均沿建筑物四周设置，框架柱轴线间距9000mm，框架梁截面尺寸450mm×900mm，梁底标高9.6m。现场配置一部塔吊和一台汽车吊进行材料的水平与垂直运输。本工程框架梁模板支撑体系高度9.6m，属于超过一定规模危险性较大的分部分项工程。施工单位编制了超过一定规模危险性较大的模板工程专项施工方案。建设单位组织召开了超过一定规模危险性较大的模板工程专项施工方案专家论证会，设计单位项目技术负责人以专家身份参会。施工方案中，采用扣件式钢管支撑体系，框架梁模板支撑架立杆下垫设页岩砖；扫地杆距地面250mm；架体顶层步距1500mm；梁底支撑架立杆均采用下部一根6m定尺钢管与上部一根定尺短钢管搭接连接。项目部针对工程特点，进行了重大危险源的辨识，编制了专项应急救援预案。项目部编制了绿色施工方案，确定了“四节一环保”的目标和措施。 | 67. A physical training venue project, construction area of 3300 square meters, building length of 72m, width of 45m, one layer on the ground, reinforced concrete frame structure, the roof using spherical grid structure. Frame column, beam are set around the building, frame column axis spacing 9000mm, frame beam section size 450mm×900mm, beam bottom elevation 9.6m. The site is equipped with a tower crane and a truck crane for horizontal and vertical transportation of materials. This project frame beam formwork support system height 9.6m, belongs to more than a certain scale of greater risk of the division of the project. The construction unit has prepared a special construction plan for the formwork project which is more dangerous than a certain scale. The construction unit organized and held the expert demonstration meeting of the formwork project special construction scheme with greater risk beyond a certain scale, and the project technical leader of the design unit attended the meeting as an expert. In the construction scheme, the fastening-type steel pipe support system is adopted, and the frame beam template support bracket is set up under the paginate rock bricks; Sweeping rod 250mm from the ground; The top step of the frame 1500mm; The bottom of the beam support frame is connected by a 6m fixed length steel pipe at the bottom and a fixed length short steel pipe at the top. According to the characteristics of the project, the project department has identified the major hazard sources and prepared a special emergency rescue plan. The project department has prepared the green construction plan and determined the goals and measures of "four sections and one environmental protection". | 67、根据重大危险源辨识，本工程专项应急救援预案中包括哪几项主要内容？ | 67. According to the identification of major hazard sources, which main contents are included in the special emergency rescue plan of this project?
CBQ-068 | 68、某体能训练场馆工程，建筑面积3300㎡，建筑物长72m，宽45m，地上一层，钢筋混凝土框架结构，屋面采用球形网架结构。框架柱、梁均沿建筑物四周设置，框架柱轴线间距9000mm，框架梁截面尺寸450mm×900mm，梁底标高9.6m。现场配置一部塔吊和一台汽车吊进行材料的水平与垂直运输。本工程框架梁模板支撑体系高度9.6m，属于超过一定规模危险性较大的分部分项工程。施工单位编制了超过一定规模危险性较大的模板工程专项施工方案。建设单位组织召开了超过一定规模危险性较大的模板工程专项施工方案专家论证会，设计单位项目技术负责人以专家身份参会。施工方案中，采用扣件式钢管支撑体系，框架梁模板支撑架立杆下垫设页岩砖；扫地杆距地面250mm；架体顶层步距1500mm；梁底支撑架立杆均采用下部一根6m定尺钢管与上部一根定尺短钢管搭接连接。项目部针对工程特点，进行了重大危险源的辨识，编制了专项应急救援预案。项目部编制了绿色施工方案，确定了“四节一环保”的目标和措施。 | 68. A physical training venue project, construction area of 3300 square meters, building length of 72m, width of 45m, one layer on the ground, reinforced concrete frame structure, the roof using spherical grid structure. Frame column, beam are set around the building, frame column axis spacing 9000mm, frame beam section size 450mm×900mm, beam bottom elevation 9.6m. The site is equipped with a tower crane and a truck crane for horizontal and vertical transportation of materials. This project frame beam formwork support system height 9.6m, belongs to more than a certain scale of greater risk of the division of the project. The construction unit has prepared a special construction plan for the formwork project which is more dangerous than a certain scale. The construction unit organized and held the expert demonstration meeting of the formwork project special construction scheme with greater risk beyond a certain scale, and the project technical leader of the design unit attended the meeting as an expert. In the construction scheme, the fastening-type steel pipe support system is adopted, and the frame beam template support bracket is set up under the paginate rock bricks; Sweeping rod 250mm from the ground; The top step of the frame 1500mm; The bottom of the beam support frame is connected by a 6m fixed length steel pipe at the bottom and a fixed length short steel pipe at the top. According to the characteristics of the project, the project department has identified the major hazard sources and prepared a special emergency rescue plan. The project department has prepared the green construction plan and determined the goals and measures of "four sections and one environmental protection". | 68、在绿色施工方案中，“四节一环保”的内容是什么？ | 68. In the green construction scheme, what is the content of "four sections and one environmental protection"?
CBQ-069 | 69、某施工单位承接一栋新建物流仓库工程。钢筋混凝土框架结构，部分为钢结构，建筑层数为2层，独立基础形式，建筑面积1.1万平方米，屋面保温层为现浇泡沫混凝土，厚度为350mm。在钢结构施工中，项目部按照相关规定，要求施焊人员在施工前，对焊枪和焊条进行了烘焙。施焊过程中因工期紧迫，焊工人员不足。项目经理随即抽调现场一名持有机械管理员证书的人员参加焊工班组施焊。在屋面泡沫混凝土浇筑前，项目部向监理单位提交了浇筑专项方案，内容包括：基层清理干净，配合比设计、拌制计量准确，采取高压泵送，一次浇筑厚度300mm。保湿养护不少于3天等内容。监理单位认为所报专项方案部分内容有误，要求按相关规定修改后重报。根据现场需要，由项目技术负责人组织编写了施工现场防火安全技术方案，填写了动火申请表，交由项目经理审批。因动火当日有雨，改为次日天晴时更换动火地点继续实施。监理工程师在现场安全检查中发现，项目部在现场出入口防护棚上方，按照从左向右顺序，集中设置了多个白、黄、蓝、绿颜色背景的安全标志牌，入口地面一侧消防箱处设置有消防设施提示标志，以规范现场安全管理。 | 69. A construction unit to undertake a new logistics warehouse project. Reinforced concrete frame structure, part of the steel structure, the number of building layers is 2, the independent foundation form, the construction area of 11,000 square meters, the roof insulation layer is cast in situ foam concrete, the thickness is 350mm. In the construction of steel structure, the project department, in accordance with relevant regulations, requires the welding personnel to bake the welding gun and electrode before construction. In the welding process, due to the urgent construction period, the welding personnel is insufficient. The project manager immediately dispatched a person holding the mechanical administrator certificate to participate in the welding team welding. Before the roof foam concrete pouring, the project department submitted a special pouring plan to the supervision unit, including: clean the base, mix ratio design, accurate mixing measurement, high pressure pumping, a pouring thickness of 300mm. Moisturizing maintenance for no less than 3 days. The supervision unit believes that part of the special plan reported is wrong, and requires that it be revised and rereported according to relevant regulations. According to the site needs, the project technical leader organized the preparation of the construction site fire safety technical plan, filled in the fire application form, submitted to the project manager for approval. Because of the rain on the day of the fire, the fire site was replaced and continued to be implemented when the next day was fine. The supervision engineer found in the on-site safety inspection that the project department set a number of safety signs with white, yellow, blue and green color background above the protection shelter at the entrance and exit of the site, in accordance with the order from left to right, and the fire protection facilities prompt signs were set at the fire box on one side of the ground of the entrance to standardize the safety management of the site. | 69、机械管理员参与施焊是否正确？说明理由。 | 69. Is it correct for the mechanical administrator to participate in welding? State the reason.
CBQ-070 | 70、某施工单位承接一栋新建物流仓库工程。钢筋混凝土框架结构，部分为钢结构，建筑层数为2层，独立基础形式，建筑面积1.1万平方米，屋面保温层为现浇泡沫混凝土，厚度为350mm。在钢结构施工中，项目部按照相关规定，要求施焊人员在施工前，对焊枪和焊条进行了烘焙。施焊过程中因工期紧迫，焊工人员不足。项目经理随即抽调现场一名持有机械管理员证书的人员参加焊工班组施焊。在屋面泡沫混凝土浇筑前，项目部向监理单位提交了浇筑专项方案，内容包括：基层清理干净，配合比设计、拌制计量准确，采取高压泵送，一次浇筑厚度300mm。保湿养护不少于3天等内容。监理单位认为所报专项方案部分内容有误，要求按相关规定修改后重报。根据现场需要，由项目技术负责人组织编写了施工现场防火安全技术方案，填写了动火申请表，交由项目经理审批。因动火当日有雨，改为次日天晴时更换动火地点继续实施。监理工程师在现场安全检查中发现，项目部在现场出入口防护棚上方，按照从左向右顺序，集中设置了多个白、黄、蓝、绿颜色背景的安全标志牌，入口地面一侧消防箱处设置有消防设施提示标志，以规范现场安全管理。 | 70. A construction unit to undertake a new logistics warehouse project. Reinforced concrete frame structure, part of the steel structure, the number of building layers is 2, the independent foundation form, the construction area of 11,000 square meters, the roof insulation layer is cast in situ foam concrete, the thickness is 350mm. In the construction of steel structure, the project department, in accordance with relevant regulations, requires the welding personnel to bake the welding gun and electrode before construction. In the welding process, due to the urgent construction period, the welding personnel is insufficient. The project manager immediately dispatched a person holding the mechanical administrator certificate to participate in the welding team welding. Before the roof foam concrete pouring, the project department submitted a special pouring plan to the supervision unit, including: clean the base, mix ratio design, accurate mixing measurement, high pressure pumping, a pouring thickness of 300mm. Moisturizing maintenance for no less than 3 days. The supervision unit believes that part of the special plan reported is wrong, and requires that it be revised and rereported according to relevant regulations. According to the site needs, the project technical leader organized the preparation of the construction site fire safety technical plan, filled in the fire application form, submitted to the project manager for approval. Because of the rain on the day of the fire, the fire site was replaced and continued to be implemented when the next day was fine. The supervision engineer found in the on-site safety inspection that the project department set a number of safety signs with white, yellow, blue and green color background above the protection shelter at the entrance and exit of the site, in accordance with the order from left to right, and the fire protection facilities prompt signs were set at the fire box on one side of the ground of the entrance to standardize the safety management of the site. | 70、指出浇筑专项方案中泵送方法、浇筑厚度和养护时间的错误之处，并予以改正 | 70. Point out the mistakes of pumping method, pouring thickness and maintenance time in the special pouring scheme, and correct them
CBQ-071 | 71、某住宅工程，地下2层，地上18层，建筑面积2.4万平方米，土方开挖范围内地下水丰沛，地上2层以上为装配式混凝土结构，预制墙板主筋采用套筒灌浆连接，构件加工由建设单位和中标单位共同选定。A单位中标后按总承包管理模式组织施工。项目部编制的施工组织设计中规定：结构工程施工中，垂直运输机械，土方开挖等专业工程实行专业分包管理，专项方案由专业分包单位组织编制。项目部考虑了施工、质量控制和专业验收等实际情况，按施工段划分了检验批。一个工作班组在吊装完成一个检验批工作量后，班组长抽调其中的4人开始给预留的孔隙做灌注浆料的前期准备和后续工作；浆料从上口灌注，在压力作用下从下口流出，并及时对留出浆料部位封堵；同时制作了一组150mm×150mm×150mm的立方体试件，以验证28d后的浆料抗压强度；此时，总监理工程师巡查发现，灌浆工作没有按方案操作，对现场监理提出了批评，给施工单位下发了停工令。该楼监控室吊顶为铝合金石膏板吊顶，吊杆长度为1800mm时，为设置反向支撑。重型灯具、电扇及其他重型设备直接安装在吊顶工程的龙骨上。 | 71. A residential project, 2 floors underground, 18 floors above the ground, construction area of 24,000 square meters, the soil excavation area of the interior water is abundant, above 2 floors for the prefabricated concrete structure, the main reinforcement of the prefabricated wall board using sleeve grouting connection, component processing by the construction unit and the winning unit jointly selected. After winning the bid, Unit A will organize the construction according to the general contracting management mode. In the construction organization design prepared by the project department, it is stipulated that: in the construction of structural engineering, professional subcontracting management shall be implemented for professional projects such as vertical transportation machinery and earthmoving excavation, and special plans shall be organized and prepared by professional subcontracting units. The project department considers the actual situation of construction, quality control and professional acceptance, and divides the inspection batch according to the construction section. After a work group has completed an inspection batch workload, the team leader dispatched 4 people to the reserved pores to do the preliminary preparation and follow-up work of filling slurry; The slurry is poured from the upper mouth, and flows out from the lower mouth under the action of pressure, and the slurry parts are blocked in time; At the same time, a set of 150mm×150mm×150mm cube specimens were made to verify the compressive strength of the slurry after 28d. At this time, the chief supervision engineer found on inspection that the grouting work did not operate according to the plan, criticized the site supervision, and issued a stop order to the construction unit. The ceiling of the monitoring room of the building is the aluminum alloy gypsum board ceiling, and when the length of the boom is 1800mm, the reverse support is set. Heavy lamps, fans and other heavy equipment are directly installed on the keel of the ceiling project. | 71、指出该检验批灌浆过程中的不妥之处，并说明正确做法。 | 71. Point out the improper place in the grouting process of the inspection lot, and explain the correct method.
CBQ-072 | 72、某住宅工程，地下2层，地上18层，建筑面积2.4万平方米，土方开挖范围内地下水丰沛，地上2层以上为装配式混凝土结构，预制墙板主筋采用套筒灌浆连接，构件加工由建设单位和中标单位共同选定。A单位中标后按总承包管理模式组织施工。项目部编制的施工组织设计中规定：结构工程施工中，垂直运输机械，土方开挖等专业工程实行专业分包管理，专项方案由专业分包单位组织编制。项目部考虑了施工、质量控制和专业验收等实际情况，按施工段划分了检验批。一个工作班组在吊装完成一个检验批工作量后，班组长抽调其中的4人开始给预留的孔隙做灌注浆料的前期准备和后续工作；浆料从上口灌注，在压力作用下从下口流出，并及时对留出浆料部位封堵；同时制作了一组150mm×150mm×150mm的立方体试件，以验证28d后的浆料抗压强度；此时，总监理工程师巡查发现，灌浆工作没有按方案操作，对现场监理提出了批评，给施工单位下发了停工令。该楼监控室吊顶为铝合金石膏板吊顶，吊杆长度为1800mm时，为设置反向支撑。重型灯具、电扇及其他重型设备直接安装在吊顶工程的龙骨上。 | 72. A residential project, 2 floors underground, 18 floors above the ground, construction area of 24,000 square meters, the soil excavation area of the interior water is abundant, above 2 floors for the prefabricated concrete structure, the main reinforcement of the prefabricated wall board using sleeve grouting connection, component processing by the construction unit and the winning unit jointly selected. After winning the bid, Unit A will organize the construction according to the general contracting management mode. In the construction organization design prepared by the project department, it is stipulated that: in the construction of structural engineering, professional subcontracting management shall be implemented for professional projects such as vertical transportation machinery and earthmoving excavation, and special plans shall be organized and prepared by professional subcontracting units. The project department considers the actual situation of construction, quality control and professional acceptance, and divides the inspection batch according to the construction section. After a work group has completed an inspection batch workload, the team leader dispatched 4 people to the reserved pores to do the preliminary preparation and follow-up work of filling slurry; The slurry is poured from the upper mouth, and flows out from the lower mouth under the action of pressure, and the slurry parts are blocked in time; At the same time, a set of 150mm×150mm×150mm cube specimens were made to verify the compressive strength of the slurry after 28d. At this time, the chief supervision engineer found on inspection that the grouting work did not operate according to the plan, criticized the site supervision, and issued a stop order to the construction unit. The ceiling of the monitoring room of the building is the aluminum alloy gypsum board ceiling, and when the length of the boom is 1800mm, the reverse support is set. Heavy lamps, fans and other heavy equipment are directly installed on the keel of the ceiling project. | 72、针对该楼吊顶施工的不妥之处，写出正确做法？ | 72. According to the improper construction of the suspended ceiling of the building, write the correct method?
CBQ-073 | 73、建设单位投资兴建酒店工程，地下1层，地上5层，钢筋混凝土框架结构，顶层为钢结构，建筑面积8000平方米，总投资4500.00万元。招标文件的部分内容为：工程质量标准为合格，工期自2018年3月1日起至2019年7月30日止；采用工程量清单计价模式；每月按照完成工作量的85%支付进度款；项目履约保证金采用银行保函方式，为签约合同价的10%；工程质量保证金为结算额的5%（每月完成工作量中扣除），玻璃幕墙、室内精装修、消防由专业公司负责，当地建设主管部门认为部分条款不妥，提出改正意见。建设单位完成整改并经当地建设主管部门审核通过后，进行了公开招投标工作，某建筑总公司中标，双方签订了施工总承包合同。建筑总公司中标后，及时组建了项目部，将主体钢结构工程分包给下属具有独立法人资格的钢结构专业公司施工。钢结构专业公司将钢结构制作委托加工，将劳务作业分包给某劳务公司负责施工，并约定劳务公司负责钢管等周转材料的租赁，钢结构公司承担租赁费用，项目部按照施工总承包要求，进行了大量的总承包管理和配合工作。例如向专业分包单位提供了相关批文、证件，提供了办公及住所，统一进行了设计图纸交底、安全文明施工交底、技术质量标准交底，提供了塔吊、脚手架的使用便利，及时封堵管道洞口，对施工垃圾进行集中清运等工作。 | 73. The construction unit invests in the construction of the hotel project, with 1 floor underground and 5 floors above ground, reinforced concrete frame structure, the top floor is steel structure, construction area of 8000 square meters, with a total investment of 4500.000 yuan. Part of the bidding documents is: the project quality standard is qualified, and the construction period starts from March 1, 2018 to July 30, 2019; The valuation mode of bill of quantities shall be adopted; Pay the progress payment according to 85% of the completed work each month; The performance bond of the project shall be 10% of the contract price in the form of bank guarantee; The project quality deposit is 5% of the settlement amount (deducted from the monthly completed workload). The glass curtain wall, interior decoration and fire protection are responsible for professional companies. The local construction authorities think that some provisions are inappropriate and put forward suggestions for correction. After the construction unit completes the rectification and is approved by the local competent construction department, it carries out the public bidding work, a construction company wins the bid, and the two sides sign the general contract for construction. After the construction company won the bid, it set up the project department in time, and subcontracted the main steel structure project to the subordinate steel structure professional company with independent legal personality for construction. The specialized steel structure company commissioned the production of steel structure, subcontracted the labor work to a labor company responsible for the construction, and agreed that the labor company is responsible for the lease of steel pipe and other revolving materials, the steel structure company bears the lease costs, and the project department carried out a lot of general contracting management and cooperation work in accordance with the requirements of the construction of general contracting. For example, to the professional subcontracting units to provide the relevant approval documents, documents, office and residence, unified design drawings, safe and civilized construction disclosure, technical quality standards disclosure, to provide tower crane, scaffolding convenient use, timely plugging the hole of the pipeline, the construction of garbage for centralized cleaning and other work. | 73、指出招标文件中的不妥之处，并说明理由。 | 73. Point out the inadequacies in the bidding documents, and explain the reasons.
CBQ-074 | 74、建设单位投资兴建酒店工程，地下1层，地上5层，钢筋混凝土框架结构，顶层为钢结构，建筑面积8000平方米，总投资4500.00万元。招标文件的部分内容为：工程质量标准为合格，工期自2018年3月1日起至2019年7月30日止；采用工程量清单计价模式；每月按照完成工作量的85%支付进度款；项目履约保证金采用银行保函方式，为签约合同价的10%；工程质量保证金为结算额的5%（每月完成工作量中扣除），玻璃幕墙、室内精装修、消防由专业公司负责，当地建设主管部门认为部分条款不妥，提出改正意见。建设单位完成整改并经当地建设主管部门审核通过后，进行了公开招投标工作，某建筑总公司中标，双方签订了施工总承包合同。建筑总公司中标后，及时组建了项目部，将主体钢结构工程分包给下属具有独立法人资格的钢结构专业公司施工。钢结构专业公司将钢结构制作委托加工，将劳务作业分包给某劳务公司负责施工，并约定劳务公司负责钢管等周转材料的租赁，钢结构公司承担租赁费用，项目部按照施工总承包要求，进行了大量的总承包管理和配合工作。例如向专业分包单位提供了相关批文、证件，提供了办公及住所，统一进行了设计图纸交底、安全文明施工交底、技术质量标准交底，提供了塔吊、脚手架的使用便利，及时封堵管道洞口，对施工垃圾进行集中清运等工作。 | 74. The construction unit invests in the construction of the hotel project, with 1 floor underground and 5 floors above ground, reinforced concrete frame structure, the top floor is steel structure, construction area of 8000 square meters, with a total investment of 4500.000 yuan. Part of the bidding documents is: the project quality standard is qualified, and the construction period starts from March 1, 2018 to July 30, 2019; The valuation mode of bill of quantities shall be adopted; Pay the progress payment according to 85% of the completed work each month; The performance bond of the project shall be 10% of the contract price in the form of bank guarantee; The project quality deposit is 5% of the settlement amount (deducted from the monthly completed workload). The glass curtain wall, interior decoration and fire protection are responsible for professional companies. The local construction authorities think that some provisions are inappropriate and put forward suggestions for correction. After the construction unit completes the rectification and is approved by the local competent construction department, it carries out the public bidding work, a construction company wins the bid, and the two sides sign the general contract for construction. After the construction company won the bid, it set up the project department in time, and subcontracted the main steel structure project to the subordinate steel structure professional company with independent legal personality for construction. The specialized steel structure company commissioned the production of steel structure, subcontracted the labor work to a labor company responsible for the construction, and agreed that the labor company is responsible for the lease of steel pipe and other revolving materials, the steel structure company bears the lease costs, and the project department carried out a lot of general contracting management and cooperation work in accordance with the requirements of the construction of general contracting. For example, to the professional subcontracting units to provide the relevant approval documents, documents, office and residence, unified design drawings, safe and civilized construction disclosure, technical quality standards disclosure, to provide tower crane, scaffolding convenient use, timely plugging the hole of the pipeline, the construction of garbage for centralized cleaning and other work. | 74、指出钢结构专业公司在工程分包管理工作中的不妥之处，并说明理由。 | 74. Point out the inadequacies of the steel structure specialized company in the management of engineering subcontracting, and explain the reasons.
CBQ-075 | 75、某住宅工程，建筑面积21600㎡，基坑开挖深度6.5m，地下二层，地上十二层，筏板基础，现浇钢筋混凝土框架结构。工程场地狭小，基坑上口北侧4m处有1栋六层砖混结构住宅楼，东侧2m处有一条埋深2m的热力管线。 工程由某总承包单位施工，基坑支护由专业分包单位承担，基坑支护施工前，专业分包单位编制了基坑支护专项施工方案，分包单位技术负责人审批签字后报总承包单位备案并直接上报监理单位审查，总监理工程师审核通过。 随后分包单位组织了3名符合相关专业要求的专家及参建各方相关人员召开论证会。 主体结构施工期间，施工单位安全主管部门进行施工升降机安全专项检查，对该项目升降机的限位装置、防护设施、安装、验收与使用等保证项目进行了全数检查，均符合要求。 施工过程中，建设单位要求施工单位在3层进行了样板间施工，并对样板间室内环境污染物浓度进行检测，检测结果合格：工程交付使用前对室内环境污染物浓度检测时，施工单位以样板间已检测合格为由将抽检房间数量减半，共抽检7间，经检测甲醛浓度超标：施工单位查找原因并采取措施后对原检测的7间房间再次进行检测，检测结果合格，施工单位认为达标，监理单位提出不同意见，要求调整抽检的房间并增加抽检房间数量。 | 75. A residential project, construction area of 21600 square meters, excavation depth of 6.5m, two underground floors, twelve above-ground floors, raft foundation, cast-in-place reinforced concrete frame structure. The project site is narrow. There is a six-story brick-concrete residential building at 4m on the north side of the upper entrance of the foundation pit. There is a heat pipeline buried 2m on the east side. The project is constructed by a general contracting unit, and the foundation pit support is undertaken by a professional subcontracting unit. Before the foundation pit support construction, the professional subcontracting unit has prepared a special construction plan for foundation pit support. After the approval and signature of the technical person in charge of the subcontracting unit, it is reported to the general contracting unit for the record and directly reported to the supervision unit for review. Subsequently, the subcontracting unit organized 3 experts who met the relevant professional requirements and the relevant personnel of the participating parties to hold a demonstration meeting. During the construction of the main structure, the safety competent department of the construction unit carried out a special inspection on the safety of the construction lift, and the limiting device, protective facilities, installation, acceptance and use of the lift of the project were all inspected, which met the requirements. During the construction process, the construction unit requires the construction unit to carry out the model room construction on the third floor, and test the concentration of indoor environmental pollutants in the model room, and the test result is qualified: When the concentration of indoor environmental pollutants is tested before the project is delivered, the construction unit will halve the number of sampling rooms on the grounds that the sample room has been tested and qualified, a total of 7 were sampled, and the formaldehyde concentration exceeded the standard by detection: After the construction unit finds out the cause and takes measures, the original 7 rooms are tested again, the test results are qualified, the construction unit thinks that the standard, the supervision unit puts forward different opinions, and requires to adjust the sampling rooms and increase the number of sampling rooms. | 75、本项目基坑支护专项施工方案编制到专家论证的过程有何不妥？并说明正确做法。 | 75. What is wrong with the process from the preparation of the special construction plan of the foundation pit support to the expert demonstration? And explain the correct way.
CBQ-076 | 76、某住宅工程，建筑面积21600㎡，基坑开挖深度6.5m，地下二层，地上十二层，筏板基础，现浇钢筋混凝土框架结构。工程场地狭小，基坑上口北侧4m处有1栋六层砖混结构住宅楼，东侧2m处有一条埋深2m的热力管线。 工程由某总承包单位施工，基坑支护由专业分包单位承担，基坑支护施工前，专业分包单位编制了基坑支护专项施工方案，分包单位技术负责人审批签字后报总承包单位备案并直接上报监理单位审查，总监理工程师审核通过。 随后分包单位组织了3名符合相关专业要求的专家及参建各方相关人员召开论证会。 主体结构施工期间，施工单位安全主管部门进行施工升降机安全专项检查，对该项目升降机的限位装置、防护设施、安装、验收与使用等保证项目进行了全数检查，均符合要求。 施工过程中，建设单位要求施工单位在3层进行了样板间施工，并对样板间室内环境污染物浓度进行检测，检测结果合格：工程交付使用前对室内环境污染物浓度检测时，施工单位以样板间已检测合格为由将抽检房间数量减半，共抽检7间，经检测甲醛浓度超标：施工单位查找原因并采取措施后对原检测的7间房间再次进行检测，检测结果合格，施工单位认为达标，监理单位提出不同意见，要求调整抽检的房间并增加抽检房间数量。 | 76. A residential project, construction area of 21600 square meters, excavation depth of 6.5m, two underground floors, twelve above-ground floors, raft foundation, cast-in-place reinforced concrete frame structure. The project site is narrow. There is a six-story brick-concrete residential building at 4m on the north side of the upper entrance of the foundation pit. There is a heat pipeline buried 2m on the east side. The project is constructed by a general contracting unit, and the foundation pit support is undertaken by a professional subcontracting unit. Before the foundation pit support construction, the professional subcontracting unit has prepared a special construction plan for foundation pit support. After the approval and signature of the technical person in charge of the subcontracting unit, it is reported to the general contracting unit for the record and directly reported to the supervision unit for review. Subsequently, the subcontracting unit organized 3 experts who met the relevant professional requirements and the relevant personnel of the participating parties to hold a demonstration meeting. During the construction of the main structure, the safety competent department of the construction unit carried out a special inspection on the safety of the construction lift, and the limiting device, protective facilities, installation, acceptance and use of the lift of the project were all inspected, which met the requirements. During the construction process, the construction unit requires the construction unit to carry out the model room construction on the third floor, and test the concentration of indoor environmental pollutants in the model room, and the test result is qualified: When the concentration of indoor environmental pollutants is tested before the project is delivered, the construction unit will halve the number of sampling rooms on the grounds that the sample room has been tested and qualified, a total of 7 were sampled, and the formaldehyde concentration exceeded the standard by detection: After the construction unit finds out the cause and takes measures, the original 7 rooms are tested again, the test results are qualified, the construction unit thinks that the standard, the supervision unit puts forward different opinions, and requires to adjust the sampling rooms and increase the number of sampling rooms. | 76、 施工单位对室内环境污染物抽检房间数量减半的理由是否成立？并说明理由。 | 76. Is the reason for the construction unit to halve the number of rooms for sampling indoor environmental pollutants valid? And explain the reasons.
CBQ-077 | 77、沿海地区某群体住宅工程，包含整体地下室、8栋住宅楼、1栋物业配套楼以及小区公共区域园林绿化等，业态丰富、体量较大，工期暂定3.5年。 招标文件约定：采用工程量清单计价模式，要求投标单位充分考虑风险，特别是通用措施费用项目均应以有竞争力的报价投标，最终按固定总价签订施工合同招标过程中，投标单位针对招标文件不妥之处向建设单位申请答疑，建设单位修订招标文件后履行完招标流程，最终确定施工单位A中标，并参照《建设工程施工合同（示范文本）》（GF-2017-0201）与A单位签订施工承包合同。 施工合同中允许总承包单位自行合法分包，A单位将物业配套楼整体分包给B单位，公共区域园林绿化分包给C单位（该单位未在施工现场设立项目管理机构，委托劳务队伍进行施工）、自行施工的8栋住宅楼的主体结构工程劳务（含钢筋、混凝土主材与模架等周转材料）分包给D单位，上述单位均具备相应施工资质。 地方建设行政主管部门在例行检查时提出不符合《建筑工程施工转包违法分包等违法行为认定查处管理办法》（建市（2014）118号）相关规定要求整改。 | 77. The residential project of a group in the coastal area, including the whole basement, 8 residential buildings, 1 property supporting building and garden greening in the public area of the community, is rich in forms and large in volume. The construction period is tentatively set at 3.5 years. The bidding documents agree: Adopt the bill of quantities valuation mode, requiring the tenderer to fully consider the risks, especially the general measures cost projects should be bid with competitive quotations, and finally sign the construction contract at a fixed total price. In the bidding process, the tenderer applies to the construction unit for questions and answers in view of the improper bidding documents, and the construction unit completes the bidding process after revising the bidding documents. Finally determine that the construction unit A wins the bid, and sign the construction contract with the construction unit A by referring to the Construction Contract (Model Text) of the Construction Project (GF-2017-0201). In the construction contract, the general contractor is allowed to legally subcontract on its own. Unit A subcontracts the whole supporting building of the property to Unit B, and the landscaping of the public area to Unit C (the unit has not set up a project management organization at the construction site. Entrust the labor team to carry out the construction), the main structure engineering services of 8 residential buildings constructed by themselves (including steel bars, concrete main materials and mold frames and other turnover materials) are subcontracted to Unit D, and the above units have the corresponding construction qualifications. The local construction administrative department in the routine inspection does not meet the "construction subcontracting illegal subcontracting and other illegal acts of the identification and investigation of management measures" (Jianchi (2014) 118) the relevant provisions of rectification. | 77、指出本工程招标文件中不妥之处，并写出相应正确做法 | 77. Point out the inadequacies in the bidding documents of this project, and write out the corresponding correct practices
CBQ-078 | 78、沿海地区某群体住宅工程，包含整体地下室、8栋住宅楼、1栋物业配套楼以及小区公共区域园林绿化等，业态丰富、体量较大，工期暂定3.5年。 招标文件约定：采用工程量清单计价模式，要求投标单位充分考虑风险，特别是通用措施费用项目均应以有竞争力的报价投标，最终按固定总价签订施工合同招标过程中，投标单位针对招标文件不妥之处向建设单位申请答疑，建设单位修订招标文件后履行完招标流程，最终确定施工单位A中标，并参照《建设工程施工合同（示范文本）》（GF-2017-0201）与A单位签订施工承包合同。 施工合同中允许总承包单位自行合法分包，A单位将物业配套楼整体分包给B单位，公共区域园林绿化分包给C单位（该单位未在施工现场设立项目管理机构，委托劳务队伍进行施工）、自行施工的8栋住宅楼的主体结构工程劳务（含钢筋、混凝土主材与模架等周转材料）分包给D单位，上述单位均具备相应施工资质。 地方建设行政主管部门在例行检查时提出不符合《建筑工程施工转包违法分包等违法行为认定查处管理办法》（建市（2014）118号）相关规定要求整改。 | 78. The residential project of a group in the coastal area, including the whole basement, 8 residential buildings, 1 property supporting building and garden greening in the public area of the community, is rich in forms and large in volume. The construction period is tentatively set at 3.5 years. The bidding documents agree: Adopt the bill of quantities valuation mode, requiring the tenderer to fully consider the risks, especially the general measures cost projects should be bid with competitive quotations, and finally sign the construction contract at a fixed total price. In the bidding process, the tenderer applies to the construction unit for questions and answers in view of the improper bidding documents, and the construction unit completes the bidding process after revising the bidding documents. Finally determine that the construction unit A wins the bid, and sign the construction contract with the construction unit A by referring to the Construction Contract (Model Text) of the Construction Project (GF-2017-0201). In the construction contract, the general contractor is allowed to legally subcontract on its own. Unit A subcontracts the whole supporting building of the property to Unit B, and the landscaping of the public area to Unit C (the unit has not set up a project management organization at the construction site. Entrust the labor team to carry out the construction), the main structure engineering services of 8 residential buildings constructed by themselves (including steel bars, concrete main materials and mold frames and other turnover materials) are subcontracted to Unit D, and the above units have the corresponding construction qualifications. The local construction administrative department in the routine inspection does not meet the "construction subcontracting illegal subcontracting and other illegal acts of the identification and investigation of management measures" (Jianchi (2014) 118) the relevant provisions of rectification. | 78、根据《建筑工程施工转包违法分包等违法行为认定查处管理办法》（建市（2014）118号）上述分包行为中哪些属于违法行为？并说明相应理由？ | 78. According to the Measures for the Identification and Administration of Illegal Acts such as Illegal Subcontracting of Construction Engineering Construction (Jianshi (2014) No. 118), which of the above subcontracting acts are illegal acts? And explain the corresponding reasons?
CBQ-079 | 79、某办公楼工程，建筑面积2400㎡，地下一层，地上十二层，筏板基础，钢筋混凝土框架结构，砌筑工程采用蒸压灰砂砖砌体。建设单位依据招投标程序选定了监理单位及施工总承包单位，并约定部分工作允许施工总承包单位自行分包。 施工总承包单位进场后，项目质量总监组织编制了项目检测试验计划，经施工企业技术部门审批后实施。建设单位指出检测试验计划编制与审批程序错误，要求项目部调整后重新报审，第一批钢筋原材到场，项目试验员会同监理单位见证人员进行见证取样，对钢筋原材相关性能指标进行复检。 本工程混凝土设计强度等级：梁板均为C30，地下部分框架柱为C40，地上部分框架柱为C35。施工总承包单位针对梁柱核心区（梁柱节点部位）混凝土浇筑制定了专项技术措施：拟采取竖向结构与水平结构连续浇筑的方式；地下部分梁柱核心区中，沿柱边设置隔离措施，先浇筑框架柱及隔离措施内的C40混凝土，再浇筑隔离措施外的C30梁板混凝土：地上部分，先浇筑柱C35混凝土至梁柱核心区底面（梁底标高处），梁柱核心区与梁、板一起浇筑C30混凝土。针对上述技术措施，监理工程师提出异议，要求修正其中的错误和补充必要的确认程序，现场才能实施。工程完工后，施工总承包单位自检合格，再由专业监理工程师组织了竣工预验收。根据预验收所提出问题施工单位整改完毕，总监理工程师及时向建设单位申请工程竣工验收，建设单位认为程序不妥拒绝验收。 项目通过竣工验收后，建设单位、监理单位、设计单位、勘察单位、施工总承包单位与分包单位会商竣工资料移交方式，建设单位要求各参建单位分别向监理单位移交资料，监理单位收集齐全后统一向城建档案馆移交。监理单位以不符合程序为由拒绝。 | 79. An office building project, construction area of 2400 square meters, one underground layer, twelve floors on the ground, raft foundation, reinforced concrete frame structure, masonry works using autoclaved lime sand brick masonry. The construction unit selected the supervision unit and the general contractor of the construction unit according to the bidding procedure, and agreed that some work allowed the general contractor of the construction unit to subcontract by itself. After the general contractor enters the site, the project quality director shall organize the preparation of the project testing and testing plan, which shall be implemented after approval by the technical department of the construction enterprise. The construction unit pointed out that the preparation and approval procedures of the test plan were wrong, and required the project department to re-submit the test after adjustment. The first batch of raw steel bars were on the scene, and the project tester and the witness personnel of the supervision unit carried out witness sampling and re-checked the related performance indicators of the raw steel bars. The design strength grade of the concrete in this project is C30 for the beams and plates, C40 for the underground part of the frame column and C35 for the above-ground part of the frame column. The general contractor of construction has formulated special technical measures for concrete pouring in the core area of beams and columns (joint parts of beams and columns) : It is proposed to adopt the mode of continuous pouring of vertical structure and horizontal structure; In the core area of the underground part of the beam and column, the isolation measures are set along the side of the column, and the C40 concrete inside the frame column and the isolation measures is poured first, and then the C30 concrete outside the isolation measures is poured. In the above part, the column C35 concrete is poured first to the bottom surface of the core area of the beam and column (the elevation of the bottom of the beam), and the C30 concrete is poured together with the beam and plate in the core area of the beam and column. In view of the above technical measures, the supervision engineer raised objections and asked to correct the errors and supplement the necessary confirmation procedures before it could be implemented on site. After the completion of the project, the general contractor of the construction passed the self-inspection, and then the professional supervision engineer organized the pre-acceptance of the completion. According to the problems raised by the pre-acceptance, the construction unit has completed the rectification, and the chief supervision engineer applies to the construction unit for the acceptance of the project completion in time. The construction unit thinks that the procedure is improper and refuses the acceptance. After the project passes the completion acceptance, the construction unit, the supervision unit, the design unit, the survey unit, the general contractor of the construction unit and the subcontractor shall discuss the transfer method of the completion data. The construction unit requires each participating unit to hand over the data to the supervision unit respectively, and the supervision unit shall uniformly hand over the data to the urban construction archives after collecting all the data. The supervision unit refuses on the grounds that it does not conform to the procedure. | 79、指出竣工验收程序有哪些不妥之处？并写出相应正确做法。 | 79. What are the inadequacies in the completion acceptance procedures? And write out the correct practices accordingly.
CBQ-080 | 80、某办公楼工程，建筑面积2400㎡，地下一层，地上十二层，筏板基础，钢筋混凝土框架结构，砌筑工程采用蒸压灰砂砖砌体。建设单位依据招投标程序选定了监理单位及施工总承包单位，并约定部分工作允许施工总承包单位自行分包。 施工总承包单位进场后，项目质量总监组织编制了项目检测试验计划，经施工企业技术部门审批后实施。建设单位指出检测试验计划编制与审批程序错误，要求项目部调整后重新报审，第一批钢筋原材到场，项目试验员会同监理单位见证人员进行见证取样，对钢筋原材相关性能指标进行复检。 本工程混凝土设计强度等级：梁板均为C30，地下部分框架柱为C40，地上部分框架柱为C35。施工总承包单位针对梁柱核心区（梁柱节点部位）混凝土浇筑制定了专项技术措施：拟采取竖向结构与水平结构连续浇筑的方式；地下部分梁柱核心区中，沿柱边设置隔离措施，先浇筑框架柱及隔离措施内的C40混凝土，再浇筑隔离措施外的C30梁板混凝土：地上部分，先浇筑柱C35混凝土至梁柱核心区底面（梁底标高处），梁柱核心区与梁、板一起浇筑C30混凝土。针对上述技术措施，监理工程师提出异议，要求修正其中的错误和补充必要的确认程序，现场才能实施。工程完工后，施工总承包单位自检合格，再由专业监理工程师组织了竣工预验收。根据预验收所提出问题施工单位整改完毕，总监理工程师及时向建设单位申请工程竣工验收，建设单位认为程序不妥拒绝验收。 项目通过竣工验收后，建设单位、监理单位、设计单位、勘察单位、施工总承包单位与分包单位会商竣工资料移交方式，建设单位要求各参建单位分别向监理单位移交资料，监理单位收集齐全后统一向城建档案馆移交。监理单位以不符合程序为由拒绝。 | 80. An office building project, construction area of 2400 square meters, one underground layer, twelve floors on the ground, raft foundation, reinforced concrete frame structure, masonry works using autoclaved lime sand brick masonry. The construction unit selected the supervision unit and the general contractor of the construction unit according to the bidding procedure, and agreed that some work allowed the general contractor of the construction unit to subcontract by itself. After the general contractor enters the site, the project quality director shall organize the preparation of the project testing and testing plan, which shall be implemented after approval by the technical department of the construction enterprise. The construction unit pointed out that the preparation and approval procedures of the test plan were wrong, and required the project department to re-submit the test after adjustment. The first batch of raw steel bars were on the scene, and the project tester and the witness personnel of the supervision unit carried out witness sampling and re-checked the related performance indicators of the raw steel bars. The design strength grade of the concrete in this project is C30 for the beams and plates, C40 for the underground part of the frame column and C35 for the above-ground part of the frame column. The general contractor of construction has formulated special technical measures for concrete pouring in the core area of beams and columns (joint parts of beams and columns) : It is proposed to adopt the mode of continuous pouring of vertical structure and horizontal structure; In the core area of the underground part of the beam and column, the isolation measures are set along the side of the column, and the C40 concrete inside the frame column and the isolation measures is poured first, and then the C30 concrete outside the isolation measures is poured. In the above part, the column C35 concrete is poured first to the bottom surface of the core area of the beam and column (the elevation of the bottom of the beam), and the C30 concrete is poured together with the beam and plate in the core area of the beam and column. In view of the above technical measures, the supervision engineer raised objections and asked to correct the errors and supplement the necessary confirmation procedures before it could be implemented on site. After the completion of the project, the general contractor of the construction passed the self-inspection, and then the professional supervision engineer organized the pre-acceptance of the completion. According to the problems raised by the pre-acceptance, the construction unit has completed the rectification, and the chief supervision engineer applies to the construction unit for the acceptance of the project completion in time. The construction unit thinks that the procedure is improper and refuses the acceptance. After the project passes the completion acceptance, the construction unit, the supervision unit, the design unit, the survey unit, the general contractor of the construction unit and the subcontractor shall discuss the transfer method of the completion data. The construction unit requires each participating unit to hand over the data to the supervision unit respectively, and the supervision unit shall uniformly hand over the data to the urban construction archives after collecting all the data. The supervision unit refuses on the grounds that it does not conform to the procedure. | 80、针对本工程的参建各方，写出正确的竣工资料移交程序。 | 80. Write out the correct completion data transfer procedure for all parties involved in the project.
CBQ-081 | 81、某企业新建办公楼工程，地下一层，地上十六楼，建筑高度55m，地下建筑面积3000㎡，总建筑面积21000㎡人，现浇混凝土框架结构。一层大厅高12m，长32m，大厅处有3道后张预应力混凝土梁。合同约定：“…工程开工时间为2016年7月1日，竣工日期为2017年10月31日，总工期488天；冬期停工35天；弱电、幕墙工程由专业分包单位施工…”总包单位与幕墙单位签订了专业分包合同。 总承包单位在施工现场安装了一台塔吊用于垂直运输，在结构、外墙装修施工时，采用落地双排扣件式钢管脚手架。 结构施工阶段，施工单位相关部门对项目安全进行检査，发现外脚手架存在安全隐患，责令项目部立即整改。 大厅后张预应力混凝土梁浇筑完成25天后，生产经理凭经验判定混凝土强度已达到设计要求，随即安排作业人员拆除了梁底模板并准备进行预应力张拉。 外墙装饰完成后，施工单位安排工人拆除外脚手架。在拆除过程中，上部钢管意外坠落击中下部施工人员，造成1名工人死亡。 | 81. A new office building project of an enterprise, one underground floor, sixteen floors on the ground, building height of 55m, underground construction area of 3000 square meters, total construction area of 21000 square meters, cast-in-place concrete frame structure. The first floor hall is 12m high, 32m long, and there are 3 post-tensioned prestressed concrete beams in the hall. The contract states: "... The commencement date of the project is July 1, 2016, and the completion date is October 31, 2017, with a total construction period of 488 days; 35 days of suspension in winter; Weak current, curtain wall works by professional subcontracting units..." The general contractor has signed a professional subcontract with the curtain wall unit. The general contractor installed a tower crane for vertical transportation on the construction site, and adopted the double-row steel pipe scaffold for the construction of the structure and exterior wall. During the construction phase, the relevant departments of the construction unit inspected the safety of the project and found that there were safety hazards in the external scaffolding, and ordered the project department to immediately rectify the situation. 25 days after the completion of the hall post-tensioned prestressed concrete beam pouring, the production manager determined that the strength of the concrete had met the design requirements based on experience, and immediately arranged the operators to remove the beam bottom formwork and prepare for prestressed tension. After the exterior wall decoration was completed, the construction unit arranged workers to remove the outer scaffolding. During the demolition process, the upper steel pipe accidentally fell and hit the lower construction workers, killing one worker. | 81、总包单位与专业分包单位签订分包合同过程中，应重点落实哪些安全管理方面的工作？ | 81. In the process of signing a subcontract between the general contractor and the professional subcontractor, what safety management work should be focused on?
CBQ-082 | 82、某企业新建办公楼工程，地下一层，地上十六楼，建筑高度55m，地下建筑面积3000㎡，总建筑面积21000㎡人，现浇混凝土框架结构。一层大厅高12m，长32m，大厅处有3道后张预应力混凝土梁。合同约定：“…工程开工时间为2016年7月1日，竣工日期为2017年10月31日，总工期488天；冬期停工35天；弱电、幕墙工程由专业分包单位施工…”总包单位与幕墙单位签订了专业分包合同。 总承包单位在施工现场安装了一台塔吊用于垂直运输，在结构、外墙装修施工时，采用落地双排扣件式钢管脚手架。 结构施工阶段，施工单位相关部门对项目安全进行检査，发现外脚手架存在安全隐患，责令项目部立即整改。 大厅后张预应力混凝土梁浇筑完成25天后，生产经理凭经验判定混凝土强度已达到设计要求，随即安排作业人员拆除了梁底模板并准备进行预应力张拉。 外墙装饰完成后，施工单位安排工人拆除外脚手架。在拆除过程中，上部钢管意外坠落击中下部施工人员，造成1名工人死亡。 | 82. A new office building project of an enterprise, one underground floor, sixteen floors on the ground, building height of 55m, underground construction area of 3000 square meters, total construction area of 21000 square meters, cast-in-place concrete frame structure. The first floor hall is 12m high, 32m long, and there are 3 post-tensioned prestressed concrete beams in the hall. The contract states: "... The commencement date of the project is July 1, 2016, and the completion date is October 31, 2017, with a total construction period of 488 days; 35 days of suspension in winter; Weak current, curtain wall works by professional subcontracting units..." The general contractor has signed a professional subcontract with the curtain wall unit. The general contractor installed a tower crane for vertical transportation on the construction site, and adopted the double-row steel pipe scaffold for the construction of the structure and exterior wall. During the construction phase, the relevant departments of the construction unit inspected the safety of the project and found that there were safety hazards in the external scaffolding, and ordered the project department to immediately rectify the situation. 25 days after the completion of the hall post-tensioned prestressed concrete beam pouring, the production manager determined that the strength of the concrete had met the design requirements based on experience, and immediately arranged the operators to remove the beam bottom formwork and prepare for prestressed tension. After the exterior wall decoration was completed, the construction unit arranged workers to remove the outer scaffolding. During the demolition process, the upper steel pipe accidentally fell and hit the lower construction workers, killing one worker. | 82、预应力混凝土梁底模拆除工作有哪些不妥之处？并说明理由。 | 82. What are the disadvantages of the demolition work of prestressed concrete beam bottom mold? And explain the reasons.
CBQ-083 | 83、某办公楼工程，框架结构，钻孔灌注桩基础，地下一层，地上20层，总建筑面积25000m2，其中地下建筑面积3000m2，施工单位中标后与建设单位签订了施工承包合同，合同约定：“…至2014年6月15日竣工，工期目标470日历天：质量目标合格：主要材料由施工单位自行采购：因建设单位原因导致工期延误，工期顺延，每延误一天支付施工单位10000元/天的延误费…”。地下室结构完成，施工单位自检合格后，项目负责人立即组织总监理工程师及建设单位，勘察单位，设计单位项目负责人进行地基基础分部验收。 | 83. An office building project, frame structure, bored pile foundation, one underground layer, 20 floors on the ground, a total construction area of 25000m2, of which the underground construction area of 3000m2, the construction unit signed a construction contract with the construction unit after winning the bid, the contract agreed: "... To the completion of June 15, 2014, the construction period target 470 calendar days: quality objectives qualified: the main materials by the construction unit to purchase: due to the construction unit caused by the delay, the construction period is extended, each day of delay to pay the construction unit 10000 yuan/day delay fee..." . After the basement structure is completed and the construction unit passes the self-inspection, the project leader immediately organizes the chief supervision engineer and the project leader of the construction unit, the survey unit and the design unit to carry out the acceptance of the foundation division. | 83、本工程地基基础分部工程的验收程序有哪些不妥之处？并说明理由。 | 83. What are the inadequacies in the acceptance procedures of the foundation subdivision of this project? And explain the reasons.
CBQ-084 | 84、某办公楼工程，框架结构，钻孔灌注桩基础，地下一层，地上20层，总建筑面积25000m2，其中地下建筑面积3000m2，施工单位中标后与建设单位签订了施工承包合同，合同约定：“…至2014年6月15日竣工，工期目标470日历天：质量目标合格：主要材料由施工单位自行采购：因建设单位原因导致工期延误，工期顺延，每延误一天支付施工单位10000元/天的延误费…”。地下室结构完成，施工单位自检合格后，项目负责人立即组织总监理工程师及建设单位，勘察单位，设计单位项目负责人进行地基基础分部验收。 | 84. An office building project, frame structure, bored pile foundation, one underground layer, 20 floors on the ground, a total construction area of 25000m2, of which the underground construction area of 3000m2, the construction unit signed a construction contract with the construction unit after winning the bid, the contract agreed: "... To the completion of June 15, 2014, the construction period target 470 calendar days: quality objectives qualified: the main materials by the construction unit to purchase: due to the construction unit caused by the delay, the construction period is extended, each day of delay to pay the construction unit 10000 yuan/day delay fee..." . After the basement structure is completed and the construction unit passes the self-inspection, the project leader immediately organizes the chief supervision engineer and the project leader of the construction unit, the survey unit and the design unit to carry out the acceptance of the foundation division. | 84、除采取组织措施外，施工进度控制措施还有哪几种措施? | 84. In addition to taking organizational measures, what kinds of measures are there to control the construction progress?
CBQ-085 | 85、某写字楼工程，建筑面积86840m2，建筑高度40m，地下一层，基坑深度4.5m，地上十一层，钢筋混凝土框架结构。 施工单位中标后组建了项目部，并与项目部签订了项目目标管理责任书。基坑开挖前，施工单位委托具备相应资质的第三方对基坑工程进行现场检测，监测单位编制了监测方案，经建设方、监理方认可后开始施工。 项目部进行质量检查时，发现现场安装完成的木模板内有铅丝及碎木屑，责令项目部进行整改。 隐蔽工程验收合格后，施工单位填报了浇筑申请单，监理工程师签字确认。施工班组将水平输送泵管固定在脚手架小横杆上，采用振动棒倾斜于混凝土内由近及远、分层浇筑，监理工程师发现后责令停工整改。 | 85. An office building project, construction area of 86840m2, building height of 40m, underground layer, foundation pit depth of 4.5m, 11 floors on the ground, reinforced concrete frame structure. After winning the bid, the construction unit set up the project department, and signed the project target management responsibility letter with the project department. Before the excavation of foundation pit, the construction unit entrusts the third party with corresponding qualifications to carry out on-site testing of foundation pit engineering, and the monitoring unit prepares the monitoring plan, and the construction begins after the approval of the construction party and the supervisor. When the project department conducted quality inspection, it found that there were lead wire and wood chips in the wood formwork installed on the site, and ordered the project department to make rectification. After passing the acceptance of the concealed works, the construction unit filled in the pouring application form, and the supervision engineer signed for confirmation. The construction team fixed the horizontal conveying pump pipe on the small cross bar of the scaffold, and used the vibrator to tilt the concrete from near to far and poured in layers. After the supervision engineer found it, he ordered to stop work for rectification. | 85、本工程在基坑检测管理工作中有哪些不妥之处？并说明理由 | 85. What are the inadequacies in the excavation detection and management work of this project? And explain the reasons
CBQ-086 | 86、某写字楼工程，建筑面积86840m2，建筑高度40m，地下一层，基坑深度4.5m，地上十一层，钢筋混凝土框架结构。 施工单位中标后组建了项目部，并与项目部签订了项目目标管理责任书。基坑开挖前，施工单位委托具备相应资质的第三方对基坑工程进行现场检测，监测单位编制了监测方案，经建设方、监理方认可后开始施工。 项目部进行质量检查时，发现现场安装完成的木模板内有铅丝及碎木屑，责令项目部进行整改。 隐蔽工程验收合格后，施工单位填报了浇筑申请单，监理工程师签字确认。施工班组将水平输送泵管固定在脚手架小横杆上，采用振动棒倾斜于混凝土内由近及远、分层浇筑，监理工程师发现后责令停工整改。 | 86. An office building project, construction area of 86840m2, building height of 40m, underground layer, foundation pit depth of 4.5m, 11 floors on the ground, reinforced concrete frame structure. After winning the bid, the construction unit set up the project department, and signed the project target management responsibility letter with the project department. Before the excavation of foundation pit, the construction unit entrusts the third party with corresponding qualifications to carry out on-site testing of foundation pit engineering, and the monitoring unit prepares the monitoring plan, and the construction begins after the approval of the construction party and the supervisor. When the project department conducted quality inspection, it found that there were lead wire and wood chips in the wood formwork installed on the site, and ordered the project department to make rectification. After passing the acceptance of the concealed works, the construction unit filled in the pouring application form, and the supervision engineer signed for confirmation. The construction team fixed the horizontal conveying pump pipe on the small cross bar of the scaffold, and used the vibrator to tilt the concrete from near to far and poured in layers. After the supervision engineer found it, he ordered to stop work for rectification. | 86、在浇筑混凝土工作中，施工班组的做法有哪些不妥之处？并说明正确做法。 | 86. In the concrete pouring work, what is the improper practice of the construction team? And explain the correct way.
CBQ-087 | 87、某新建商用群体建设项目，地下二层，地上八层，现浇钢筋混凝土框架结构，桩筏基础，建筑面积88000㎡。某施工单位中标后组建项目部进场施工，在项目现场搭设临时办公室、各类加工车间、库房、食堂和宿舍等临时设施；并根据场地实际情况，在现场临时设施区域内设置了环形消防通道、消火栓、消防供水池等消防设施。 施工单位在每月例行的安全生产与文明施工巡查中，对照《建筑施工安全检查标准》（JGJ 59-2011）中“文明施工检查评分表”的保证项目逐一进行检查；经统计，现场生产区临时设施总面积超过了1200㎡，检查组认为现场临时设施区域内消防设施配备不齐全，要求项目部整改。 针对地下室200mm厚的无梁楼盖，项目部编制了模板及支撑架专项施工方案。方案中采用扣件式钢管支撑架体系，支撑架立杆纵横向间距均为1600mm，扫地杆距地面约150mm，每步设置纵横向水平杆，步距为1500mm，立杆伸出顶层水平杆的长度控制在150mm-300mm，顶托螺杆插入立杆的长度不小于150mm、伸出立杆的长度控制在500mm以内。 在装饰装修阶段，项目部使用钢管和扣件临时搭设了一个移动式操作平台用于顶棚装置装修作业。该操作平台的台面面积8.64㎡，台面距楼地面高4.6m。 | 87. A new commercial group construction project, two underground floors, eight floors on the ground, cast-in-place reinforced concrete frame structure, pile raft foundation, construction area 88000 square meters. After a construction unit won the bid, the project department was set up for construction, and temporary facilities such as temporary offices, various processing workshops, warehouses, canteens and dormitories were set up on the project site. And according to the actual situation of the site, fire protection facilities such as ring fire passage, fire hydrant and fire supply pool are set up in the temporary facilities area. In the monthly routine inspection of safety production and civilized construction, the construction unit checks the guarantee items of "civilized construction inspection rating Table" in the "Safety Inspection Standard for Building Construction" (JGJ 59-2011) one by one; According to statistics, the total area of temporary facilities in the production area of the site exceeds 1200 square meters, and the inspection team believes that the fire protection facilities in the temporary facilities area of the site are not complete, requiring the project department to rectify. For the 200mm thick beamless floor in the basement, the project department has prepared a special construction plan for the formwork and support frame. In the scheme, fastener type steel pipe support frame system is adopted, the vertical and horizontal spacing of the vertical pole of the support frame is 1600mm, the sweeping rod is about 150mm from the ground, each step is set up vertical and horizontal rods, the step distance is 1500mm, the length of the vertical rod extending out of the top level rod is controlled within 150mm-300mm. The length of the top support screw inserted into the vertical rod is not less than 150mm, and the length of the extended vertical rod is controlled within 500mm. In the decoration stage, the project department used steel pipes and fasteners to temporarily set up a mobile operating platform for the decoration of the ceiling device. The countertop area of the operating platform is 8.64 square meters, and the countertop is 4.6m high from the ground of the building. | 87、针对本项目生产区临时设施总面积情况，在生产区临时设施区域内还应增设哪些消防器材或设施？ | 87. According to the total area of temporary facilities in the production area of the project, what fire fighting equipment or facilities should be added in the temporary facilities area of the production area?
CBQ-088 | 88、某新建商用群体建设项目，地下二层，地上八层，现浇钢筋混凝土框架结构，桩筏基础，建筑面积88000㎡。某施工单位中标后组建项目部进场施工，在项目现场搭设临时办公室、各类加工车间、库房、食堂和宿舍等临时设施；并根据场地实际情况，在现场临时设施区域内设置了环形消防通道、消火栓、消防供水池等消防设施。 施工单位在每月例行的安全生产与文明施工巡查中，对照《建筑施工安全检查标准》（JGJ 59-2011）中“文明施工检查评分表”的保证项目逐一进行检查；经统计，现场生产区临时设施总面积超过了1200㎡，检查组认为现场临时设施区域内消防设施配备不齐全，要求项目部整改。 针对地下室200mm厚的无梁楼盖，项目部编制了模板及支撑架专项施工方案。方案中采用扣件式钢管支撑架体系，支撑架立杆纵横向间距均为1600mm，扫地杆距地面约150mm，每步设置纵横向水平杆，步距为1500mm，立杆伸出顶层水平杆的长度控制在150mm-300mm，顶托螺杆插入立杆的长度不小于150mm、伸出立杆的长度控制在500mm以内。 在装饰装修阶段，项目部使用钢管和扣件临时搭设了一个移动式操作平台用于顶棚装置装修作业。该操作平台的台面面积8.64㎡，台面距楼地面高4.6m。 | 88. A new commercial group construction project, two underground floors, eight floors on the ground, cast-in-place reinforced concrete frame structure, pile raft foundation, construction area 88000 square meters. After a construction unit won the bid, the project department was set up for construction, and temporary facilities such as temporary offices, various processing workshops, warehouses, canteens and dormitories were set up on the project site. And according to the actual situation of the site, fire protection facilities such as ring fire passage, fire hydrant and fire supply pool are set up in the temporary facilities area. In the monthly routine inspection of safety production and civilized construction, the construction unit checks the guarantee items of "civilized construction inspection rating Table" in the "Safety Inspection Standard for Building Construction" (JGJ 59-2011) one by one; According to statistics, the total area of temporary facilities in the production area of the site exceeds 1200 square meters, and the inspection team believes that the fire protection facilities in the temporary facilities area of the site are not complete, requiring the project department to rectify. For the 200mm thick beamless floor in the basement, the project department has prepared a special construction plan for the formwork and support frame. In the scheme, fastener type steel pipe support frame system is adopted, the vertical and horizontal spacing of the vertical pole of the support frame is 1600mm, the sweeping rod is about 150mm from the ground, each step is set up vertical and horizontal rods, the step distance is 1500mm, the length of the vertical rod extending out of the top level rod is controlled within 150mm-300mm. The length of the top support screw inserted into the vertical rod is not less than 150mm, and the length of the extended vertical rod is controlled within 500mm. In the decoration stage, the project department used steel pipes and fasteners to temporarily set up a mobile operating platform for the decoration of the ceiling device. The countertop area of the operating platform is 8.64 square meters, and the countertop is 4.6m high from the ground of the building. | 88、指出本项目模板及支撑架专项施工方案中的不妥之处，并分别写出正确做法。 | 88. Point out the improper place in the special construction plan of the project template and support frame, and write out the correct method respectively.
CBQ-089 | 89、某现浇钢筋混凝土框架-剪力墙结构办公楼工程，地下一层，地上十六层，建筑面积18600㎡，基坑开挖深度5.5m。该工程由某施工单位总承包，其中基坑支护工程由专业分包单位承担施工。 在基坑支护工程施工前，分包单位编制了基坑支护安全专项施工方案，经分包单位技术负责人审批后组织专家论证。监理机构认为专项施工方案及专家论证均不符合规定，不同意进行论证。 在二层的墙体模板拆除后，监理工程师巡视发现局部存在较严重蜂窝孔洞质量缺陷，指令按照《混凝土结构工程施工规范》（GB 50666-2011）的规定进行修正。 主体结构施工至十层时，项目部在例行安全检查中发现五层楼板有2处（一处为短边尺寸200mm的孔口，一处为尺寸1600mm×2600mm的洞口）安全防护措施不符合规定，责令现场立即整改。 结构封顶后，在总监理工程师组织参建方进行主体结构分部工程验收前，监理工程师审核发现施工单位提交的报验资料所涉及的分项不全，指令补充后重新报审。 | 89. A cast-in-place reinforced concrete frame - shear wall structure office building project, one underground floor, sixteen floors on the ground, construction area of 18600 square meters, foundation pit excavation depth of 5.5m. The project is contracted by a construction unit, of which the foundation pit support engineering is undertaken by a professional subcontractor. Before the construction of foundation pit support engineering, the subcontractor has prepared a special construction plan for foundation pit support safety, and organized experts to demonstrate it after the approval of the technical person in charge of the subcontractor. The supervision agency thinks that the special construction plan and the expert demonstration are not in line with the regulations, and does not agree to demonstrate. After the removal of the wall formwork on the second floor, the supervision engineer found that there were serious quality defects in the local honeycomb holes, and the instructions were amended in accordance with the provisions of the "Code for Construction of Concrete Structure Engineering" (GB 50666-2011). When the main structure was constructed to the tenth floor, the project department found in the routine safety inspection that there were two safety protection measures in the five-floor slab (one was a hole with a short side size of 200mm, and the other was a hole with a size of 1600mm×2600mm) that did not meet the regulations, and ordered immediate rectification on the site. After the structure is capped, before the chief supervision engineer organized the participating party to carry out the acceptance of the main structure division project, the supervision engineer found that the items involved in the inspection materials submitted by the construction unit were incomplete, and ordered them to be resubmitted for approval after supplementation. | 89、指出本工程的基坑支护安全专项施工方案审批手续及专家论证组织中的错误之处，并分别写出正确做法。 | 89. Points out the approval procedures of the foundation pit support safety special construction scheme of this project and the mistakes in the organization of expert demonstration, and write out the correct methods respectively.
CBQ-090 | 90、某现浇钢筋混凝土框架-剪力墙结构办公楼工程，地下一层，地上十六层，建筑面积18600㎡，基坑开挖深度5.5m。该工程由某施工单位总承包，其中基坑支护工程由专业分包单位承担施工。 在基坑支护工程施工前，分包单位编制了基坑支护安全专项施工方案，经分包单位技术负责人审批后组织专家论证。监理机构认为专项施工方案及专家论证均不符合规定，不同意进行论证。 在二层的墙体模板拆除后，监理工程师巡视发现局部存在较严重蜂窝孔洞质量缺陷，指令按照《混凝土结构工程施工规范》（GB 50666-2011）的规定进行修正。 主体结构施工至十层时，项目部在例行安全检查中发现五层楼板有2处（一处为短边尺寸200mm的孔口，一处为尺寸1600mm×2600mm的洞口）安全防护措施不符合规定，责令现场立即整改。 结构封顶后，在总监理工程师组织参建方进行主体结构分部工程验收前，监理工程师审核发现施工单位提交的报验资料所涉及的分项不全，指令补充后重新报审。 | 90. A cast-in-place reinforced concrete frame - shear wall structure office building project, one underground floor, sixteen floors on the ground, construction area of 18600 square meters, foundation pit excavation depth of 5.5m. The project is contracted by a construction unit, of which the foundation pit support engineering is undertaken by a professional subcontractor. Before the construction of foundation pit support engineering, the subcontractor has prepared a special construction plan for foundation pit support safety, and organized experts to demonstrate it after the approval of the technical person in charge of the subcontractor. The supervision agency thinks that the special construction plan and the expert demonstration are not in line with the regulations, and does not agree to demonstrate. After the removal of the wall formwork on the second floor, the supervision engineer found that there were serious quality defects in the local honeycomb holes, and the instructions were amended in accordance with the provisions of the "Code for Construction of Concrete Structure Engineering" (GB 50666-2011). When the main structure was constructed to the tenth floor, the project department found in the routine safety inspection that there were two safety protection measures in the five-floor slab (one was a hole with a short side size of 200mm, and the other was a hole with a size of 1600mm×2600mm) that did not meet the regulations, and ordered immediate rectification on the site. After the structure is capped, before the chief supervision engineer organized the participating party to carry out the acceptance of the main structure division project, the supervision engineer found that the items involved in the inspection materials submitted by the construction unit were incomplete, and ordered them to be resubmitted for approval after supplementation. | 90、本工程主体结构分部工程验收资料应包含哪些分项工程。 | 90. What sub-projects should be included in the acceptance data of the main structure of the project.
CBQ-091 | 91、某施工单位在中标某高档办公楼工程后，与建设单位按照《建设工程施工合同（示范文本）》（GF-2013-0201）签订了施工总承包合同。合同中约定总承包单位将装饰装修、幕墙等分部分项工程进行专业分包。 施工过程中，监理单位下发针对专业分包工程范围内墙面装饰装修做法的设计变更指令。在变更指令下发后的第10天，专业分包单位向监理工程师提出该项变更的估价申请。监理工程师审核时发现计算有误，要求施工单位修改。于变更指令下发后的第17天，监理工程师再次收到变更估价申请，经审核无误后提交建设单位，但一直未收到建设单位的审批意见。次月底，施工单位再上报已完工程进度款支付时，包含了经监理工程师审核、已完成的该项变更所对应的费用，建设单位以未审批同意为由予以扣除，并提出变更设计增加款项只能在竣工结算前最后一期的进度款中支付。 该工程完工后，建设单位指令施工单位组织相关人员进行竣工预验收，并要求总监理工程师在预验收通过后立即组织参建各方相关人员进行竣工验收。建设行政主管部门提出验收组织安排有误，责令建设单位予以更正。 竣工验收通过后，总承包单位、专业分包单位分别将各自施工范围的工程资料移交给监理机构，监理机构整理后将施工资料与工程监理资料一并向当地城建档案管理部门移交，被城建档案管理部门以资料移交程序错误为由予以拒绝。 | 91. After winning the bid for a high-grade office building project, a construction unit signed a general contract with the construction unit in accordance with the Construction Contract (Model Text) of the Construction Project (GF-2013-0201). In the contract, it is agreed that the general contractor will carry out professional subcontracting for some projects such as decoration and decoration and curtain wall. During the construction process, the supervision unit will issue a design change instruction for the wall decoration and decoration practices within the scope of professional subcontracting projects. On the 10th day after the change instruction is issued, the professional subcontracting unit shall submit an application for valuation of the change to the supervision engineer. During the review, the supervising engineer found that the calculation was wrong and asked the construction unit to revise it. On the 17th day after the change instruction was issued, the supervision engineer received the application for change valuation again and submitted it to the construction unit after examination and verification, but has not received the approval comments from the construction unit. At the end of the next month, when the construction unit reports the progress payment of the completed project again, it includes the corresponding cost of the completed change reviewed by the supervision engineer, and the construction unit deducts it on the grounds of non-approval and approval, and proposes that the increase payment for the change design can only be paid in the last phase of progress payment before the completion settlement. After the completion of the project, the construction unit instructs the construction unit to organize relevant personnel to carry out the completion pre-acceptance, and requires the chief supervision engineer to organize relevant personnel of the participating parties to carry out the completion acceptance immediately after the pre-acceptance is passed. The competent administrative department of construction shall put forward that the organization arrangement of acceptance inspection is wrong and order the construction unit to correct it. After the completion of the acceptance, the general contractor and the specialized subcontracting unit will respectively hand over the project data of their respective construction scope to the supervision institution, and the supervision institution will hand over the construction data together with the project supervision data to the local urban construction archives management department after sorting out, which is refused by the urban construction archives management department on the grounds that the data transfer procedure is wrong. | 91、在墙面装饰装修做法的设计变更估价申请报送及进度款支付过程中都存在哪些不妥之处？并分别写出正确做法。 | 91. What are the inadequacies in the process of submitting the application for design change evaluation of the wall decoration practice and paying the progress payment? And write out the correct practices respectively.
CBQ-092 | 92、某施工单位在中标某高档办公楼工程后，与建设单位按照《建设工程施工合同（示范文本）》（GF-2013-0201）签订了施工总承包合同。合同中约定总承包单位将装饰装修、幕墙等分部分项工程进行专业分包。 施工过程中，监理单位下发针对专业分包工程范围内墙面装饰装修做法的设计变更指令。在变更指令下发后的第10天，专业分包单位向监理工程师提出该项变更的估价申请。监理工程师审核时发现计算有误，要求施工单位修改。于变更指令下发后的第17天，监理工程师再次收到变更估价申请，经审核无误后提交建设单位，但一直未收到建设单位的审批意见。次月底，施工单位再上报已完工程进度款支付时，包含了经监理工程师审核、已完成的该项变更所对应的费用，建设单位以未审批同意为由予以扣除，并提出变更设计增加款项只能在竣工结算前最后一期的进度款中支付。 该工程完工后，建设单位指令施工单位组织相关人员进行竣工预验收，并要求总监理工程师在预验收通过后立即组织参建各方相关人员进行竣工验收。建设行政主管部门提出验收组织安排有误，责令建设单位予以更正。 竣工验收通过后，总承包单位、专业分包单位分别将各自施工范围的工程资料移交给监理机构，监理机构整理后将施工资料与工程监理资料一并向当地城建档案管理部门移交，被城建档案管理部门以资料移交程序错误为由予以拒绝。 | 92. After winning the bid for a high-grade office building project, a construction unit signed a general contract with the construction unit in accordance with the Construction Contract (Model Text) of the Construction Project (GF-2013-0201). In the contract, it is agreed that the general contractor will carry out professional subcontracting for some projects such as decoration and decoration and curtain wall. During the construction process, the supervision unit will issue a design change instruction for the wall decoration and decoration practices within the scope of professional subcontracting projects. On the 10th day after the change instruction is issued, the professional subcontracting unit shall submit an application for valuation of the change to the supervision engineer. During the review, the supervising engineer found that the calculation was wrong and asked the construction unit to revise it. On the 17th day after the change instruction was issued, the supervision engineer received the application for change valuation again and submitted it to the construction unit after examination and verification, but has not received the approval comments from the construction unit. At the end of the next month, when the construction unit reports the progress payment of the completed project again, it includes the corresponding cost of the completed change reviewed by the supervision engineer, and the construction unit deducts it on the grounds of non-approval and approval, and proposes that the increase payment for the change design can only be paid in the last phase of progress payment before the completion settlement. After the completion of the project, the construction unit instructs the construction unit to organize relevant personnel to carry out the completion pre-acceptance, and requires the chief supervision engineer to organize relevant personnel of the participating parties to carry out the completion acceptance immediately after the pre-acceptance is passed. The competent administrative department of construction shall put forward that the organization arrangement of acceptance inspection is wrong and order the construction unit to correct it. After the completion of the acceptance, the general contractor and the specialized subcontracting unit will respectively hand over the project data of their respective construction scope to the supervision institution, and the supervision institution will hand over the construction data together with the project supervision data to the local urban construction archives management department after sorting out, which is refused by the urban construction archives management department on the grounds that the data transfer procedure is wrong. | 92、针对建设行政主管部门责令改正的验收组织错误，本工程的竣工预验收应由谁来组织？施工单位哪些人必须参加？本工程的竣工验收应由谁进行组织？ | 92. Who shall organize the pre-completion acceptance of the project in view of the errors in the acceptance organization ordered to be corrected by the construction administrative department? Who must participate in the construction unit? Who shall organize the completion and acceptance of the project?
CBQ-093 | 93、某学校活动中心工程，现浇钢筋混凝土框架结构，地上六层，地下二层，采用自然通风。 在施工过程中，发生了下列事件： 事件一：在基础底板混凝土浇筑前，监理工程师督查施工单位的技术管理工作，要求施工单位按规定检查混凝土运输单。并做好混凝土扩展度测定等工作。全部工作完成并确认无误后，方可浇筑混凝土。 事件二：主体结构施工过程中，施工单位对进场的钢筋按国家现行有关标准抽样检验了抗拉强度、屈服强度、结构施工至四层时，施工单位进场一批72吨18螺纹钢筋，在此前因同厂家、同牌号的该规格钢筋已连续三次进场检验均一次检验合格，施工单位对此批钢筋仅抽取一组试件送检，监理工程师认为取样组数不足。 事件三：建筑节能分部工程验收时，由施工单位项目经理主持、施工单位质量负责人以及相关专业的质量检查员参加，总监理工程师认为该验收主持及参加人员均不满足规定，要求重新组织验收。 事件四：该工程交付使用7天后，建设单位委托有资质的检验单位进行室内环境污染，在对室内环境的甲醛、苯、氨、TVOC浓度进行检测时，检测人员将房间对外门窗关闭30分钟后进行检测，在对室内环境的氡浓度进行检测时，检测人员将房间对外门窗关闭12小时后进行检测。 | 93. A school activity center project, cast-in-place reinforced concrete frame structure, six floors above ground, two underground, using natural ventilation. During the construction process, the following events occurred: Event one: Before the concrete was poured on the foundation floor, the supervising engineer supervised the technical management work of the construction unit and asked the construction unit to check the concrete transport bill according to the regulations. And do a good job of concrete expansion measurement and other work. After all the work is completed and confirmed, the concrete can be poured. Event Two: During the construction of the main structure, the construction unit sampled the tensile strength and yield strength of the steel bars entering the site according to the current relevant national standards. When the structure was constructed to the fourth floor, the construction unit entered the site for a batch of 72 tons of 18-thread steel bars. The specifications of the steel bars of the same manufacturer and the same brand had been inspected for three consecutive times and passed the inspection. The construction unit only extracts a group of specimens for inspection, and the supervision engineer thinks that the number of sampling groups is insufficient. Event 3: Building energy conservation division project acceptance, by the construction unit project manager, the construction unit quality person in charge and related professional quality inspectors to participate in, the chief supervision engineer believes that the acceptance of the host and participants do not meet the requirements, require to re-organize the acceptance. Event four: 7 days after the project was put into use, the construction unit commissioned a qualified inspection unit to carry out indoor environmental pollution. When testing the concentrations of formaldehyde, benzene, ammonia and TVOC in the indoor environment, the inspection personnel should close the external doors and Windows of the room for 30 minutes for testing. When testing the radon concentration in the indoor environment, The inspection personnel shall close the external doors and Windows of the room for 12 hours before testing. | 93、事件一中，除已列出的工作内容外，施工单位针对混凝土运输单还要做哪些技术管理与测定工作？ | 93. In Event 1, in addition to the work content already listed, what technical management and measurement work should the construction unit do for the concrete transport order?
CBQ-094 | 94、某学校活动中心工程，现浇钢筋混凝土框架结构，地上六层，地下二层，采用自然通风。 在施工过程中，发生了下列事件： 事件一：在基础底板混凝土浇筑前，监理工程师督查施工单位的技术管理工作，要求施工单位按规定检查混凝土运输单。并做好混凝土扩展度测定等工作。全部工作完成并确认无误后，方可浇筑混凝土。 事件二：主体结构施工过程中，施工单位对进场的钢筋按国家现行有关标准抽样检验了抗拉强度、屈服强度、结构施工至四层时，施工单位进场一批72吨18螺纹钢筋，在此前因同厂家、同牌号的该规格钢筋已连续三次进场检验均一次检验合格，施工单位对此批钢筋仅抽取一组试件送检，监理工程师认为取样组数不足。 事件三：建筑节能分部工程验收时，由施工单位项目经理主持、施工单位质量负责人以及相关专业的质量检查员参加，总监理工程师认为该验收主持及参加人员均不满足规定，要求重新组织验收。 事件四：该工程交付使用7天后，建设单位委托有资质的检验单位进行室内环境污染，在对室内环境的甲醛、苯、氨、TVOC浓度进行检测时，检测人员将房间对外门窗关闭30分钟后进行检测，在对室内环境的氡浓度进行检测时，检测人员将房间对外门窗关闭12小时后进行检测。 | 94. A school activity center project, cast-in-place reinforced concrete frame structure, six floors above ground, two underground, using natural ventilation. During the construction process, the following events occurred: Event one: Before the concrete was poured on the foundation floor, the supervising engineer supervised the technical management work of the construction unit and asked the construction unit to check the concrete transport bill according to the regulations. And do a good job of concrete expansion measurement and other work. After all the work is completed and confirmed, the concrete can be poured. Event Two: During the construction of the main structure, the construction unit sampled the tensile strength and yield strength of the steel bars entering the site according to the current relevant national standards. When the structure was constructed to the fourth floor, the construction unit entered the site for a batch of 72 tons of 18-thread steel bars. The specifications of the steel bars of the same manufacturer and the same brand had been inspected for three consecutive times and passed the inspection. The construction unit only extracts a group of specimens for inspection, and the supervision engineer thinks that the number of sampling groups is insufficient. Event 3: Building energy conservation division project acceptance, by the construction unit project manager, the construction unit quality person in charge and related professional quality inspectors to participate in, the chief supervision engineer believes that the acceptance of the host and participants do not meet the requirements, require to re-organize the acceptance. Event four: 7 days after the project was put into use, the construction unit commissioned a qualified inspection unit to carry out indoor environmental pollution. When testing the concentrations of formaldehyde, benzene, ammonia and TVOC in the indoor environment, the inspection personnel should close the external doors and Windows of the room for 30 minutes for testing. When testing the radon concentration in the indoor environment, The inspection personnel shall close the external doors and Windows of the room for 12 hours before testing. | 94、事件四中，有哪些不妥之处？并分别说明正确说法。 | 94. In event 4, what are the inadequacies? And explain the correct statement respectively.
CBQ-095 | 95、某建设单位投资新建办公楼，建筑面积8000m2，钢筋混凝土框架结构，地上八层，招标文件规定，本工程实行设计、采购、施工的总承包交钥匙方式。土建、水电、通风空调、内外装饰、消防、园林景观等工程全部由中标单位负责组织施工。经公开招投标，A施工总承包单位中标，双方签订的工程总承包合同中约定：合同工期为10个月，质量目标为合格。在合同履行过程中，发生了下列事件中：事件一、A施工总承包单位中标后，按照“设计、采购、施工”的总承包方式开展相关工作。事件二、A施工总承包单位在项目管理过程中，与F劳务公司进行了主体结构劳务分包洽谈，约定将模板和脚手架费用计入承包总价，并签订了劳务分包合同。经建设单位同意，A施工总承包单位将玻璃幕墙工程分包给B专业分包单位施工。A施工总承包单位自行将通风空调工程分包给C专业分包单位施工。C专业分包单位按照分包工程合同总价收取8%的管理费后分包D专业分包单位。事件三、A施工总承包单位对工程中标造价进行分析，费用情况如下：分部分项工程费4800万元，措施项目费576万元，暂列金额222万元，风险费260万元，规费64万元，税金218万元。事件四、A施工总承包单位按照风险管理要求，重点对某风险点的施工方案、工程机械等方面制定了专项策划，明确了分工、责任人及应对措施等管控流程。 | 95. A construction unit invested in a new office building, construction area of 8000m2, reinforced concrete frame structure, eight floors above the ground, the bidding document stipulates that the project implementation of design, procurement, construction of the general contract turnkey. Civil construction, water and electricity, ventilation and air conditioning, interior and exterior decoration, fire protection, garden landscape and other projects are all organized by the winning unit. After public bidding and bidding, the general contractor of A won the bid. As agreed in the general contract signed by both parties, the contract period is 10 months and the quality target is qualified. During the performance of the contract, the following events occurred: Event 1. After the general contractor of A wins the bid, relevant work is carried out according to the general contracting method of "design, procurement and construction". Event 2. In the process of project management, the general contractor of A conducted labor subcontracting negotiations with F Labor Service Company for the main structure, agreed to include the costs of formwork and scaffolding in the total contract price, and signed the labor subcontracting contract. With the consent of the construction unit, the general contractor of A subcontracted the glass curtain wall project to the professional subcontractor of B for construction. The general contractor of A will subcontract the ventilation and air conditioning project to the professional subcontractor of C. C professional subcontractor shall subcontract D professional subcontractor after charging 8% management fee according to the total contract price of the subcontracted project. Event 3. The general contractor of A construction analyzed the winning cost of the project, and the costs were as follows: the sub-project cost of 48 million yuan, the measure project cost of 5.76 million yuan, the provisional amount of 2.22 million yuan, the risk fee of 2.6 million yuan, the fee of 640,000 yuan, and the tax of 2.18 million yuan. In accordance with the requirements of risk management, the general contractor of A construction has formulated a special plan for the construction scheme and construction machinery of a certain risk point, and has defined the control process such as division of labor, responsible persons and countermeasures. | 95、事件二中，哪些分包行为属于违法分包，并分别说明理由。 | 95. In Event 2, which subcontracting acts are illegal subcontracting, and explain the reasons respectively.
CBQ-096 | 96、某建设单位投资新建办公楼，建筑面积8000m2，钢筋混凝土框架结构，地上八层，招标文件规定，本工程实行设计、采购、施工的总承包交钥匙方式。土建、水电、通风空调、内外装饰、消防、园林景观等工程全部由中标单位负责组织施工。经公开招投标，A施工总承包单位中标，双方签订的工程总承包合同中约定：合同工期为10个月，质量目标为合格。在合同履行过程中，发生了下列事件中：事件一、A施工总承包单位中标后，按照“设计、采购、施工”的总承包方式开展相关工作。事件二、A施工总承包单位在项目管理过程中，与F劳务公司进行了主体结构劳务分包洽谈，约定将模板和脚手架费用计入承包总价，并签订了劳务分包合同。经建设单位同意，A施工总承包单位将玻璃幕墙工程分包给B专业分包单位施工。A施工总承包单位自行将通风空调工程分包给C专业分包单位施工。C专业分包单位按照分包工程合同总价收取8%的管理费后分包D专业分包单位。事件三、A施工总承包单位对工程中标造价进行分析，费用情况如下：分部分项工程费4800万元，措施项目费576万元，暂列金额222万元，风险费260万元，规费64万元，税金218万元。事件四、A施工总承包单位按照风险管理要求，重点对某风险点的施工方案、工程机械等方面制定了专项策划，明确了分工、责任人及应对措施等管控流程。 | 96. A construction unit invested in a new office building, construction area of 8000m2, reinforced concrete frame structure, eight floors above the ground, the bidding document stipulates that the project implementation of design, procurement, construction of the general contract turnkey. Civil construction, water and electricity, ventilation and air conditioning, interior and exterior decoration, fire protection, garden landscape and other projects are all organized by the winning unit. After public bidding and bidding, the general contractor of A won the bid. As agreed in the general contract signed by both parties, the contract period is 10 months and the quality target is qualified. During the performance of the contract, the following events occurred: Event 1. After the general contractor of A wins the bid, relevant work is carried out according to the general contracting method of "design, procurement and construction". Event 2. In the process of project management, the general contractor of A conducted labor subcontracting negotiations with F Labor Service Company for the main structure, agreed to include the costs of formwork and scaffolding in the total contract price, and signed the labor subcontracting contract. With the consent of the construction unit, the general contractor of A subcontracted the glass curtain wall project to the professional subcontractor of B for construction. The general contractor of A will subcontract the ventilation and air conditioning project to the professional subcontractor of C. C professional subcontractor shall subcontract D professional subcontractor after charging 8% management fee according to the total contract price of the subcontracted project. Event 3. The general contractor of A construction analyzed the winning cost of the project, and the costs were as follows: the sub-project cost of 48 million yuan, the measure project cost of 5.76 million yuan, the provisional amount of 2.22 million yuan, the risk fee of 2.6 million yuan, the fee of 640,000 yuan, and the tax of 2.18 million yuan. In accordance with the requirements of risk management, the general contractor of A construction has formulated a special plan for the construction scheme and construction machinery of a certain risk point, and has defined the control process such as division of labor, responsible persons and countermeasures. | 96、事件四中，A施工总承包单位进行的风险管理属于施工风险的哪个类型？施工风险管理过程中包括哪些方面？ | 96. In Event 4, which type of construction risk does the risk management carried out by the general contractor A belong to? What aspects does the construction risk management process include?
CBQ-097 | 97、某新建综合楼工程，现浇钢筋混凝土框架结构，地下一层，地上十层，建筑檐口高度45米，某建筑工程公司中标后成立项目部进场组织施工。 在施工过程中，发生了下列事件： 事件一：根据施工组织设计的安排，施工高峰期现场同时使用机械设备达到8台。项目土建施工员仅编制了安全用电和电气防火措施报送给项目监理工程师。监理工程师认为存在多处不妥，要求整改。 事件二：施工过程中，项目部要求安全员对现场固定式塔吊的安全装置进行全面检查，但安全员仅对塔吊的力矩限制器、爬梯护圈、小车断绳保护装置、小车断轴保护装置进行了安全检查。 事件三：公司例行安全检查中，发现施工区域主出入通道处多种类型的安全警示牌布置混乱，要求项目部按规定要求从左到右正确排列。 | 97. A new comprehensive building project, cast-in-place reinforced concrete frame structure, one floor underground, ten floors above the ground, building cornice height of 45 meters, a construction engineering company after winning the bid to set up the project department to organize construction. During the construction process, the following events occurred: Event 1: According to the arrangement of the construction organization design, 8 mechanical equipment were used on site at the same time during the construction peak. The civil construction workers of the project only prepared safe electricity consumption and electrical fire prevention measures and submitted them to the project supervision engineer. The supervising engineer thought that there were many inadequacies and requested rectification. Event 2: During the construction process, the project department required the safety officer to carry out a comprehensive inspection of the safety devices of the fixed tower crane on site, but the safety officer only carried out a safety inspection of the tower crane's moment limiter, ladder protection ring, car broken rope protection device, and car broken shaft protection device. Event 3: In the routine safety inspection of the company, it was found that the layout of various types of safety warning signs at the main access road in the construction area was chaotic, and the project department was required to arrange them correctly from left to right according to the regulations. | 97、事件一中，存在哪些不妥之处？并分别说明理由。 | 97. What are the inadequacies in Event 1? And explain the reasons respectively.
CBQ-098 | 98、某新建综合楼工程，现浇钢筋混凝土框架结构，地下一层，地上十层，建筑檐口高度45米，某建筑工程公司中标后成立项目部进场组织施工。 在施工过程中，发生了下列事件： 事件一：根据施工组织设计的安排，施工高峰期现场同时使用机械设备达到8台。项目土建施工员仅编制了安全用电和电气防火措施报送给项目监理工程师。监理工程师认为存在多处不妥，要求整改。 事件二：施工过程中，项目部要求安全员对现场固定式塔吊的安全装置进行全面检查，但安全员仅对塔吊的力矩限制器、爬梯护圈、小车断绳保护装置、小车断轴保护装置进行了安全检查。 事件三：公司例行安全检查中，发现施工区域主出入通道处多种类型的安全警示牌布置混乱，要求项目部按规定要求从左到右正确排列。 | 98. A new comprehensive building project, cast-in-place reinforced concrete frame structure, one floor underground, ten floors above the ground, building cornice height of 45 meters, a construction engineering company after winning the bid to set up the project department to organize construction. During the construction process, the following events occurred: Event 1: According to the arrangement of the construction organization design, 8 mechanical equipment were used on site at the same time during the construction peak. The civil construction workers of the project only prepared safe electricity consumption and electrical fire prevention measures and submitted them to the project supervision engineer. The supervising engineer thought that there were many inadequacies and requested rectification. Event 2: During the construction process, the project department required the safety officer to carry out a comprehensive inspection of the safety devices of the fixed tower crane on site, but the safety officer only carried out a safety inspection of the tower crane's moment limiter, ladder protection ring, car broken rope protection device, and car broken shaft protection device. Event 3: In the routine safety inspection of the company, it was found that the layout of various types of safety warning signs at the main access road in the construction area was chaotic, and the project department was required to arrange them correctly from left to right according to the regulations. | 98、事件三中，安全警示牌通常都有哪些类型？各种类型的安全警示牌按一排布置时，从左到右的正确排列顺序是什么？ | 98. In Event 3, what are the usual types of safety warning signs? When the various types of safety signs are arranged in a row, what is the correct order from left to right?
CBQ-099 | 99、某高校新建新校区，包括办公楼、教学楼、科研中心，后勤服务楼、学生宿舍等多个单体建筑，由某建筑工程公司进行该群体工程的施工建设。其中，科研中心工程为现浇钢筋混凝土框架结构，地上十层，地下二层，建筑檐口高度45米，由于有超大尺寸的特殊设备，设置在地下二层的试验室为两层通高；结构设计图纸说明中规定地下室的后浇带需待主楼结构封顶后才能封闭。在施工过程中，发生了下列事件：事件一；施工单位进场后，针对群体工程进度计划的不同编制对象。施工单位分别编制了各种施工进度计划，上报监理机构审批后作为参建各方进度控制的依据。事件二；在科研中心工程的后浇带施工方案中，明确指出： 梁、板的模板与支架整体一次性搭设完毕； 在楼板浇筑混凝土前，后浇带两侧用快易收口网进行分隔、上部用木板遮盖防止落入物料；两侧混凝土结构强度达到拆模条件后，拆除所有底模及支架，后浇带位置处重新搭设支架及模板，两侧进行回顶，待主体结构封顶后浇筑后浇带混凝土。监理工程师认为方案中上述做法存在不妥，责令改正后重新报审。针对后浇带混凝土填充作业，监理工程师要求施工单位提前将施工技术要点以书面形式对作业人员进行交底。 | 99. A new campus of a university, including office buildings, teaching buildings, scientific research centers, logistics service buildings, student dormitories and other single buildings, by a construction engineering company to carry out the construction of the group project. Among them, the research center project for castin reinforced concrete frame structure, ten floors on the ground, the underground two floors, the building cornice height of 45 meters, due to the special equipment of large size, set in the underground two floors of the laboratory for two double-height; In the structural design drawings, the post-pouring belt of the basement is required to be closed after the main building structure is capped. During the construction process, the following events occurred: Event 1; After the construction unit enters the field, the different preparation objects of the group project schedule plan are targeted. The construction unit shall prepare various construction schedule plans respectively, which shall be submitted to the supervision authority for approval as the basis for the progress control of the participating parties. Event II; In the construction scheme of the post-casting belt of the scientific research center project, it is clearly pointed out that: the template and support of the beam and plate are set up at one time; Before concrete is poured on the floor, both sides of the post-pouring belt are separated by quick and easy closure net, and the upper part is covered with wood to prevent falling into the material; After the strength of the concrete structure on both sides reaches the demoulding conditions, all the bottom molds and supports are removed, and the supports and formwork are re-installed at the position of the post-pouring belt, and the post-pouring belt concrete is poured on both sides after the main structure is capped. The supervision engineer thinks that the above practices in the scheme are inappropriate, and orders them to be corrected and resubmitted for review. For the concrete filling operation of the post cast belt, the supervision engineer requires the construction unit to disclose the key points of construction technology to the operators in writing in advance. | 99、事件一中，按照编制对象不同，本工程应编制哪些施工进度计划？ | 99. Event 1, according to the preparation of different objects, which construction progress plan should be prepared in this project?
CBQ-100 | 100、某高校新建新校区，包括办公楼、教学楼、科研中心，后勤服务楼、学生宿舍等多个单体建筑，由某建筑工程公司进行该群体工程的施工建设。其中，科研中心工程为现浇钢筋混凝土框架结构，地上十层，地下二层，建筑檐口高度45米，由于有超大尺寸的特殊设备，设置在地下二层的试验室为两层通高；结构设计图纸说明中规定地下室的后浇带需待主楼结构封顶后才能封闭。在施工过程中，发生了下列事件：事件一；施工单位进场后，针对群体工程进度计划的不同编制对象。施工单位分别编制了各种施工进度计划，上报监理机构审批后作为参建各方进度控制的依据。事件二；在科研中心工程的后浇带施工方案中，明确指出： 梁、板的模板与支架整体一次性搭设完毕； 在楼板浇筑混凝土前，后浇带两侧用快易收口网进行分隔、上部用木板遮盖防止落入物料；两侧混凝土结构强度达到拆模条件后，拆除所有底模及支架，后浇带位置处重新搭设支架及模板，两侧进行回顶，待主体结构封顶后浇筑后浇带混凝土。监理工程师认为方案中上述做法存在不妥，责令改正后重新报审。针对后浇带混凝土填充作业，监理工程师要求施工单位提前将施工技术要点以书面形式对作业人员进行交底。 | 100. A new campus of a university, including office buildings, teaching buildings, scientific research centers, logistics service buildings, student dormitories and other single buildings, by a construction engineering company to carry out the construction of the group project. Among them, the research center project for castin reinforced concrete frame structure, ten floors on the ground, the underground two floors, the building cornice height of 45 meters, due to the special equipment of large size, set in the underground two floors of the laboratory for two double-height; In the structural design drawings, the post-pouring belt of the basement is required to be closed after the main building structure is capped. During the construction process, the following events occurred: Event 1; After the construction unit enters the field, the different preparation objects of the group project schedule plan are targeted. The construction unit shall prepare various construction schedule plans respectively, which shall be submitted to the supervision authority for approval as the basis for the progress control of the participating parties. Event II; In the construction scheme of the post-casting belt of the scientific research center project, it is clearly pointed out that: the template and support of the beam and plate are set up at one time; Before concrete is poured on the floor, both sides of the post-pouring belt are separated by quick and easy closure net, and the upper part is covered with wood to prevent falling into the material; After the strength of the concrete structure on both sides reaches the demoulding conditions, all the bottom molds and supports are removed, and the supports and formwork are re-installed at the position of the post-pouring belt, and the post-pouring belt concrete is poured on both sides after the main structure is capped. The supervision engineer thinks that the above practices in the scheme are inappropriate, and orders them to be corrected and resubmitted for review. For the concrete filling operation of the post cast belt, the supervision engineer requires the construction unit to disclose the key points of construction technology to the operators in writing in advance. | 100、事件三中，后浇带施工方案中有哪些不妥之处？ | 100. In event 3, what are the inadequacies in the construction plan of the post-casting belt?

## Experts for formulating MCQs
Experts for formulating the 2,225 multiple-choice questions
No. | Affiliation | Role | Experience | The course they taught | If holds registered construction engineer qualifications | If teaches CEM course | Research Direction | If has experience in creating multiple-choice questions
E03 | Jiangsu University | Professor | 13 years | Construction Engineering Management | √ | √ | Quality control | √
E06 | Nanjing Forestry University | Associate professor | 8 years | Construction Engineering Management | √ | √ | Occupational health, safety and environment management | √
E07 | China University of Mining and Technology | Associate professor | 5 years | Construction Engineering Management | √ | √ | Schedule control | √
E08 | Yangzhou University | Lecturer | 8 years | Construction Engineering Management | √ | √ | Information management | √
E09 | Tianjin University | Lecturer | 6 years | Construction Engineering Management | √ | √ | Contracts and contract management | √
E10 | Hohai University | Lecturer | 4 years | Construction Engineering Management | √ | √ | Occupational health, safety and environment management | √
E16 | Tongji University | Professor | 20 years | Construction Engineering Management | √ | √ | Organization and management | √
E17 | Jiangsu University of Science and Technology University | Professor | 15 years | Construction Engineering Management | √ | √ | Quality control | √
E18 | Zhejiang University of Finance and Economics | Professor | 11 years | Construction Engineering Management | √ | √ | Contracts and contract management | √
E19 | Nanjing University of Aeronautics and Astronautics | Associate professor | 13 years | Construction Engineering Management | √ | √ | Cost management | √
E20 | Nanjing Institute of Technology | Associate professor | 3 years | Construction Engineering Management | √ | √ | Occupational health, safety and environment management | √
E21 | Central South University | Lecturer | 5 years | Construction Engineering Management | √ | √ | Cost management | √

## Experts for CBQ review
Experts rating the answers to each case-based question
No. | Affiliation | Role | Experience | Field
E07 | China University of Mining and Technology | Associate professor | 5 years | Construction Engineering Management
E06 | Nanjing Forestry University | Associate professor | 8 years | Construction Engineering Management
E01 | Southeast University | Professor | 22 years | Construction Engineering Management